## 1. Stats
Sell.do Onboarding Pipeline - Statistics
Pipeline 27474 ¦ 83 open deals ¦ Snapshot 18-Jun-2026
Ageing = days since deal CREATED (created_at). Movement = days since last activity (separate metric).
By Owner
Category | Count
Muntazar Mhate | 19
Venkat Viswavardhan | 14
Shweta Gouda | 14
Sahil Jane | 12
Raahul Ramanan R | 8
Sanket Nampalliwar | 6
Atharva Patil | 5
Shubham Dubey | 5
Total | 83
By Pipeline Stage
Category | Count
Open | 19
Kickoff Done | 3
Onboarding In Progress | 50
Pending on Customer | 11
Under Usage Tracking | 0
Total | 83
Deal Ageing = days since CREATED (created_at)
Category | Count
<14 days | 28
14-30 days | 15
30-60 days | 24
60-90 days | 3
90-180 days | 6
180+ days | 7
Total | 83
Movement = days since LAST ACTIVITY
Category | Count
<=5 days (healthy) | 50
5-7 days | 5
7-15 days | 4
15-30 days | 9
30+ days | 15
Total | 83
Touch cadence = days since LAST NOTE (interim proxy until meetings are logged)
Category | Count
<=5 days (OK) | 28
6-10 days | 4
11-15 days | 3
16-30 days | 12
31+ days | 9
Never (no note) | 27
Total | 83
Meetings ON DEALS (not yet logged - format ready going forward)
Category | Count
Deals with a meeting logged on the deal | 0
Meeting scheduled/conducted within 5 days | 0
NO meeting logged (team to start logging) | 83
Risk & Data-Quality Flags
Category | Count
No activity 5+ days (your risk rule) | 33
No notes logged at all | 27
Target go-live date already breached | 40
Customer 'Yet to sign up' | 19
No future follow-up task | 58
Has an OVERDUE task | 22
Billed Amount field blank | 54
Estimated Value populated | 0
Meetings linked to these onboarding deals | 0

## 2. Exec Summary (CEO-CRO)
Onboarding Pipeline - Executive Summary
For CEO & CRO ¦ 18-Jun-2026
The headline
83 deals are open in onboarding. Nearly half (40) are already past their committed go-live date, and 33 (40%) have had no activity in 5+ days. Onboarding is meant to run in weeks - 7 deals have been open 180+ days.
The bigger structural issue: the system is not telling the truth. 26 of 83 deals (31%) have zero notes, 80 of 83 have no healthy next task, Billed Amount is blank on 65% and Estimated Value is empty on every deal. We cannot currently see revenue-at-risk in any report.
Where the money is exposed
Cash collected but customer not live ('Yet to sign up' while paid): Raghava Elite Park ~Rs12.1L, Dhanvanthari Rs9.8L (only Rs6.8L received), Greenrich Rs7.06L, Definer Rs5.07L, Sujay Avalon Rs3.56L. Plus uncollected balances: Dhanvanthari ~Rs3.0L and Sandeep ~Rs3.2L outstanding.
Largest single account at risk: Kunwarji Realtors - 150 licenses, Category A, every setup step 'Waiting on customer', go-live already breached, and ZERO notes.
What we are asking leadership to back
1. A weekly onboarding hygiene standard: every open deal must have a LOGGED MEETING (scheduled or conducted) at least every 5 days, a dated note, and a next task; stage moved at each milestone. (Meetings are currently not logged on deals at all.)
2. Make Billed Amount mandatory at deal creation so revenue-at-risk is visible.
3. A 'collections + activation' sweep on the paid-but-dormant accounts above (CRO + Onboarding).
4. De-clutter: delete test/duplicate deals (dummy, 4 'Post Sales' copies, IRA 'Copy') so reporting is real.

## 3. Owner Scorecard
Owner Scorecard - gaps for the Onboarding Head
Counts per owner across the key risk flags. Use for owner 1:1s.
Owner | Open deals | A-grade | Idle 5+ d | No notes | Go-live overdue | Not signed up | No next task | Overdue task | Key gap to address
Muntazar Mhate | 19 | 0 | 3 | 4 | 3 | 5 | 13 | 3 | Highest load (19). Several 'No movement/On hold' (Propleaf, Raado) - decide HOLD vs push.
Venkat Viswavardhan | 14 | 5 | 10 | 4 | 9 | 4 | 10 | 4 | 14 deals incl AI-Calling set stalled on Mcube; i5 & YES Proptech have no notes.
Shweta Gouda | 14 | 0 | 4 | 6 | 1 | 2 | 10 | 4 | 14 deals; many at 'pending training/lead import' - chase customers to close.
Sahil Jane | 12 | 1 | 1 | 3 | 4 | 3 | 8 | 4 | 12 deals, many brand-new with no notes/next task - log first note + kickoff.
Raahul Ramanan R | 8 | 3 | 0 | 0 | 7 | 2 | 6 | 2 | 8 deals; Voora stuck since Feb in Pending-on-Customer; Calicut only has a 'timesheet' note.
Sanket Nampalliwar | 6 | 4 | 5 | 1 | 6 | 1 | 2 | 4 | 6 deals but the most stuck: Shree Auto/Honda (Dec), Dhanvanthari, Kunwarji (150 lic, no notes).
Atharva Patil | 5 | 2 | 5 | 5 | 5 | 1 | 5 | 0 | All 5 are IRIS deals, all idle 30+ d with NO notes; 2 are actually live - just not closed.
Shubham Dubey | 5 | 0 | 5 | 4 | 5 | 1 | 4 | 1 | 5 deals = mostly Post-Sales duplicates + 'dummy'. Clean these up.
TOTAL | 83 | 15 | 33 | 27 | 40 | 19 | 58 | 22

## 4. Deal-Level Tracker
Deal-Level Tracker - for the Onboarding Head to action
Meeting columns are ready for when the team logs meetings on deals; none are logged yet (marked 'None logged'). Target: a meeting scheduled/conducted every <=5 days. Interim cadence uses last note.
Deal ID | Deal Name | Owner | Stage | Last activity | Last note date | Days since note | Has notes | Go-live overdue | Not signed up | Billed (Rs) | Licenses | Cat | Last note / status | Age (created) | Key Next Step (recommended) | Touch cadence (interim, vs 5d) | Last meeting | Next meeting | Mtg <=5d?
3343526 | B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer | 30+ d |  |  | No | Yes |  |  | 6 | A | NO NOTES (but acct signed up & actual go-live 06-Oct recorded - effectively live). | >180 d | Close to 'Handover Complete' - already live (go-live 06-Oct); shouldn't sit in Pending. | Risk-no touch ever | None logged | None logged | No - none logged
3347148 | Definer Properties IRIS | Atharva Patil | Open | 30+ d |  |  | No | Yes |  | 507400 | 10 | B | NO NOTES (acct Active, Rs5.07L paid, still in Open). | >180 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. (re-grade to A) | Risk-no touch ever | None logged | None logged | No - none logged
3650857 | Greenrich Constructions IRIS | Atharva Patil | Open | 30+ d |  |  | No | Yes |  | 705640 | 3 | C | NO NOTES (Rs7.06L paid, all steps Initiated, stuck in Open). | 90-180 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. (re-grade to A) | Risk-no touch ever | None logged | None logged | No - none logged
3334464 | Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress | 30+ d |  |  | No | Yes |  |  |  | A | NO NOTES. | >180 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Risk-no touch ever | None logged | None logged | No - none logged
4197640 | Sujay Avalon IRIS | Atharva Patil | Open | 30+ d |  |  | No | Yes | Yes | 355652 | 3 | C | NO NOTES (Rs3.56L paid, 'Yet to sign up'). | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | Risk-no touch ever | None logged | None logged | No - none logged
3506901 | Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | 30+ d | 04-Jan-26 | 164 | Yes | Yes | Yes | 979400 | 30 | A | Onboarding questionnaire pending from client; all steps waiting on customer. | 90-180 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. Collect balance ~Rs3.0L. | Risk (164d) | None logged | None logged | No - none logged
4230613 | Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done | 30+ d |  |  | No | Yes |  |  | 150 | A | NO NOTES (150 licenses, Cat-A, EVERY setup step 'Waiting on customer'). | 30-60 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Risk-no touch ever | None logged | None logged | No - none logged
4090500 | SANDEEP DWELLERS PVT LTD | Sanket Nampalliwar | Onboarding In Progress | 30+ d | 07-May-26 | 41 | Yes | Yes |  | 373780 | 22 | A | Most tasks complete; SV-form JIRA raised; only Rs52k of Rs3.74L collected. | 60-90 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. Collect balance ~Rs3.2L. | Risk (41d) | None logged | None logged | No - none logged
3304062 | Shree Automotive | Sanket Nampalliwar | Pending on Customer | 30+ d | 08-Dec-25 | 191 | Yes | Yes |  | 104784 | 4 | C | Awaiting client details to start setup; 2 customization JIRAs pushed. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Risk (191d) | None logged | None logged | No - none logged
3304063 | Shree Honda | Sanket Nampalliwar | Pending on Customer | 30+ d | 08-Dec-25 | 191 | Yes | Yes |  | 210983 | 5 | C | Awaiting client details; customization JIRAs pending. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Risk (191d) | None logged | None logged | No - none logged
3439810 | IRA Estate Copy post sale | Shubham Dubey | Onboarding In Progress | 30+ d | 22-Dec-25 | 177 | Yes | Yes |  |  | 9 | C | Post-sale req gathering; follow-up for client data. | >180 d | De-dupe: merge into the primary deal and close this duplicate. | Risk (177d) | None logged | None logged | No - none logged
4262552 | M/S SURI DEVELOPERS Post Sales | Shubham Dubey | Open | 30+ d |  |  | No | Yes |  | 128384 | 2 | C | NO NOTES (post-sale DUP of SURI). | 30-60 d | De-dupe: merge into the primary deal and close this duplicate. | Risk-no touch ever | None logged | None logged | No - none logged
4239798 | Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress | 30+ d |  |  | No | Yes | Yes | 1210680 | 15 | B | NO NOTES (DUP of Raghava EP; Rs12.1L paid, 'Yet to sign up'). | 30-60 d | De-dupe: merge into the primary deal and close this duplicate. | Risk-no touch ever | None logged | None logged | No - none logged
4044687 | dummy | Shubham Dubey | Open | 30+ d |  |  | No | Yes |  |  | 1 | (none) | NO NOTES - test record ('dummy'). | 60-90 d | Delete - test/dummy record. | Risk-no touch ever | None logged | None logged | No - none logged
4233562 | Krishvi Group | Shweta Gouda | Onboarding In Progress | 30+ d |  |  | No | Yes |  | 81184 | 3 | (none) | NO NOTES (Active, go-live 20-May missed). | 30-60 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Risk-no touch ever | None logged | None logged | No - none logged
4325924 | Sujay Global Homes Post Sales | Shubham Dubey | Open | 15-30 d |  |  | No | Yes |  |  |  | C | NO NOTES (post-sale DUP of Sujay Global Homes). | 14-30 d | De-dupe: merge into the primary deal and close this duplicate. | Risk-no touch ever | None logged | None logged | No - none logged
4236338 | The Perfect Leasing | Shweta Gouda | Onboarding In Progress | 15-30 d | 27-May-26 | 21 | Yes |  |  |  |  | Broker | Core done; lead import & Meta pending from customer. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (21d) | None logged | None logged | No - none logged
4144089 | Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress | 15-30 d | 02-Jun-26 | 15 | Yes | Yes |  |  |  | C | Sourcing training done, customer has feedback; WhatsApp blocked on customer meta verification. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to A) | Risk (15d) | None logged | None logged | No - none logged
4147287 | Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | 15-30 d | 01-Jun-26 | 16 | Yes | Yes |  |  |  | A | Most done; sales/pres training pending - customer unavailable (office shifting). | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Risk (16d) | None logged | None logged | No - none logged
4241966 | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | 15-30 d | 21-May-26 | 27 | Yes | Yes |  |  |  | C | Mcube & bot configured, shared with customer - awaiting customer. | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Risk (27d) | None logged | None logged | No - none logged
4233715 | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | 15-30 d | 01-Jun-26 | 16 | Yes | Yes |  |  |  | C | BOT shared for testing; awaiting Mcube number from customer. | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Risk (16d) | None logged | None logged | No - none logged
4233760 | Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress | 15-30 d | 02-Jun-26 | 15 | Yes | Yes |  |  |  | C | Number details shared to Sanket; awaiting AI-calling setup. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (15d) | None logged | None logged | No - none logged
4325921 | Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress | 15-30 d | 01-Jun-26 | 16 | Yes | Yes |  |  |  | C | Priority tasks; source list pending from customer. | 14-30 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to B) | Risk (16d) | None logged | None logged | No - none logged
4204921 | Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress | 15-30 d | 18-May-26 | 30 | Yes | Yes |  |  |  | A | Core done; bulk lead/CP/inventory awaiting files from customer. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (30d) | None logged | None logged | No - none logged
4285334 | True Stone | Sahil Jane | Onboarding In Progress | 7-15 d | 10-Jun-26 | 7 | Yes | Yes |  |  |  | C | Core + training done; property portal/Meta pending. | 14-30 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
4299083 | Brick & Mortar Realty | Shweta Gouda | Onboarding In Progress | 7-15 d | 27-May-26 | 21 | Yes |  |  |  |  | Broker | Core done; sales training missed (customer no-show). | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (21d) | None logged | None logged | No - none logged
4269153 | Northstone Realty | Shweta Gouda | Onboarding In Progress | 7-15 d | 27-May-26 | 21 | Yes |  |  |  |  | Broker | Core done; Meta pending (no leads to import per client). | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (21d) | None logged | None logged | No - none logged
4358959 | YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Open | 7-15 d |  |  | No |  |  |  |  | Broker | NO NOTES (Open stage). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4079157 | Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer | 5-7 d | 25-May-26 | 23 | Yes |  |  |  |  | B | Most tasks complete; near handover. | 60-90 d | Complete pending setup items and progress toward handover. | Risk (23d) | None logged | None logged | No - none logged
4196905 | Pranav Infra & Trade Ventures | Muntazar Mhate | Onboarding In Progress | 5-7 d | 10-May-26 | 38 | Yes |  |  |  |  | B | Core done; bulk lead/inventory pending from customer. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (38d) | None logged | None logged | No - none logged
4364225 | Real Estate Square | Muntazar Mhate | Onboarding In Progress | 5-7 d | 11-Jun-26 | 6 | Yes |  | Yes |  |  | Broker | Priority task list shared; early stage. | <14 d | Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
3968505 | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | 5-7 d | 19-May-26 | 29 | Yes | Yes |  |  |  | A | Most tasks complete; GRE walk-in form feedback implemented. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (29d) | None logged | None logged | No - none logged
4370308 | VAZHRAA NIRMAAN PRIVATE LTD | Venkat Viswavardhan | Open | 5-7 d |  |  | No |  | Yes |  |  | C | NO NOTES (Open). | <14 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | Risk-no touch ever | None logged | None logged | No - none logged
4310934 | 9tothrive | Muntazar Mhate | Onboarding In Progress | <=5 d | 08-Jun-26 | 9 | Yes |  |  |  |  | C | Core done; Google ads/integrations pending. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
4351088 | Aaradhya Fortune Pvt Ltd | Muntazar Mhate | Onboarding In Progress | <=5 d | 18-Jun-26 | 0 | Yes |  |  |  |  | Broker | Most tasks complete incl bulk lead. | <14 d | Complete pending setup items and progress toward handover. | OK | None logged | None logged | No - none logged
4262054 | Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress | <=5 d | 18-Jun-26 | 0 | Yes | Yes |  |  |  | B | Most tasks complete incl training. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK | None logged | None logged | No - none logged
4375344 | Aura Proptech | Muntazar Mhate | Onboarding In Progress | <=5 d | 15-Jun-26 | 2 | Yes |  |  |  |  | C | Kickoff task list shared; early stage. | <14 d | Complete pending setup items and progress toward handover. | OK | None logged | None logged | No - none logged
4246414 | Hakkache Ghar Realty | Muntazar Mhate | Onboarding In Progress | <=5 d | 15-Jun-26 | 2 | Yes |  |  |  |  | C | Core + admin training done; bulk lead pending. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
4377422 | Miva Real Estate | Muntazar Mhate | Open | <=5 d |  |  | No |  | Yes |  |  | C | NO NOTES (Open). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4383150 | Phantom Advisory | Muntazar Mhate | Open | <=5 d |  |  | No |  | Yes |  |  | Broker | NO NOTES (Open). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4275064 | Propleaf | Muntazar Mhate | Onboarding In Progress | <=5 d | 15-Jun-26 | 2 | Yes |  |  |  |  | C | 'No movement from client side. Will check till Wed or put ON HOLD.' | 30-60 d | Customer unresponsive - set a 7-day deadline, then move to 'On Hold' with reason. | OK | None logged | None logged | No - none logged
4336863 | Raado Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | <=5 d | 15-Jun-26 | 2 | Yes |  |  |  |  | C | 'No movement from client side.' | 14-30 d | Customer unresponsive - set a 7-day deadline, then move to 'On Hold' with reason. | OK | None logged | None logged | No - none logged
4386888 | Red Estate Destination Pvt Ltd | Muntazar Mhate | Open | <=5 d |  |  | No |  | Yes |  |  | C | NO NOTES (Open, new). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4299438 | Ribitto Private Limited | Muntazar Mhate | Onboarding In Progress | <=5 d | 18-Jun-26 | 0 | Yes | Yes |  |  |  | C | Most done incl admin training; bulk lead pending. | 14-30 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
4345401 | Sangram Group | Muntazar Mhate | Onboarding In Progress | <=5 d | 18-Jun-26 | 0 | Yes |  |  |  |  | C | Kickoff done; basics complete; bulk lead pending. | <14 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
4336926 | Shri Krish Housing and Properties | Muntazar Mhate | Open | <=5 d | 18-Jun-26 | 0 | Yes |  |  |  |  | C | Kickoff call pending from client side. | 14-30 d | Chase kickoff slot; escalate to customer exec if no response in 5 days. | OK | None logged | None logged | No - none logged
4370376 | Shrimant Developers | Muntazar Mhate | Onboarding In Progress | <=5 d | 18-Jun-26 | 0 | Yes |  |  |  |  | C | Basics done; website/bulk lead pending. | <14 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
4225090 | Sir Biotech Private Limited | Muntazar Mhate | Onboarding In Progress | <=5 d | 16-Jun-26 | 1 | Yes | Yes |  |  |  | C | Core + LinkedIn done; bulk lead pending. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
4370391 | Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Open | <=5 d |  |  | No |  | Yes |  |  | C | NO NOTES (Open). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4255693 | Calicut Landmark Builders | Raahul Ramanan R | Onboarding In Progress | <=5 d | 15-Jun-26 | 2 | Yes | Yes |  |  |  | A | Only a 'Timesheet' file attached - no status update. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK | None logged | None logged | No - none logged
4177642 | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | <=5 d | 15-Jun-26 | 2 | Yes | Yes |  |  |  | C | Task status live; WhatsApp in progress, call scheduled 18-Jun. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | OK | None logged | None logged | No - none logged
4255701 | REALYESTAKE CONSULTING | Raahul Ramanan R | Onboarding In Progress | <=5 d | 15-Jun-26 | 2 | Yes | Yes | Yes |  |  | C | Acct + users done; lead import to be done by client; WhatsApp done. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
3929883 | Rattha Realty | Raahul Ramanan R | Pending on Customer | <=5 d | 15-Jun-26 | 2 | Yes | Yes | Yes |  |  | C | Task status mostly Done; actively progressing. | 90-180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | OK | None logged | None logged | No - none logged
4255681 | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | <=5 d | 15-Jun-26 | 2 | Yes | Yes |  |  |  | A | Only a 'Timesheet' file attached - no status update. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK | None logged | None logged | No - none logged
3623014 | Upcurve Consumer Tech | Raahul Ramanan R | Onboarding In Progress | <=5 d | 15-Feb-26 | 122 | Yes | Yes |  |  |  | Broker | Bulk lead in progress; many integrations pending. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (122d) | None logged | None logged | No - none logged
4359667 | Vishaal Promotors | Raahul Ramanan R | Onboarding In Progress | <=5 d | 15-Jun-26 | 2 | Yes |  |  |  |  | C | Large part done; few items in progress. | <14 d | Complete pending setup items and progress toward handover. (re-grade to B) | OK | None logged | None logged | No - none logged
3575524 | Voora Developers | Raahul Ramanan R | Pending on Customer | <=5 d | 23-Feb-26 | 114 | Yes | Yes |  |  |  | A | Requirement sheet shared; 'internal handover scheduled' - no progress since Feb. | 90-180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Risk (114d) | None logged | None logged | No - none logged
4357637 | Apex Construction | Sahil Jane | Onboarding In Progress | <=5 d | 16-Jun-26 | 1 | Yes |  |  |  |  | C | 'Multiple times call rescheduled. Will schedule next on Friday.' | <14 d | Customer keeps rescheduling - lock one firm slot or pause the account. | OK | None logged | None logged | No - none logged
4389674 | Axon Developer | Sahil Jane | Open | <=5 d |  |  | No |  |  |  |  | A | NO NOTES (Open, new). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4349900 | B2Day Real Estate Pvt Ltd | Sahil Jane | Onboarding In Progress | <=5 d | 16-Jun-26 | 1 | Yes | Yes |  |  |  | C | Most done; AI Sensi pending on customer. | <14 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
4382909 | Dreams true realty | Sahil Jane | Kickoff Done | <=5 d | 16-Jun-26 | 1 | Yes |  | Yes |  |  | (none) | Meta integration call rescheduled. | <14 d | Customer keeps rescheduling - lock one firm slot or pause the account. | OK | None logged | None logged | No - none logged
4389699 | Leonaara PVt LTD | Sahil Jane | Open | <=5 d |  |  | No |  |  |  |  | C | NO NOTES (Open, new). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4338510 | Mundra Housing Projects LLP | Sahil Jane | Onboarding In Progress | <=5 d | 16-Jun-26 | 1 | Yes | Yes |  |  |  | C | Core done; bulk lead file received today; FB call tomorrow. | 14-30 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK | None logged | None logged | No - none logged
4382913 | Pachnai Group (Darjeeling) | Sahil Jane | Kickoff Done | <=5 d |  |  | No |  |  |  |  | C | NO NOTES (Kickoff Done stage). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4382895 | SS Salesforce | Sahil Jane | Open | <=5 d | 16-Jun-26 | 1 | Yes |  | Yes |  |  | C | Priority task list shared; early stage. | <14 d | Complete pending setup items and progress toward handover. | OK | None logged | None logged | No - none logged
4368709 | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | <=5 d | 16-Jun-26 | 1 | Yes |  | Yes |  |  | C | 'Multiple times call rescheduled; account on hold few days.' | <14 d | Customer unresponsive - set a 7-day deadline, then move to 'On Hold' with reason. | OK | None logged | None logged | No - none logged
4313304 | Yula Globas | Sahil Jane | Onboarding In Progress | <=5 d | 16-Jun-26 | 1 | Yes |  |  |  |  | C | Most integrations done. | 14-30 d | Complete pending setup items and progress toward handover. | OK | None logged | None logged | No - none logged
4285364 | Yula Homes | Sahil Jane | Onboarding In Progress | <=5 d | 16-Jun-26 | 1 | Yes | Yes |  |  |  | C | Most done; Mcube data push issue raised to vendor. | 14-30 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK | None logged | None logged | No - none logged
3302998 | Times Group | Sanket Nampalliwar | Onboarding In Progress | <=5 d | 10-Nov-25 | 219 | Yes | Yes |  | 944000 | 50 | A | FM app final field list shared, raised on JIRA for dev. | >180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Risk (219d) | None logged | None logged | No - none logged
4364144 | Gruhshilp Construction | Shweta Gouda | Open | <=5 d |  |  | No |  |  |  |  | Broker | NO NOTES. | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4288574 | Nandd Mahal Group | Shweta Gouda | Onboarding In Progress | <=5 d | 27-May-26 | 21 | Yes |  |  |  |  | Broker | Core done; Meta/portal pending on customer decision. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (21d) | None logged | None logged | No - none logged
4357586 | Pavani Infra | Shweta Gouda | Onboarding In Progress | <=5 d | 13-Jun-26 | 4 | Yes |  |  |  |  | (none) | Core done; lead import client-side. | <14 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
4367528 | RUDRA REALTY | Shweta Gouda | Onboarding In Progress | <=5 d | 13-Jun-26 | 4 | Yes |  | Yes |  |  | Broker | Core done; lead import client-side. | <14 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
4386522 | Rana Propmart | Shweta Gouda | Open | <=5 d |  |  | No |  |  |  |  | (none) | NO NOTES (Open, new). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4348094 | Shri Swami Samarth Associates | Shweta Gouda | Onboarding In Progress | <=5 d |  |  | No |  |  |  |  | (none) | NO NOTES. | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4321660 | Shri krishna real estate | Shweta Gouda | Onboarding In Progress | <=5 d | 13-Jun-26 | 4 | Yes |  |  |  |  | Broker | Core done; lead import to be done client-side. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK | None logged | None logged | No - none logged
4375201 | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | <=5 d |  |  | No |  | Yes |  |  | Broker | NO NOTES (Open). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4258672 | US Associates | Shweta Gouda | Onboarding In Progress | <=5 d | 27-May-26 | 21 | Yes |  |  |  |  | C | Core + Meta done; lead file pending from customer. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (21d) | None logged | None logged | No - none logged
4383383 | VIVANTA GROUP | Shweta Gouda | Open | <=5 d |  |  | No |  |  |  |  | C | NO NOTES (Open). | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4348936 | GARDEN OF EDEN PROPERTY DEV | Venkat Viswavardhan | Onboarding In Progress | <=5 d |  |  | No |  |  |  |  | C | NO NOTES. | <14 d | Log first status note and book kickoff; set a next task. | Risk-no touch ever | None logged | None logged | No - none logged
4293765 | KR Developers | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 08-Jun-26 | 9 | Yes | Yes | Yes |  |  | A | Sales training completed. | 14-30 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4197691 | Raghava Elite Park | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 02-Jun-26 | 15 | Yes |  | Yes |  |  | B | AI Calling setup complete, awaiting customer feedback. | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to A) | Risk (15d) | None logged | None logged | No - none logged
4337048 | i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | <=5 d |  |  | No |  | Yes |  |  | A | NO NOTES (in 'Pending on Customer' with zero record). | 14-30 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. | Risk-no touch ever | None logged | None logged | No - none logged

## 5. Large-Stuck-Attention
Large deals, Stuck deals & Deals needing attention - for everyone
A) LARGE DEALS (value / licenses) - protect these
Deal | Owner | Stage | Billed (Rs) | Licenses | Cat | Status / note
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress | 1210680 | 15 | B | NO NOTES (DUP of Raghava EP; Rs12.1L paid, 'Yet to sign up').
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | 979400 | 30 | A | Onboarding questionnaire pending from client; all steps waiting on customer.
Times Group | Sanket Nampalliwar | Onboarding In Progress | 944000 | 50 | A | FM app final field list shared, raised on JIRA for dev.
Greenrich Constructions IRIS | Atharva Patil | Open | 705640 | 3 | C | NO NOTES (Rs7.06L paid, all steps Initiated, stuck in Open).
Definer Properties IRIS | Atharva Patil | Open | 507400 | 10 | B | NO NOTES (acct Active, Rs5.07L paid, still in Open).
SANDEEP DWELLERS PVT LTD | Sanket Nampalliwar | Onboarding In Progress | 373780 | 22 | A | Most tasks complete; SV-form JIRA raised; only Rs52k of Rs3.74L collected.
Sujay Avalon IRIS | Atharva Patil | Open | 355652 | 3 | C | NO NOTES (Rs3.56L paid, 'Yet to sign up').
Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done |  | 150 | A | NO NOTES (150 licenses, Cat-A, EVERY setup step 'Waiting on customer').
B) STUCK DEALS (30+ days idle, or notes say 'no movement / on hold / call rescheduled')
Deal | Owner | Stage | Last note | Idle | Status / note
Sujay Avalon IRIS | Atharva Patil | Open |  | 30+ d | NO NOTES (Rs3.56L paid, 'Yet to sign up').
B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer |  | 30+ d | NO NOTES (but acct signed up & actual go-live 06-Oct recorded - effectively live).
Greenrich Constructions IRIS | Atharva Patil | Open |  | 30+ d | NO NOTES (Rs7.06L paid, all steps Initiated, stuck in Open).
Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress |  | 30+ d | NO NOTES.
Definer Properties IRIS | Atharva Patil | Open |  | 30+ d | NO NOTES (acct Active, Rs5.07L paid, still in Open).
SANDEEP DWELLERS PVT LTD | Sanket Nampalliwar | Onboarding In Progress | 07-May-26 | 30+ d | Most tasks complete; SV-form JIRA raised; only Rs52k of Rs3.74L collected.
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | 04-Jan-26 | 30+ d | Onboarding questionnaire pending from client; all steps waiting on customer.
Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done |  | 30+ d | NO NOTES (150 licenses, Cat-A, EVERY setup step 'Waiting on customer').
Shree Automotive | Sanket Nampalliwar | Pending on Customer | 08-Dec-25 | 30+ d | Awaiting client details to start setup; 2 customization JIRAs pushed.
Shree Honda | Sanket Nampalliwar | Pending on Customer | 08-Dec-25 | 30+ d | Awaiting client details; customization JIRAs pending.
dummy | Shubham Dubey | Open |  | 30+ d | NO NOTES - test record ('dummy').
M/S SURI DEVELOPERS Post Sales | Shubham Dubey | Open |  | 30+ d | NO NOTES (post-sale DUP of SURI).
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress |  | 30+ d | NO NOTES (DUP of Raghava EP; Rs12.1L paid, 'Yet to sign up').
IRA Estate Copy post sale | Shubham Dubey | Onboarding In Progress | 22-Dec-25 | 30+ d | Post-sale req gathering; follow-up for client data.
Krishvi Group | Shweta Gouda | Onboarding In Progress |  | 30+ d | NO NOTES (Active, go-live 20-May missed).
Raado Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | 15-Jun-26 | <=5 d | 'No movement from client side.'
Propleaf | Muntazar Mhate | Onboarding In Progress | 15-Jun-26 | <=5 d | 'No movement from client side. Will check till Wed or put ON HOLD.'
Apex Construction | Sahil Jane | Onboarding In Progress | 16-Jun-26 | <=5 d | 'Multiple times call rescheduled. Will schedule next on Friday.'
Dreams true realty | Sahil Jane | Kickoff Done | 16-Jun-26 | <=5 d | Meta integration call rescheduled.
Veedhan Buildtech | Sahil Jane | Onboarding In Progress | 16-Jun-26 | <=5 d | 'Multiple times call rescheduled; account on hold few days.'
C) NEEDS ATTENTION (paid but 'Yet to sign up', or large + go-live breached)
Deal | Owner | Stage | Billed (Rs) | Signed up? | Go-live overdue | Status / note
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress | 1210680 | Yet to sign up | Yes | NO NOTES (DUP of Raghava EP; Rs12.1L paid, 'Yet to sign up').
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | 979400 | Yet to sign up | Yes | Onboarding questionnaire pending from client; all steps waiting on customer.
Times Group | Sanket Nampalliwar | Onboarding In Progress | 944000 | - | Yes | FM app final field list shared, raised on JIRA for dev.
Greenrich Constructions IRIS | Atharva Patil | Open | 705640 | - | Yes | NO NOTES (Rs7.06L paid, all steps Initiated, stuck in Open).
Definer Properties IRIS | Atharva Patil | Open | 507400 | - | Yes | NO NOTES (acct Active, Rs5.07L paid, still in Open).
Sujay Avalon IRIS | Atharva Patil | Open | 355652 | Yet to sign up | Yes | NO NOTES (Rs3.56L paid, 'Yet to sign up').
Real Estate Square | Muntazar Mhate | Onboarding In Progress |  | Yet to sign up |  | Priority task list shared; early stage.
Voora Developers | Raahul Ramanan R | Pending on Customer |  | - | Yes | Requirement sheet shared; 'internal handover scheduled' - no progress since Feb.
KR Developers | Venkat Viswavardhan | Onboarding In Progress |  | Yet to sign up | Yes | Sales training completed.
VAZHRAA NIRMAAN PRIVATE LTD | Venkat Viswavardhan | Open |  | Yet to sign up |  | NO NOTES (Open).
Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress |  | - | Yes | Core done; bulk lead/CP/inventory awaiting files from customer.
Calicut Landmark Builders | Raahul Ramanan R | Onboarding In Progress |  | - | Yes | Only a 'Timesheet' file attached - no status update.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer |  | - | Yes | Most done; sales/pres training pending - customer unavailable (office shifting).
Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress |  | - | Yes | Sourcing training done, customer has feedback; WhatsApp blocked on customer meta verification.
REALYESTAKE CONSULTING | Raahul Ramanan R | Onboarding In Progress |  | Yet to sign up | Yes | Acct + users done; lead import to be done by client; WhatsApp done.
Rattha Realty | Raahul Ramanan R | Pending on Customer |  | Yet to sign up | Yes | Task status mostly Done; actively progressing.

## 6. Pending-on-Customer Check
'Pending on Customer' validation - is it really moving?
11 deals sit in this stage. Verdict from last 2-3 notes + activity.
Deal | Owner | Last note | Days since | Verdict | Clear next action
Shree Automotive | Sanket Nampalliwar | 08-Dec-25 | 191 | STUCK | Waiting on customer since Dec for WhatsApp/telephony. Final call or move to HOLD.
Shree Honda | Sanket Nampalliwar | 08-Dec-25 | 191 | STUCK | Waiting on customer since Dec. Final call or move to HOLD.
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | 04-Jan-26 | 164 | STUCK | All steps waiting on customer since Jan; not signed up; Rs3L unpaid. Escalate + collections.
Voora Developers | Raahul Ramanan R | 23-Feb-26 | 114 | STUCK | Last note Feb-23; 'handover scheduled' never happened. Escalate or re-open kickoff.
i5 Housing and Properties LLP | Venkat Viswavardhan |  |  | Unknown | No notes at all. Owner must log status + next step immediately.
GGC AI Calling | Venkat Viswavardhan | 21-May-26 | 27 | Stalled | Bot shared 21-May, no update since. Chase customer; if no response in 7d, flag HOLD.
B SQUARE ASSEST Iris | Atharva Patil |  |  | Mis-staged | Actually LIVE (go-live 06-Oct). Move to Handover Complete - shouldn't be here.
Dreamworks Realtors | Venkat Viswavardhan | 01-Jun-26 | 16 | Customer-blocked | Customer unavailable (office shifting). Re-book training, set drop-dead date.
Gram Strategic Advisors LLP | Muntazar Mhate | 25-May-26 | 23 | Near done | Most complete; schedule final handover this week.
Kohinoor AI Calling | Venkat Viswavardhan | 01-Jun-26 | 16 | Moving slowly | BOT shared; chase customer for Mcube number, set test date.
Rattha Realty | Raahul Ramanan R | 15-Jun-26 | 2 | Moving | Active (note 15-Jun). Push remaining items to handover.

## 7. Customer Category
Customer Category - usage & priority check
A/B/C/Broker should drive onboarding priority & SLA. Today it is captured but not acted on.
Distribution & risk by category
Category | Deals | % of pipe | Idle 5+ d | No notes | Not signed up | Go-live overdue
A (top priority) | 15 | 18% | 8 | 5 | 3 | 13
B | 6 | 7% | 4 | 2 | 2 | 3
C | 43 | 52% | 14 | 12 | 9 | 21
Broker | 13 | 16% | 5 | 4 | 4 | 1
Uncategorized | 6 | 7% | 2 | 4 | 1 | 2
Total | 83
What this tells us
- A-grade = your most important accounts, yet 8 of 15 have had NO activity in 5+ days and 5 have no notes at all. Priority is captured but the A's are actually the most neglected.
- Category is not used to prioritise: A deals (Kunwarji 150 lic, Times, Dhanvanthari, Sandeep) sit stuck alongside C deals with the same (lack of) attention.
- Category does not track value/size consistently: the single biggest deal, Raghava Elite Park (~Rs12.1L), is tagged B, not A; while several small C deals are routine. Re-grade against value+licenses.
- 6 deals are Uncategorized (incl. Krishvi which is already Active, plus Pavani, Rana, Dreams True) - they fall through prioritisation entirely. 'dummy' is also uncategorized.
- 52% of the pipeline (43) is tagged C. Either genuinely low-value, or default/lazy tagging - worth a quick audit so C actually means C.
- Recommendation: tie an SLA to category - A = white-glove, named owner, weekly touch + exec visibility; B = fortnightly; C/Broker = templatised. Make category mandatory and value-aligned at deal creation.
A-GRADE WATCHLIST (protect these 15 - sorted by neglect)
Deal | Owner | Stage | Idle | Last note | Billed (Rs) | Lic | Status / note
B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer | 30+ d |  |  | 6 | NO NOTES (but acct signed up & actual go-live 06-Oct recorded - effectively live).
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | 30+ d | 04-Jan-26 | 979400 | 30 | Onboarding questionnaire pending from client; all steps waiting on customer.
Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done | 30+ d |  |  | 150 | NO NOTES (150 licenses, Cat-A, EVERY setup step 'Waiting on customer').
Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress | 30+ d |  |  |  | NO NOTES.
SANDEEP DWELLERS PVT LTD | Sanket Nampalliwar | Onboarding In Progress | 30+ d | 07-May-26 | 373780 | 22 | Most tasks complete; SV-form JIRA raised; only Rs52k of Rs3.74L collected.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | 15-30 d | 01-Jun-26 |  |  | Most done; sales/pres training pending - customer unavailable (office shifting).
Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress | 15-30 d | 18-May-26 |  |  | Core done; bulk lead/CP/inventory awaiting files from customer.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | 5-7 d | 19-May-26 |  |  | Most tasks complete; GRE walk-in form feedback implemented.
Axon Developer | Sahil Jane | Open | <=5 d |  |  |  | NO NOTES (Open, new).
Calicut Landmark Builders | Raahul Ramanan R | Onboarding In Progress | <=5 d | 15-Jun-26 |  |  | Only a 'Timesheet' file attached - no status update.
KR Developers | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 08-Jun-26 |  |  | Sales training completed.
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | <=5 d | 15-Jun-26 |  |  | Only a 'Timesheet' file attached - no status update.
Times Group | Sanket Nampalliwar | Onboarding In Progress | <=5 d | 10-Nov-25 | 944000 | 50 | FM app final field list shared, raised on JIRA for dev.
Voora Developers | Raahul Ramanan R | Pending on Customer | <=5 d | 23-Feb-26 |  |  | Requirement sheet shared; 'internal handover scheduled' - no progress since Feb.
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | <=5 d |  |  |  | NO NOTES (in 'Pending on Customer' with zero record).

## 8. Re-grade (value+brand)
Category re-grade - value + licenses + brand/enterprise
Suggested grade = max of value, licence count, and brand/enterprise weight. Under-grading is the concern; higher-than-needed is low priority.
Summary: 15 under-graded (fix), 6 ungraded (set a grade), 1 clearly over-graded (low priority). ~8 A-deals score B on size alone (20-49 lic) - acceptable for enterprise/brand, not listed.
A) UNDER-GRADED - high value/brand but graded low (FIX THESE)
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Definer Properties IRIS | Atharva Patil | B | A | >180 d | Rs5.07L | 10 |  | billed Rs5.07L
Dhanraj Realbuild Llp | Venkat Viswavardhan | C | A | 30-60 d | Rs5-7L | <10/blank |  | billed Rs5-7L
Greenrich Constructions IRIS | Atharva Patil | C | A | 90-180 d | Rs7.06L | 3 |  | billed Rs7.06L
Raghava Elite Park | Venkat Viswavardhan | B | A | 30-60 d | >=Rs7L | 10-19 | Strong | billed >=Rs7L; strong brand
Raghava Elite Park Post Sales | Shubham Dubey | B | A | 30-60 d | Rs12.11L | 15 | Strong | billed Rs12.11L; strong brand
GARDEN OF EDEN PROPERTY DEV | Venkat Viswavardhan | C | B | <14 d | Rs2-3L | <10/blank |  | billed Rs2-3L
Kohinoor AI Calling | Venkat Viswavardhan | C | B | 30-60 d | blank/<1L | <10/blank | Known | known brand
NPS DEVELOPERS | Raahul Ramanan R | C | B | 30-60 d | Rs3-5L | 10-19 |  | billed Rs3-5L
Rattha Realty | Raahul Ramanan R | C | B | 90-180 d | blank/<1L | 10-19 | Known | known brand
Shree Honda | Sanket Nampalliwar | C | B | >180 d | Rs2.11L | 5 |  | billed Rs2.11L
Sujay Avalon IRIS | Atharva Patil | C | B | 30-60 d | Rs3.56L | 3 |  | billed Rs3.56L
Sujay Global Homes | Venkat Viswavardhan | C | B | 14-30 d | Rs3-5L | <10/blank |  | billed Rs3-5L
Sujay Global Homes Post Sales | Shubham Dubey | C | B | 14-30 d | Rs3-5L | <10/blank |  | billed Rs3-5L
VAZHRAA NIRMAAN PRIVATE LTD | Venkat Viswavardhan | C | B | <14 d | Rs2-3L | <10/blank |  | billed Rs2-3L
Vishaal Promotors | Raahul Ramanan R | C | B | <14 d | Rs3-5L | <10/blank |  | billed Rs3-5L
B) UNGRADED - no category set (assign one)
Includes Krishvi (already Active) and the 'dummy' test record.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
dummy | Shubham Dubey | (none) | C | 60-90 d | blank/<1L | 1 |  | no value/licenses captured
Krishvi Group | Shweta Gouda | (none) | C | 30-60 d | Rs0.81L | 3 |  | no value/licenses captured
Shri Swami Samarth Associates | Shweta Gouda | (none) | C | <14 d | blank/<1L | 10-19 |  | small ticket (blank/<1L, 10-19 lic)
Pavani Infra | Shweta Gouda | (none) | C | <14 d | blank/<1L | <10/blank |  | no value/licenses captured
Dreams true realty | Sahil Jane | (none) | C | <14 d | blank/<1L | <10/blank |  | no value/licenses captured
Rana Propmart | Shweta Gouda | (none) | C | <14 d | blank/<1L | <10/blank |  | no value/licenses captured
C) Clearly over-graded - review (low priority)
B Square is actually live - close it rather than re-grade.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
B SQUARE ASSEST Iris | Atharva Patil | A | C | >180 d | blank/<1L | 6 |  | no value/licenses captured

## 9. Comparison & Movement
Comparison & Movement vs previous run(s)
Run 1 (Thu 18-Jun-2026) - BASELINE
BASELINE RUN - no prior report to compare against yet.
Comparison (what moved, what is stuck, SUPER-RED for no movement) starts from the next run.
Baseline anchors (today):
Open deals | 83
Touched <=5 days (cadence OK) | 28
No touch logged ever | 27
Idle 5+ days (at risk) | 33
Stage 'Pending on Customer' | 11
Under-graded vs value/brand | 15
From next run each deal gets: prev stage -> now, prev note vs now, movement verdict (Progressed / Same-blocker / No-touch), stuck-streak, and SUPER-RED if not genuinely moved for 2 runs.