## 1. Stats
Sell.do Onboarding Pipeline - Statistics
Pipeline 27474 ¦ 78 open deals ¦ Snapshot 2026-06-22
Ageing = days since deal CREATED (created_at). Movement = days since last activity (separate metric).
By Owner
Category | Count
Muntazar Mhate | 15
Venkat Viswavardhan | 15
Shweta Gouda | 14
Sahil Jane | 10
Raahul Ramanan R | 7
Shubham Dubey | 6
Sanket Nampalliwar | 6
Atharva Patil | 5
Total | 78
By Pipeline Stage
Category | Count
Open | 8
Kickoff Done | 1
Onboarding In Progress | 57
Pending on Customer | 12
Under Usage Tracking | 0
Total | 78
Deal Ageing = days since CREATED (created_at)
Category | Count
<14 days | 30
14-30 days | 11
30-60 days | 21
60-90 days | 3
90-180 days | 6
180+ days | 7
Total | 78
Movement = days since LAST ACTIVITY
Category | Count
<=5 days (healthy) | 50
5-7 days | 0
7-15 days | 8
15-30 days | 3
30+ days | 17
Total | 78
Touch cadence = days since LAST NOTE (interim proxy until meetings are logged)
Category | Count
<=5 days (OK) | 37
6-10 days | 11
11-15 days | 1
16-30 days | 6
31+ days | 10
Never (no note) | 13
Total | 78
Meetings ON DEALS (not yet logged - format ready going forward)
Category | Count
Deals with a meeting logged on the deal | 0
Meeting scheduled/conducted within 5 days | 0
NO meeting logged (team to start logging) | 78
Risk & Data-Quality Flags
Category | Count
No activity 5+ days (your risk rule) | 28
No notes logged at all | 13
Target go-live date already breached | 32
Customer 'Yet to sign up' | 15
No future follow-up task | 49
Has an OVERDUE task | 23
Billed Amount field blank | 54
Estimated Value populated | 0
Meetings linked to these onboarding deals | 0

## 2. Exec Summary (CEO-CRO)
Onboarding Pipeline - Executive Summary
For CEO & CRO ¦ 2026-06-22
The headline
83 deals are open in onboarding. Nearly half (40) are already past their committed go-live date, and 33 (40%) have had no activity in 5+ days. Onboarding is meant to run in weeks - 7 deals have been open 180+ days.
The bigger structural issue: the system is not telling the truth. 26 of 83 deals (31%) have zero notes, 80 of 83 have no healthy next task, Billed Amount is blank on 65% and Estimated Value is empty on every deal. We cannot currently see revenue-at-risk in any report.
Where the money is exposed
Cash collected but customer not live ('Yet to sign up' while paid): Raghava Elite Park ~Rs12.1L, Dhanvanthari Rs9.8L (only Rs6.8L received), Greenrich Rs7.06L, Definer Rs5.07L, Sujay Avalon Rs3.56L. Plus uncollected balances: Dhanvanthari ~Rs3.0L and Sandeep ~Rs3.2L outstanding.
Largest single account at risk: Kunwarji Realtors - 150 licenses, Category A, every setup step 'Waiting on customer', go-live already breached, and ZERO notes.
What we are asking leadership to back
1. A weekly onboarding hygiene standard: every open deal must have a LOGGED MEETING (scheduled or conducted) at least every 5 days, a dated note, and a next task; stage moved at each milestone. (Meetings are currently not logged on deals at all.)
2. Make Billed Amount mandatory at deal creation so revenue-at-risk is visible.
3. A 'collections + activation' sweep on the paid-but-dormant accounts above (CRO + Onboarding).
4. De-clutter: delete test/duplicate deals (dummy, 4 'Post Sales' copies, IRA 'Copy') so reporting is real.

## 3. Owner Scorecard
Owner Scorecard - gaps for the Onboarding Head
Counts per owner across the key risk flags. Use for owner 1:1s.
Owner | Open deals | A-grade | Idle 5+ d | No notes | Go-live overdue | Not signed up | No next task | Overdue task | Key gap to address
Muntazar Mhate | 15 | 0 | 6 | 0 | 4 | 5 | 11 | 1 | Highest load (19). Several 'No movement/On hold' (Propleaf, Raado) - decide HOLD vs push.
Venkat Viswavardhan | 15 | 4 | 1 | 0 | 2 | 3 | 8 | 7 | 14 deals incl AI-Calling set stalled on Mcube; i5 & YES Proptech have no notes.
Shweta Gouda | 14 | 0 | 2 | 1 | 1 | 3 | 9 | 5 | 14 deals; many at 'pending training/lead import' - chase customers to close.
Sahil Jane | 10 | 1 | 0 | 1 | 3 | 0 | 4 | 3 | 12 deals, many brand-new with no notes/next task - log first note + kickoff.
Raahul Ramanan R | 7 | 3 | 4 | 0 | 6 | 1 | 5 | 2 | 8 deals; Voora stuck since Feb in Pending-on-Customer; Calicut only has a 'timesheet' note.
Shubham Dubey | 6 | 0 | 5 | 5 | 5 | 1 | 5 | 1 | 5 deals = mostly Post-Sales duplicates + 'dummy'. Clean these up.
Sanket Nampalliwar | 6 | 4 | 5 | 1 | 6 | 1 | 2 | 4 | 6 deals but the most stuck: Shree Auto/Honda (Dec), Dhanvanthari, Kunwarji (150 lic, no notes).
Atharva Patil | 5 | 2 | 5 | 5 | 5 | 1 | 5 | 0 | All 5 are IRIS deals, all idle 30+ d with NO notes; 2 are actually live - just not closed.
TOTAL | 78 | 14 | 28 | 13 | 32 | 15 | 49 | 23

## 4. Deal-Level Tracker
Deal-Level Tracker - for the Onboarding Head to action
Cols E-F = movement vs the LAST run: Progressed / NEW / STUCK (same blocker or no activity). Stuck deals are grouped at the top. SUPER-RED = no genuine movement for 2+ consecutive runs.
Deal ID | Deal Name | Owner | Stage | Moved? (vs last run) | Movement detail (prev -> now) | Last activity | Last note date | Days since note | Has notes | Go-live overdue | Not signed up | Billed (Rs) | Licenses | Cat | Last note / status | Age (created) | Key Next Step (recommended) | Touch cadence (interim, vs 5d) | Last meeting | Next meeting | Mtg <=5d?
3343526 | B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes |  |  | 6 | A |  | >180 d | Close to 'Handover Complete' - already live (go-live 06-Oct); shouldn't sit in Pending. | Risk (never) | None logged | None logged | No - none logged
3347148 | Definer Properties IRIS | Atharva Patil | Open | STUCK - no activity | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes |  | 507400 | 10 | B |  | >180 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. (re-grade to A) | Risk (never) | None logged | None logged | No - none logged
3650857 | Greenrich Constructions IRIS | Atharva Patil | Open | STUCK - no activity | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes |  | 705640 | 3 | C |  | 90-180 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. (re-grade to A) | Risk (never) | None logged | None logged | No - none logged
3334464 | Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes |  |  |  | A |  | >180 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Risk (never) | None logged | None logged | No - none logged
4197640 | Sujay Avalon IRIS | Atharva Patil | Open | STUCK - no activity | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes | Yes | 355652 | 3 | C |  | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | Risk (never) | None logged | None logged | No - none logged
3623014 | Upcurve Consumer Tech | Raahul Ramanan R | Pending on Customer | STUCK - same blocker | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-02-15 -> 2026-02-22 ¦ Notes still from Feb; moved to Pending-on-Customer; integrations still pending. [stuck x1] | 30+ d | 22-Feb-26 | 120 | Yes | Yes |  |  |  | Broker | Completed: user login, project, pipeline stages. In progress: bulk lead. Pending: default report, Meta, website, Google Ads, IVR (Acefone, dev raised), Wisr Parrot WhatsApp. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (120d) | None logged | None logged | No - none logged
3506901 | Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-01-04 -> 2026-01-04 ¦ No new note/stage change since 2026-01-04. [stuck x1] | 30+ d | 04-Jan-26 | 169 | Yes | Yes | Yes | 979400 | 30 | A | Onboarding questionnaire pending from client; all steps waiting on customer. | 90-180 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. Collect balance ~Rs3.0L. | Risk (169d) | None logged | None logged | No - none logged
4230613 | Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done | STUCK - no activity | Stage Kickoff Done -> Kickoff Done ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes |  |  | 150 | A |  | 30-60 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Risk (never) | None logged | None logged | No - none logged
4090500 | SANDEEP DWELLERS PVT LTD | Sanket Nampalliwar | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-07 -> 2026-05-07 ¦ No new note/stage change since 2026-05-07. [stuck x1] | 30+ d | 07-May-26 | 46 | Yes | Yes |  | 373780 | 22 | A | Most tasks complete; SV-form JIRA raised; only Rs52k of Rs3.74L collected. | 60-90 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. Collect balance ~Rs3.2L. | Risk (46d) | None logged | None logged | No - none logged
3304062 | Shree Automotive | Sanket Nampalliwar | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2025-12-08 -> 2025-12-08 ¦ No new note/stage change since 2025-12-08. [stuck x1] | 30+ d | 08-Dec-25 | 196 | Yes | Yes |  | 104784 | 4 | C | Awaiting client details to start setup; 2 customization JIRAs pushed. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Risk (196d) | None logged | None logged | No - none logged
3304063 | Shree Honda | Sanket Nampalliwar | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2025-12-08 -> 2025-12-08 ¦ No new note/stage change since 2025-12-08. [stuck x1] | 30+ d | 08-Dec-25 | 196 | Yes | Yes |  | 210983 | 5 | C | Awaiting client details; customization JIRAs pending. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Risk (196d) | None logged | None logged | No - none logged
3439810 | IRA Estate Copy post sale | Shubham Dubey | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2025-12-22 -> 2025-12-22 ¦ No new note/stage change since 2025-12-22. [stuck x1] | 30+ d | 22-Dec-25 | 182 | Yes | Yes |  |  | 9 | C | Post-sale req gathering; follow-up for client data. | >180 d | De-dupe: merge into the primary deal and close this duplicate. | Risk (182d) | None logged | None logged | No - none logged
4262552 | M/S SURI DEVELOPERS Post Sales | Shubham Dubey | Open | STUCK - no activity | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes |  | 128384 | 2 | C |  | 30-60 d | De-dupe: merge into the primary deal and close this duplicate. | Risk (never) | None logged | None logged | No - none logged
4239798 | Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes | Yes | 1210680 | 15 | B |  | 30-60 d | De-dupe: merge into the primary deal and close this duplicate. | Risk (never) | None logged | None logged | No - none logged
4044687 | dummy | Shubham Dubey | Open | STUCK - no activity | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes |  |  | 1 | (none) |  | 60-90 d | Delete - test/dummy record. | Risk (never) | None logged | None logged | No - none logged
4233562 | Krishvi Group | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 30+ d |  |  | No | Yes |  | 81184 | 3 | (none) |  | 30-60 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Risk (never) | None logged | None logged | No - none logged
4299438 | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | STUCK - same blocker | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-06-18 -> 2026-06-22 ¦ Moved INTO Pending-on-Customer; same bulk-lead blocker restated. [stuck x1] | 15-30 d | 22-Jun-26 | 0 | Yes | Yes |  |  |  | C | Completed: user login, project, default report, routing, product briefing, WATI, offline dialer, GPS, clock, admin training. Pending: bulk lead, FB integration. | 14-30 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (0d) | None logged | None logged | No - none logged
4325924 | Sujay Global Homes Post Sales | Shubham Dubey | Open | STUCK - no activity | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 15-30 d |  |  | No | Yes |  |  |  | C |  | 14-30 d | De-dupe: merge into the primary deal and close this duplicate. | Risk (never) | None logged | None logged | No - none logged
4236338 | The Perfect Leasing | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-27 -> 2026-05-27 ¦ No new note/stage change since 2026-05-27. [stuck x1] | 15-30 d | 27-May-26 | 26 | Yes |  |  |  |  | Broker | Core done; lead import & Meta pending from customer. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (26d) | None logged | None logged | No - none logged
4079157 | Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-05-25 -> 2026-05-25 ¦ No new note/stage change since 2026-05-25. [stuck x1] | 7-15 d | 25-May-26 | 28 | Yes | Yes |  |  |  | B | Most tasks complete; near handover. | 60-90 d | Complete pending setup items and progress toward handover. | Risk (28d) | None logged | None logged | No - none logged
4196905 | Pranav Infra & Trade Ventures | Muntazar Mhate | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-10 -> 2026-05-25 ¦ Latest note predates baseline (25-May); idle 30+ d; no change since last run. [stuck x1] | 7-15 d | 25-May-26 | 28 | Yes | Yes |  |  |  | B | Completed: user login, project, default report, routing, 99acres, bulk lead. Pending: FB, inventory, GRE walkin. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (28d) | None logged | None logged | No - none logged
4336863 | Raado Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-15 ¦ No new note/stage change since 2026-06-15. [stuck x1] | 7-15 d | 15-Jun-26 | 7 | Yes |  |  |  |  | C | 'No movement from client side.' | 14-30 d | Customer unresponsive - set a 7-day deadline, then move to 'On Hold' with reason. | Watch | None logged | None logged | No - none logged
4364225 | Real Estate Square | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-11 -> 2026-06-11 ¦ No new note/stage change since 2026-06-11. [stuck x1] | 7-15 d | 11-Jun-26 | 11 | Yes |  | Yes |  |  | Broker | Priority task list shared; early stage. | <14 d | Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4255693 | Calicut Landmark Builders | Raahul Ramanan R | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-15 ¦ No new note/stage change since 2026-06-15. [stuck x1] | 7-15 d | 15-Jun-26 | 7 | Yes | Yes |  |  |  | A | Only a 'Timesheet' file attached - no status update. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4177642 | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-15 ¦ No new note/stage change since 2026-06-15. [stuck x1] | 7-15 d | 15-Jun-26 | 7 | Yes | Yes |  |  |  | C | Task status live; WhatsApp in progress, call scheduled 18-Jun. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | Watch | None logged | None logged | No - none logged
4255681 | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-15 ¦ No new note/stage change since 2026-06-15. [stuck x1] | 7-15 d | 15-Jun-26 | 7 | Yes | Yes |  |  |  | A | Only a 'Timesheet' file attached - no status update. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4262054 | Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-18 -> 2026-06-18 ¦ No new note/stage change since 2026-06-18. [stuck x1] | <=5 d | 18-Jun-26 | 4 | Yes | Yes |  |  |  | B | Most tasks complete incl training. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (4d) | None logged | None logged | No - none logged
4375344 | Aura Proptech | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-15 ¦ No new note/stage change since 2026-06-15. [stuck x1] | <=5 d | 15-Jun-26 | 7 | Yes |  |  |  |  | C | Kickoff task list shared; early stage. | <14 d | Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4336926 | Shri Krish Housing and Properties | Muntazar Mhate | Open | STUCK - same blocker | Stage Open -> Open ¦ Note 2026-06-18 -> 2026-06-22 ¦ Kickoff still pending from client; only 'highlighted to Sales POC' added. [stuck x1] | <=5 d | 22-Jun-26 | 0 | Yes |  |  |  |  | C | Kickoff Call pending from client side. Highlighted to Sales POC. | 14-30 d | Chase kickoff slot; escalate to customer exec if no response in 5 days. | OK (0d) | None logged | None logged | No - none logged
4370376 | Shrimant Developers | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-18 -> 2026-06-18 ¦ No new note/stage change since 2026-06-18. [stuck x1] | <=5 d | 18-Jun-26 | 4 | Yes |  |  |  |  | C | Basics done; website/bulk lead pending. | <14 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (4d) | None logged | None logged | No - none logged
3929883 | Rattha Realty | Raahul Ramanan R | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-15 -> 2026-06-15 ¦ No new note/stage change since 2026-06-15. [stuck x1] | <=5 d | 15-Jun-26 | 7 | Yes | Yes | Yes |  |  | C | Task status mostly Done; actively progressing. | 90-180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | Watch | None logged | None logged | No - none logged
4359667 | Vishaal Promotors | Raahul Ramanan R | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-15 ¦ No new note/stage change since 2026-06-15. [stuck x1] | <=5 d | 15-Jun-26 | 7 | Yes | Yes |  |  |  | C | Large part done; few items in progress. | <14 d | Complete pending setup items and progress toward handover. (re-grade to B) | Watch | None logged | None logged | No - none logged
3575524 | Voora Developers | Raahul Ramanan R | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-02-23 -> 2026-02-23 ¦ No new note/stage change since 2026-02-23. [stuck x1] | <=5 d | 23-Feb-26 | 119 | Yes |  |  |  |  | A | Requirement sheet shared; 'internal handover scheduled' - no progress since Feb. | 90-180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Risk (119d) | None logged | None logged | No - none logged
4357637 | Apex Construction | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-16 ¦ No new note/stage change since 2026-06-16. [stuck x1] | <=5 d | 16-Jun-26 | 6 | Yes |  |  |  |  | C | 'Multiple times call rescheduled. Will schedule next on Friday.' | <14 d | Customer keeps rescheduling - lock one firm slot or pause the account. | Watch | None logged | None logged | No - none logged
4349900 | B2Day Real Estate Pvt Ltd | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-16 ¦ No new note/stage change since 2026-06-16. [stuck x1] | <=5 d | 16-Jun-26 | 6 | Yes | Yes |  |  |  | C | Most done; AI Sensi pending on customer. | <14 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
4313304 | Yula Globas | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-16 ¦ No new note/stage change since 2026-06-16. [stuck x1] | <=5 d | 16-Jun-26 | 6 | Yes | Yes |  |  |  | C | Most integrations done. | 14-30 d | Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
3302998 | Times Group | Sanket Nampalliwar | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2025-11-10 -> 2025-11-10 ¦ Note still from 10-Nov (inventory UAT); no movement since last run. [stuck x1] | <=5 d | 10-Nov-25 | 224 | Yes | Yes |  | 944000 | 50 | A | Inventory UAT still in progress; multiple fields updated per client suggestions; FM app final list raised on JIRA. | >180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Risk (224d) | None logged | None logged | No - none logged
4364144 | Gruhshilp Construction | Shweta Gouda | Open | STUCK - same blocker | Stage Open -> Open ¦ Note no note -> 2026-06-19 ¦ First note is a HOLD - customer unavailable; no onboarding progress. [stuck x1] | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | Broker | Customer unavailable this week; account on HOLD until they confirm readiness for kick-off call. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4144089 | Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-02 -> 2026-06-02 ¦ No new note/stage change since 2026-06-02. [stuck x1] | <=5 d | 02-Jun-26 | 20 | Yes |  |  |  |  | C | Sourcing training done, customer has feedback; WhatsApp blocked on customer meta verification. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to A) | Risk (20d) | None logged | None logged | No - none logged
3968505 | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-19 -> 2026-05-19 ¦ No new note/stage change since 2026-05-19. [stuck x1] | <=5 d | 19-May-26 | 34 | Yes |  |  |  |  | A | Most tasks complete; GRE walk-in form feedback implemented. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (34d) | None logged | None logged | No - none logged
4233715 | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-01 -> 2026-06-01 ¦ No new note/stage change since 2026-06-01. [stuck x1] | <=5 d | 01-Jun-26 | 21 | Yes | Yes |  |  |  | C | BOT shared for testing; awaiting Mcube number from customer. | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Risk (21d) | None logged | None logged | No - none logged
4233760 | Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-02 -> 2026-06-02 ¦ No new note/stage change since 2026-06-02. [stuck x1] | <=5 d | 02-Jun-26 | 20 | Yes |  |  |  |  | C | Number details shared to Sanket; awaiting AI-calling setup. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (20d) | None logged | None logged | No - none logged
4204921 | Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-18 -> 2026-05-18 ¦ No new note/stage change since 2026-05-18. [stuck x1] | <=5 d | 18-May-26 | 35 | Yes |  |  |  |  | A | Core done; bulk lead/CP/inventory awaiting files from customer. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (35d) | None logged | None logged | No - none logged
4337048 | i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | STUCK - same blocker | Stage Pending on Customer -> Pending on Customer ¦ Note no note -> 2026-06-22 ¦ First note is a chase; property portal & IVR still pending on vendor/customer. [stuck x1] | <=5 d | 22-Jun-26 | 0 | Yes |  | Yes |  |  | A | Asked for update on pending property portal & IVR integration; vendors emailed, awaiting response; customer to follow up with portal POC. | 14-30 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. | OK (0d) | None logged | None logged | No - none logged
4267898 | Kalim Premier Realty LLP | Sahil Jane | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 19-Jun-26 | 3 | Yes |  |  | 28320 | 2 | C | Completed: user login, project, default report, routing, bulk lead, Mcube tested lead#19, sales training. Pending: website, inventory. | 30-60 d | New onboarding deal - log kickoff note + set next task. | OK (3d) | None logged | None logged | No - none logged
4402390 | Navkar Realty Post Sales | Shubham Dubey | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  |  | 495600 | 4 | C |  | <14 d | New onboarding deal - log kickoff note + set next task. | Risk (never) | None logged | None logged | No - none logged
4334932 | New Keys Real Estate | Shweta Gouda | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 19-Jun-26 | 3 | Yes |  | Yes |  | 2 | Broker | Client was on hold; received lead file 18 June. Will upload & expedite. Pending: lead import etc. | 14-30 d | New onboarding deal - log kickoff note + set next task. | OK (3d) | None logged | None logged | No - none logged
4410353 | Shree Homes | Shweta Gouda | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 22-Jun-26 | 0 | Yes |  |  |  |  | C | Tried reaching to discuss pending points & resume onboarding; call unanswered. Asked to msg on WhatsApp. | <14 d | New onboarding deal - log kickoff note + set next task. | OK (0d) | None logged | None logged | No - none logged
4402389 | Navkar Realty | Venkat Viswavardhan | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 19-Jun-26 | 3 | Yes |  |  | 495600 | 4 | C | Priority onboarding tasks shared: user login, project, default report, source, routing, CP form. | <14 d | New onboarding deal - log kickoff note + set next task. | OK (3d) | None logged | None logged | No - none logged
4402374 | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 19-Jun-26 | 3 | Yes |  |  | 350000 | 15 | B | Priority onboarding tasks shared: user login, project, default report, source, routing, bulk lead, inventory upload. | <14 d | New onboarding deal - log kickoff note + set next task. | OK (3d) | None logged | None logged | No - none logged
4241966 | GGC AI Calling | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Pending on Customer -> Onboarding In Progress ¦ Note 2026-05-21 -> 2026-06-19 ¦ Stage Pending on Customer -> Onboarding In Progress. | 30+ d | 19-Jun-26 | 3 | Yes | Yes |  |  |  | C | Vinay to speak with Nilesh (GGC) and update. Connected with customer, showcased different AI voices. | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (3d) | None logged | None logged | No - none logged
4310934 | 9tothrive | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-08 -> 2026-06-15 ¦ Website + IVR (MCube) newly integrated. | 7-15 d | 15-Jun-26 | 7 | Yes |  |  |  |  | C | Completed: user login, project, default report, routing, FB, website, IVR MCube. Pending: Google Ads, LinkedIn, inventory. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
4377422 | Miva Real Estate | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jun-26 | 3 | Yes |  | Yes |  |  | C | Priority tasks: user login, project, default report, routing, bulk lead, FB/Meta, native WhatsApp (confirm Meta Suite verified), sales. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4383150 | Phantom Advisory | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jun-26 | 3 | Yes |  | Yes |  |  | Broker | Priority tasks: user login, project, default report, routing, bulk lead, native WhatsApp (need verified Meta Business Suite). | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4386888 | Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jun-26 | 3 | Yes |  | Yes |  |  | C | Priority tasks: user login, project, default report, routing, property portal (99A/MB), FB/Meta, bulk lead, website, Google Ads, landing pages. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4345401 | Sangram Group | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-18 -> 2026-06-22 ¦ IVR (MCube) integration newly completed. | <=5 d | 22-Jun-26 | 0 | Yes |  |  |  |  | C | Completed: user login, project, default report, routing, IVR MCube integration. Pending: bulk lead import (as discussed at kickoff). | <14 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (0d) | None logged | None logged | No - none logged
4370391 | Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-22 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 22-Jun-26 | 0 | Yes |  | Yes |  |  | C | Will add Priority Tasks by afternoon. | <14 d | Log first status note and book kickoff; set a next task. | OK (0d) | None logged | None logged | No - none logged
4389674 | Axon Developer | Sahil Jane | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | A | Priority tasks: user login, project, default report, routing, hierarchy, workflow, CAPI (need Meta Pixel ID+token), sourcing, FB, bulk lead, Mcube. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4382909 | Dreams true realty | Sahil Jane | Onboarding In Progress | Progressed | Stage Kickoff Done -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-21 ¦ Stage Kickoff Done -> Onboarding In Progress. | <=5 d | 21-Jun-26 | 1 | Yes |  |  |  |  | (none) | Completed: project, default report, user login. Pending: routing, bulk lead (await file), Meta (email to poc), Sell.do Android dialer. | <14 d | Customer keeps rescheduling - lock one firm slot or pause the account. | OK (1d) | None logged | None logged | No - none logged
4389699 | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-22 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 22-Jun-26 | 0 | Yes |  |  |  |  | C | Completed: user login, project, default report, call routing, FB. Pending: website integ, bulk lead, WhatsApp Interakt, Mcube IVR (email initiated). | <14 d | Log first status note and book kickoff; set a next task. | OK (0d) | None logged | None logged | No - none logged
4338510 | Mundra Housing Projects LLP | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-19 ¦ Bulk lead now completed; sales training scheduled 23-Jun. | <=5 d | 19-Jun-26 | 3 | Yes | Yes |  |  |  | C | Completed: user login, project, default report, routing, bulk lead. Pending: inventory, dialer, sales training scheduled 23 June, property portal. | 14-30 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (3d) | None logged | None logged | No - none logged
4382913 | Pachnai Group (Darjeeling) | Sahil Jane | Onboarding In Progress | Progressed | Stage Kickoff Done -> Onboarding In Progress ¦ Note no note -> no note ¦ Stage Kickoff Done -> Onboarding In Progress. | <=5 d |  |  | No |  |  |  |  | C |  | <14 d | Log first status note and book kickoff; set a next task. | Risk (never) | None logged | None logged | No - none logged
4382895 | SS Salesforce | Sahil Jane | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | C | Completed: user login, project, default report, 99acres, FB. Pending: bulk lead, inventory manual, dialer, website, sales/admin training. | <14 d | Complete pending setup items and progress toward handover. | OK (3d) | None logged | None logged | No - none logged
4269153 | Northstone Realty | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-27 -> 2026-06-19 ¦ User activation + clock-in/out + lead import newly completed. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | Broker | Completed: user activation, lead import (no leads wanted), project, clock in/out, default report. Pending: Meta (once campaigns live), dialer, sales training. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4357586 | Pavani Infra | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-13 -> 2026-06-19 ¦ Meta (#10) newly captured beyond core setup. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | (none) | Completed: user login, project, lead import guided, Meta lead #10, default report config. Pending items remain. | <14 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4367528 | RUDRA REALTY | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-13 -> 2026-06-19 ¦ Meta (#32) + 99acres newly integrated; teams created. | <=5 d | 19-Jun-26 | 3 | Yes |  | Yes |  |  | Broker | Completed: user login, teams, default report, lead import guided, Meta lead #32, 99acres. | <14 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4386522 | Rana Propmart | Shweta Gouda | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | (none) | Completed: user login, project, default report. Lead import guided (share file if needed), clock in/out, inventories pending. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4348094 | Shri Swami Samarth Associates | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ From no-notes to setup + 99acres/MagicBricks integrated. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | (none) | Completed: user login, project, default report, property portal 99acres/MagicBricks (lead #2,#5). Pending: Real Estate India (API details shared). | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4321660 | Shri krishna real estate | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-13 -> 2026-06-19 ¦ Clock-in/out, pipeline stages, 99acres newly completed. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | Broker | Completed: user login, lead import guided, default report, clock in/out, pipeline stages, property portal 99acres. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4375201 | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ First real setup logged (login/project/report, lead import guided). | <=5 d | 19-Jun-26 | 3 | Yes |  | Yes |  |  | Broker | Completed: user login, project, default report, lead import guided (share file). Pending: clock in/out, website (API details shared). | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4258672 | US Associates | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-27 -> 2026-06-19 ¦ Lead-file blocker cleared; pipeline stages + Meta done; now only portal pending. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | C | Completed: user login, project, pipeline stages, default report, lead import guided, Meta lead. Pending: property portal. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4383383 | VIVANTA GROUP | Shweta Gouda | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | C | Onboarding to complete: lead imports, inventories, project, website integ, IVR (incoming only), offline dialer, Meta, sales/admin training. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4147287 | Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-01 -> 2026-06-19 ¦ Training blocker resolved (sales+admin training + WhatsApp done); only bulk lead left. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | A | Completed: user login, project, default report, routing, Meta, property portal, SV form, website, sales+admin training, WhatsApp. Pending: bulk lead import. | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (3d) | None logged | None logged | No - none logged
4348936 | GARDEN OF EDEN PROPERTY DEV | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ From no-notes to setup done + Meta integrated (#10-13). | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | C | Completed: user login, project, default report, routing, Meta done (#10-13). Pending: bulk lead - is import file ready? | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4197691 | Raghava Elite Park | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-02 -> 2026-06-19 ¦ WhatsApp + inventory newly completed beyond AI-calling. | <=5 d | 19-Jun-26 | 3 | Yes |  | Yes |  |  | B | Completed: user login, project, default report, routing, WhatsApp, inventory (post-sales); AI Calling setup completed awaiting feedback. Pending: GRE walk-in form. | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to A) | OK (3d) | None logged | None logged | No - none logged
4325921 | Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-01 -> 2026-06-19 ¦ Bulk lead now Done; CP/inventory upload progressed. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | C | Onboarding updates: user login, project, default report, source creation (share list), routing, Bulk Lead: Done, CP upload, inventory upload. | 14-30 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to B) | OK (3d) | None logged | None logged | No - none logged
4370308 | VAZHRAA NIRMAAN PRIVATE LTD | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jun-26 | 3 | Yes |  | Yes |  |  | C | Completed: user login, project, default report, routing, 99 Acres done. Pending: bulk lead - are files ready? | <14 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | OK (3d) | None logged | None logged | No - none logged
4358959 | YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jun-26 | 3 | Yes |  |  |  |  | Broker | Completed: user login, project, default report, routing, CommonFloor. Pending: property portals; MagicBricks done awaiting payload; 99acres in progress. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged

## 5. Large-Stuck-Attention
Large deals, Stuck deals & Deals needing attention - for everyone
A) LARGE DEALS (value / licenses) - protect these
Deal | Owner | Stage | Billed (Rs) | Licenses | Cat | Status / note
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress | 1210680 | 15 | B
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | 979400 | 30 | A | Onboarding questionnaire pending from client; all steps waiting on customer.
Times Group | Sanket Nampalliwar | Onboarding In Progress | 944000 | 50 | A | Inventory UAT still in progress; multiple fields updated per client suggestions; FM app final list raised on JIRA.
Greenrich Constructions IRIS | Atharva Patil | Open | 705640 | 3 | C
Definer Properties IRIS | Atharva Patil | Open | 507400 | 10 | B
Navkar Realty Post Sales | Shubham Dubey | Onboarding In Progress | 495600 | 4 | C
Navkar Realty | Venkat Viswavardhan | Onboarding In Progress | 495600 | 4 | C | Priority onboarding tasks shared: user login, project, default report, source, routing, CP form.
SANDEEP DWELLERS PVT LTD | Sanket Nampalliwar | Onboarding In Progress | 373780 | 22 | A | Most tasks complete; SV-form JIRA raised; only Rs52k of Rs3.74L collected.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 350000 | 15 | B | Priority onboarding tasks shared: user login, project, default report, source, routing, bulk lead, inventory upload.
Sujay Avalon IRIS | Atharva Patil | Open | 355652 | 3 | C
Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done |  | 150 | A
B) STUCK DEALS (30+ days idle, or notes say 'no movement / on hold / call rescheduled')
Deal | Owner | Stage | Last note | Idle | Status / note
Sujay Avalon IRIS | Atharva Patil | Open |  | 30+ d
B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer |  | 30+ d
Greenrich Constructions IRIS | Atharva Patil | Open |  | 30+ d
Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress |  | 30+ d
Definer Properties IRIS | Atharva Patil | Open |  | 30+ d
Upcurve Consumer Tech | Raahul Ramanan R | Pending on Customer | 22-Feb-26 | 30+ d | Completed: user login, project, pipeline stages. In progress: bulk lead. Pending: default report, Meta, website, Google Ads, IVR (Acefone, dev raised), Wisr Parrot WhatsApp.
SANDEEP DWELLERS PVT LTD | Sanket Nampalliwar | Onboarding In Progress | 07-May-26 | 30+ d | Most tasks complete; SV-form JIRA raised; only Rs52k of Rs3.74L collected.
Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done |  | 30+ d
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | 04-Jan-26 | 30+ d | Onboarding questionnaire pending from client; all steps waiting on customer.
Shree Automotive | Sanket Nampalliwar | Pending on Customer | 08-Dec-25 | 30+ d | Awaiting client details to start setup; 2 customization JIRAs pushed.
Shree Honda | Sanket Nampalliwar | Pending on Customer | 08-Dec-25 | 30+ d | Awaiting client details; customization JIRAs pending.
dummy | Shubham Dubey | Open |  | 30+ d
M/S SURI DEVELOPERS Post Sales | Shubham Dubey | Open |  | 30+ d
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress |  | 30+ d
IRA Estate Copy post sale | Shubham Dubey | Onboarding In Progress | 22-Dec-25 | 30+ d | Post-sale req gathering; follow-up for client data.
Krishvi Group | Shweta Gouda | Onboarding In Progress |  | 30+ d
GGC AI Calling | Venkat Viswavardhan | Onboarding In Progress | 19-Jun-26 | 30+ d | Vinay to speak with Nilesh (GGC) and update. Connected with customer, showcased different AI voices.
Raado Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | 15-Jun-26 | 7-15 d | 'No movement from client side.'
Apex Construction | Sahil Jane | Onboarding In Progress | 16-Jun-26 | <=5 d | 'Multiple times call rescheduled. Will schedule next on Friday.'
New Keys Real Estate | Shweta Gouda | Onboarding In Progress | 19-Jun-26 | <=5 d | Client was on hold; received lead file 18 June. Will upload & expedite. Pending: lead import etc.
Gruhshilp Construction | Shweta Gouda | Open | 19-Jun-26 | <=5 d | Customer unavailable this week; account on HOLD until they confirm readiness for kick-off call.
C) NEEDS ATTENTION (paid but 'Yet to sign up', or large + go-live breached)
Deal | Owner | Stage | Billed (Rs) | Signed up? | Go-live overdue | Status / note
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress | 1210680 | Yet to sign up | Yes
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | 979400 | Yet to sign up | Yes | Onboarding questionnaire pending from client; all steps waiting on customer.
Times Group | Sanket Nampalliwar | Onboarding In Progress | 944000 | - | Yes | Inventory UAT still in progress; multiple fields updated per client suggestions; FM app final list raised on JIRA.
Greenrich Constructions IRIS | Atharva Patil | Open | 705640 | - | Yes
Definer Properties IRIS | Atharva Patil | Open | 507400 | - | Yes
Sujay Avalon IRIS | Atharva Patil | Open | 355652 | Yet to sign up | Yes
Real Estate Square | Muntazar Mhate | Onboarding In Progress |  | Yet to sign up |  | Priority task list shared; early stage.
Calicut Landmark Builders | Raahul Ramanan R | Onboarding In Progress |  | - | Yes | Only a 'Timesheet' file attached - no status update.
Rattha Realty | Raahul Ramanan R | Pending on Customer |  | Yet to sign up | Yes | Task status mostly Done; actively progressing.

## 6. Pending-on-Customer Check
'Pending on Customer' validation - is it really moving?
12 deals sit in this stage. Verdict from last 2-3 notes + activity.
Deal | Owner | Last note | Days since | Verdict | Clear next action
Upcurve Consumer Tech | Raahul Ramanan R | 22-Feb-26 | 120 | STUCK | No movement since Feb; Acefone IVR + Wisr WhatsApp + Meta still pending. Escalate.
Voora Developers | Raahul Ramanan R | 23-Feb-26 | 119 | STUCK | Last note Feb; 'handover scheduled' never happened. Escalate or re-open kickoff.
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | 04-Jan-26 | 169 | STUCK | All steps waiting on customer since Jan; not signed up; balance unpaid. Escalate + collections.
Shree Honda | Sanket Nampalliwar | 08-Dec-25 | 196 | STUCK | Waiting on customer since Dec. Final call or move to HOLD.
Shree Automotive | Sanket Nampalliwar | 08-Dec-25 | 196 | STUCK | Waiting on customer since Dec for WhatsApp/telephony. Final call or move to HOLD.
Kohinoor AI Calling | Venkat Viswavardhan | 01-Jun-26 | 21 | Stalled | BOT shared; awaiting Mcube details from customer. Chase + set test date.
i5 Housing and Properties LLP | Venkat Viswavardhan | 22-Jun-26 | 0 | Customer-blocked | Property portal & IVR pending on vendor + customer; vendors emailed. Set drop-dead date.
B SQUARE ASSEST Iris | Atharva Patil |  |  | Mis-staged | Actually LIVE. Move to Handover Complete - shouldn't be here.
Ribitto Private Limited | Muntazar Mhate | 22-Jun-26 | 0 | Moving slowly | Most setup done; chase customer for bulk lead file + FB integration.
Dreamworks Realtors | Venkat Viswavardhan | 19-Jun-26 | 3 | Near done | Only bulk lead import pending; schedule final handover this week.
Gram Strategic Advisors LLP | Muntazar Mhate | 25-May-26 | 28 | Near done | Most complete; schedule final handover this week.
Rattha Realty | Raahul Ramanan R | 15-Jun-26 | 7 | Moving | Active (note 18-Jun). Push remaining items to handover.

## 7. Customer Category
Customer Category - usage & priority check
A/B/C/Broker should drive onboarding priority & SLA. Today it is captured but not acted on.
Distribution & risk by category
Category | Deals | % of pipe | Idle 5+ d | No notes | Not signed up | Go-live overdue
A (top priority) | 14 | 18% | 7 | 3 | 2 | 8
B | 7 | 9% | 4 | 2 | 2 | 5
C | 40 | 51% | 12 | 6 | 6 | 16
Broker | 11 | 14% | 3 | 0 | 5 | 1
Uncategorized | 6 | 8% | 2 | 2 | 0 | 2
Total | 78
What this tells us
- A-grade = your most important accounts, yet 7 of 15 have had NO activity in 5+ days and 3 have no notes at all. Priority is captured but the A's are actually the most neglected.
- Category is not used to prioritise: A deals (Kunwarji 150 lic, Times, Dhanvanthari, Sandeep) sit stuck alongside C deals with the same (lack of) attention.
- Category does not track value/size consistently: the single biggest deal, Raghava Elite Park (~Rs12.1L), is tagged B, not A; while several small C deals are routine. Re-grade against value+licenses.
- 6 deals are Uncategorized (incl. Krishvi which is already Active, plus Pavani, Rana, Dreams True) - they fall through prioritisation entirely. 'dummy' is also uncategorized.
- 52% of the pipeline (43) is tagged C. Either genuinely low-value, or default/lazy tagging - worth a quick audit so C actually means C.
- Recommendation: tie an SLA to category - A = white-glove, named owner, weekly touch + exec visibility; B = fortnightly; C/Broker = templatised. Make category mandatory and value-aligned at deal creation.
A-GRADE WATCHLIST (protect these 15 - sorted by neglect)
Deal | Owner | Stage | Idle | Last note | Billed (Rs) | Lic | Status / note
B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer | 30+ d |  |  | 6
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer | 30+ d | 04-Jan-26 | 979400 | 30 | Onboarding questionnaire pending from client; all steps waiting on customer.
Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done | 30+ d |  |  | 150
Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress | 30+ d
SANDEEP DWELLERS PVT LTD | Sanket Nampalliwar | Onboarding In Progress | 30+ d | 07-May-26 | 373780 | 22 | Most tasks complete; SV-form JIRA raised; only Rs52k of Rs3.74L collected.
Calicut Landmark Builders | Raahul Ramanan R | Onboarding In Progress | 7-15 d | 15-Jun-26 |  |  | Only a 'Timesheet' file attached - no status update.
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | 7-15 d | 15-Jun-26 |  |  | Only a 'Timesheet' file attached - no status update.
Axon Developer | Sahil Jane | Onboarding In Progress | <=5 d | 19-Jun-26 |  |  | Priority tasks: user login, project, default report, routing, hierarchy, workflow, CAPI (need Meta Pixel ID+token), sourcing, FB, bulk lead, Mcube.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | <=5 d | 19-Jun-26 |  |  | Completed: user login, project, default report, routing, Meta, property portal, SV form, website, sales+admin training, WhatsApp. Pending: bulk lead import.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 19-May-26 |  |  | Most tasks complete; GRE walk-in form feedback implemented.
Times Group | Sanket Nampalliwar | Onboarding In Progress | <=5 d | 10-Nov-25 | 944000 | 50 | Inventory UAT still in progress; multiple fields updated per client suggestions; FM app final list raised on JIRA.
Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 18-May-26 |  |  | Core done; bulk lead/CP/inventory awaiting files from customer.
Voora Developers | Raahul Ramanan R | Pending on Customer | <=5 d | 23-Feb-26 |  |  | Requirement sheet shared; 'internal handover scheduled' - no progress since Feb.
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | <=5 d | 22-Jun-26 |  |  | Asked for update on pending property portal & IVR integration; vendors emailed, awaiting response; customer to follow up with portal POC.

## 8. Re-grade (value+brand)
Category re-grade - value + licenses + brand/enterprise
Suggested grade = max of value, licence count, and brand/enterprise weight. Under-grading is the concern; higher-than-needed is low priority.
Summary: 15 under-graded (fix), 6 ungraded (set a grade), 1 clearly over-graded (low priority). ~8 A-deals score B on size alone (20-49 lic) - acceptable for enterprise/brand, not listed.
A) UNDER-GRADED - high value/brand but graded low (FIX THESE)
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Definer Properties IRIS | Atharva Patil | B | A | >180 d | Rs5.07L | 10 |  | billed Rs5.07L
Dhanraj Realbuild Llp | Venkat Viswavardhan | C | A | 30-60 d | Rs5-7L | <10/blank |  | billed Rs5-7L
Greenrich Constructions IRIS | Atharva Patil | C | A | 90-180 d | Rs7.06L | 3 |  | billed Rs7.06L
Raghava Elite Park | Venkat Viswavardhan | B | A | 30-60 d | >=Rs7L | 10-19 | Strong | billed >=Rs7L; strong brand
Raghava Elite Park Post Sales | Shubham Dubey | B | A | 30-60 d | Rs12.11L | 15 | Strong | billed Rs12.11L; strong brand
GARDEN OF EDEN PROPERTY DEV | Venkat Viswavardhan | C | B | <14 d | Rs2-3L | <10/blank |  | billed Rs2-3L
Kohinoor AI Calling | Venkat Viswavardhan | C | B | 30-60 d | blank/<1L | <10/blank | Known | known brand
NPS DEVELOPERS | Raahul Ramanan R | C | B | 30-60 d | Rs3-5L | 10-19 |  | billed Rs3-5L
Rattha Realty | Raahul Ramanan R | C | B | 90-180 d | blank/<1L | 10-19 | Known | known brand
Shree Honda | Sanket Nampalliwar | C | B | >180 d | Rs2.11L | 5 |  | billed Rs2.11L
Sujay Avalon IRIS | Atharva Patil | C | B | 30-60 d | Rs3.56L | 3 |  | billed Rs3.56L
Sujay Global Homes | Venkat Viswavardhan | C | B | 14-30 d | Rs3-5L | <10/blank |  | billed Rs3-5L
Sujay Global Homes Post Sales | Shubham Dubey | C | B | 14-30 d | Rs3-5L | <10/blank |  | billed Rs3-5L
VAZHRAA NIRMAAN PRIVATE LTD | Venkat Viswavardhan | C | B | <14 d | Rs2-3L | <10/blank |  | billed Rs2-3L
Vishaal Promotors | Raahul Ramanan R | C | B | <14 d | Rs3-5L | <10/blank |  | billed Rs3-5L
B) UNGRADED - no category set (assign one)
Includes Krishvi (already Active) and the 'dummy' test record.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
dummy | Shubham Dubey | (none) | C | 60-90 d | blank/<1L | 1 |  | no value/licenses captured
Rana Propmart | Shweta Gouda | (none) | C | <14 d | blank/<1L | <10/blank |  | no value/licenses captured
Dreams true realty | Sahil Jane | (none) | C | <14 d | blank/<1L | <10/blank |  | no value/licenses captured
Pavani Infra | Shweta Gouda | (none) | C | <14 d | blank/<1L | <10/blank |  | no value/licenses captured
Shri Swami Samarth Associates | Shweta Gouda | (none) | C | <14 d | blank/<1L | 10-19 |  | small ticket (blank/<1L, 10-19 lic)
Krishvi Group | Shweta Gouda | (none) | C | 30-60 d | Rs0.81L | 3 |  | no value/licenses captured
C) Clearly over-graded - review (low priority)
B Square is actually live - close it rather than re-grade.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
B SQUARE ASSEST Iris | Atharva Patil | A | C | >180 d | blank/<1L | 6 |  | no value/licenses captured

## 9. Comparison & Movement
Comparison & Movement vs previous run(s)
Run 2 (Mon 22-Jun-2026) vs baseline 18-Jun
Deal | Owner | Stage prev->now | Last note prev->now | Movement verdict | Stuck streak | Reason / action
Apex Construction | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-16 -> 2026-06-16 | No-touch | 1 | No new note/stage change since 2026-06-16.
Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-18 -> 2026-06-18 | No-touch | 1 | No new note/stage change since 2026-06-18.
Aura Proptech | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-15 | No-touch | 1 | No new note/stage change since 2026-06-15.
B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer -> Pending on Customer | - -> - | No-touch | 1 | No new note/stage change since ?.
B2Day Real Estate Pvt Ltd | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-16 -> 2026-06-16 | No-touch | 1 | No new note/stage change since 2026-06-16.
Calicut Landmark Builders | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-15 | No-touch | 1 | No new note/stage change since 2026-06-15.
Definer Properties IRIS | Atharva Patil | Open -> Open | - -> - | No-touch | 1 | No new note/stage change since ?.
Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-02 -> 2026-06-02 | No-touch | 1 | No new note/stage change since 2026-06-02.
Dhanvanthari Land Dev (Sameera) | Sanket Nampalliwar | Pending on Customer -> Pending on Customer | 2026-01-04 -> 2026-01-04 | No-touch | 1 | No new note/stage change since 2026-01-04.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-05-19 -> 2026-05-19 | No-touch | 1 | No new note/stage change since 2026-05-19.
Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-05-25 -> 2026-05-25 | No-touch | 1 | No new note/stage change since 2026-05-25.
Greenrich Constructions IRIS | Atharva Patil | Open -> Open | - -> - | No-touch | 1 | No new note/stage change since ?.
Gruhshilp Construction | Shweta Gouda | Open -> Open | - -> 2026-06-19 | Same-blocker | 1 | First note is a HOLD - customer unavailable; no onboarding progress.
IRA Estate Copy post sale | Shubham Dubey | Onboarding In Progress -> Onboarding In Progress | 2025-12-22 -> 2025-12-22 | No-touch | 1 | No new note/stage change since 2025-12-22.
Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-01 -> 2026-06-01 | No-touch | 1 | No new note/stage change since 2026-06-01.
Krishvi Group | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | - -> - | No-touch | 1 | No new note/stage change since ?.
Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done -> Kickoff Done | - -> - | No-touch | 1 | No new note/stage change since ?.
M/S SURI DEVELOPERS Post Sales | Shubham Dubey | Open -> Open | - -> - | No-touch | 1 | No new note/stage change since ?.
Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress -> Onboarding In Progress | - -> - | No-touch | 1 | No new note/stage change since ?.
Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-02 -> 2026-06-02 | No-touch | 1 | No new note/stage change since 2026-06-02.
NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-15 | No-touch | 1 | No new note/stage change since 2026-06-15.
Pranav Infra & Trade Ventures | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-05-10 -> 2026-05-25 | Same-blocker | 1 | Latest note predates baseline (25-May); idle 30+ d; no change since last run.
Raado Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-15 | No-touch | 1 | No new note/stage change since 2026-06-15.
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress -> Onboarding In Progress | - -> - | No-touch | 1 | No new note/stage change since ?.
Rattha Realty | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-06-15 -> 2026-06-15 | No-touch | 1 | No new note/stage change since 2026-06-15.
Real Estate Square | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-11 -> 2026-06-11 | No-touch | 1 | No new note/stage change since 2026-06-11.
Ribitto Private Limited | Muntazar Mhate | Onboarding In Progress -> Pending on Customer | 2026-06-18 -> 2026-06-22 | Same-blocker | 1 | Moved INTO Pending-on-Customer; same bulk-lead blocker restated.
SANDEEP DWELLERS PVT LTD | Sanket Nampalliwar | Onboarding In Progress -> Onboarding In Progress | 2026-05-07 -> 2026-05-07 | No-touch | 1 | No new note/stage change since 2026-05-07.
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-15 | No-touch | 1 | No new note/stage change since 2026-06-15.
Shree Automotive | Sanket Nampalliwar | Pending on Customer -> Pending on Customer | 2025-12-08 -> 2025-12-08 | No-touch | 1 | No new note/stage change since 2025-12-08.
Shree Honda | Sanket Nampalliwar | Pending on Customer -> Pending on Customer | 2025-12-08 -> 2025-12-08 | No-touch | 1 | No new note/stage change since 2025-12-08.
Shri Krish Housing and Properties | Muntazar Mhate | Open -> Open | 2026-06-18 -> 2026-06-22 | Same-blocker | 1 | Kickoff still pending from client; only 'highlighted to Sales POC' added.
Shrimant Developers | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-18 -> 2026-06-18 | No-touch | 1 | No new note/stage change since 2026-06-18.
Sujay Avalon IRIS | Atharva Patil | Open -> Open | - -> - | No-touch | 1 | No new note/stage change since ?.
Sujay Global Homes Post Sales | Shubham Dubey | Open -> Open | - -> - | No-touch | 1 | No new note/stage change since ?.
The Perfect Leasing | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-05-27 -> 2026-05-27 | No-touch | 1 | No new note/stage change since 2026-05-27.
Times Group | Sanket Nampalliwar | Onboarding In Progress -> Onboarding In Progress | 2025-11-10 -> 2025-11-10 | Same-blocker | 1 | Note still from 10-Nov (inventory UAT); no movement since last run.
Upcurve Consumer Tech | Raahul Ramanan R | Onboarding In Progress -> Pending on Customer | 2026-02-15 -> 2026-02-22 | Same-blocker | 1 | Notes still from Feb; moved to Pending-on-Customer; integrations still pending.
Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-05-18 -> 2026-05-18 | No-touch | 1 | No new note/stage change since 2026-05-18.
Vishaal Promotors | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-15 | No-touch | 1 | No new note/stage change since 2026-06-15.
Voora Developers | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-02-23 -> 2026-02-23 | No-touch | 1 | No new note/stage change since 2026-02-23.
Yula Globas | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-16 -> 2026-06-16 | No-touch | 1 | No new note/stage change since 2026-06-16.
dummy | Shubham Dubey | Open -> Open | - -> - | No-touch | 1 | No new note/stage change since ?.
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | - -> 2026-06-22 | Same-blocker | 1 | First note is a chase; property portal & IVR still pending on vendor/customer.
9tothrive | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-08 -> 2026-06-15 | Progressed | 0 | Website + IVR (MCube) newly integrated.
Axon Developer | Sahil Jane | Open -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Dreams true realty | Sahil Jane | Kickoff Done -> Onboarding In Progress | 2026-06-16 -> 2026-06-21 | Progressed | 0 | Stage Kickoff Done -> Onboarding In Progress.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-01 -> 2026-06-19 | Progressed | 0 | Training blocker resolved (sales+admin training + WhatsApp done); only bulk lead left.
GARDEN OF EDEN PROPERTY DEV | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | From no-notes to setup done + Meta integrated (#10-13).
GGC AI Calling | Venkat Viswavardhan | Pending on Customer -> Onboarding In Progress | 2026-05-21 -> 2026-06-19 | Progressed | 0 | Stage Pending on Customer -> Onboarding In Progress.
Kalim Premier Realty LLP | Sahil Jane | NEW this run | - -> 2026-06-19 | NEW | 0 | New in pipeline this run.
Leonaara PVt LTD | Sahil Jane | Open -> Onboarding In Progress | - -> 2026-06-22 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Miva Real Estate | Muntazar Mhate | Open -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Mundra Housing Projects LLP | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-16 -> 2026-06-19 | Progressed | 0 | Bulk lead now completed; sales training scheduled 23-Jun.
Navkar Realty | Venkat Viswavardhan | NEW this run | - -> 2026-06-19 | NEW | 0 | New in pipeline this run.
Navkar Realty Post Sales | Shubham Dubey | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
New Keys Real Estate | Shweta Gouda | NEW this run | - -> 2026-06-19 | NEW | 0 | New in pipeline this run.
Northstone Realty | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-05-27 -> 2026-06-19 | Progressed | 0 | User activation + clock-in/out + lead import newly completed.
Pachnai Group (Darjeeling) | Sahil Jane | Kickoff Done -> Onboarding In Progress | - -> - | Progressed | 0 | Stage Kickoff Done -> Onboarding In Progress.
Pavani Infra | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-13 -> 2026-06-19 | Progressed | 0 | Meta (#10) newly captured beyond core setup.
Phantom Advisory | Muntazar Mhate | Open -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
RUDRA REALTY | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-13 -> 2026-06-19 | Progressed | 0 | Meta (#32) + 99acres newly integrated; teams created.
Raghava Elite Park | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-02 -> 2026-06-19 | Progressed | 0 | WhatsApp + inventory newly completed beyond AI-calling.
Rana Propmart | Shweta Gouda | Open -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Red Estate Destination Pvt Ltd | Muntazar Mhate | Open -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
SS Salesforce | Sahil Jane | Open -> Onboarding In Progress | 2026-06-16 -> 2026-06-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Sangram Group | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-18 -> 2026-06-22 | Progressed | 0 | IVR (MCube) integration newly completed.
Shree Homes | Shweta Gouda | NEW this run | - -> 2026-06-22 | NEW | 0 | New in pipeline this run.
Shri Swami Samarth Associates | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | From no-notes to setup + 99acres/MagicBricks integrated.
Shri krishna real estate | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-13 -> 2026-06-19 | Progressed | 0 | Clock-in/out, pipeline stages, 99acres newly completed.
Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Open -> Onboarding In Progress | - -> 2026-06-22 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Strata Capital Holdings | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | First real setup logged (login/project/report, lead import guided).
Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-01 -> 2026-06-19 | Progressed | 0 | Bulk lead now Done; CP/inventory upload progressed.
US Associates | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-05-27 -> 2026-06-19 | Progressed | 0 | Lead-file blocker cleared; pipeline stages + Meta done; now only portal pending.
VAZHRAA NIRMAAN PRIVATE LTD | Venkat Viswavardhan | Open -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | NEW this run | - -> 2026-06-19 | NEW | 0 | New in pipeline this run.
VIVANTA GROUP | Shweta Gouda | Open -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Open -> Onboarding In Progress | - -> 2026-06-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.