## 1. Stats
Sell.do Onboarding Pipeline - Statistics
Pipeline 27474 ¦ 79 open deals ¦ Snapshot 2026-06-25
Ageing = days since deal CREATED (created_at). Movement = days since last activity (separate metric).
By Owner
Category | Count
Muntazar Mhate | 16
Venkat Viswavardhan | 16
Shweta Gouda | 13
Sahil Jane | 13
Shubham Dubey | 7
Atharva Patil | 5
Sanket Nampalliwar | 4
Sourabh Sahu | 3
Raahul Ramanan R | 2
Total | 79
By Pipeline Stage
Category | Count
Open | 12
Kickoff Done | 1
Onboarding In Progress | 54
Pending on Customer | 12
Under Usage Tracking | 0
Total | 79
Deal Ageing = days since CREATED (created_at)
Category | Count
<14 days | 24
14-30 days | 19
30-60 days | 19
60-90 days | 5
90-180 days | 4
180+ days | 8
Total | 79
Movement = days since LAST ACTIVITY
Category | Count
<=5 days (healthy) | 68
5-7 days | 0
7-15 days | 1
15-30 days | 1
30+ days | 9
Total | 79
Touch cadence = days since LAST NOTE (interim proxy until meetings are logged)
Category | Count
<=5 days (OK) | 32
6-10 days | 17
11-15 days | 0
16-30 days | 3
31+ days | 12
Never (no note) | 15
Total | 79
Meetings ON DEALS (not yet logged - format ready going forward)
Category | Count
Deals with a meeting logged on the deal | 0
Meeting scheduled/conducted within 5 days | 0
NO meeting logged (team to start logging) | 79
Risk & Data-Quality Flags
Category | Count
No activity 5+ days (your risk rule) | 11
No notes logged at all | 15
Target go-live date already breached | 25
Customer 'Yet to sign up' | 8
No future follow-up task | 55
Has an OVERDUE task | 14
Billed Amount field blank | 54
Estimated Value populated | 0
Meetings linked to these onboarding deals | 0

## 2. Exec Summary (CEO-CRO)
Onboarding Pipeline - Executive Summary
For CEO & CRO ¦ 2026-06-25
The headline
83 deals are open in onboarding. Nearly half (40) are already past their committed go-live date, and 33 (40%) have had no activity in 5+ days. Onboarding is meant to run in weeks - 7 deals have been open 180+ days.
The bigger structural issue: the system is not telling the truth. 26 of 83 deals (31%) have zero notes, 80 of 83 have no healthy next task, Billed Amount is blank on 65% and Estimated Value is empty on every deal. We cannot currently see revenue-at-risk in any report.
Where the money is exposed
Cash collected but customer not live ('Yet to sign up' while paid): Raghava Elite Park ~Rs12.1L, Dhanvanthari Rs9.8L (only Rs6.8L received), Greenrich Rs7.06L, Definer Rs5.07L, Sujay Avalon Rs3.56L. Plus uncollected balances: Dhanvanthari ~Rs3.0L and Sandeep ~Rs3.2L outstanding.
Largest single account at risk: Kunwarji Realtors - 150 licenses, Category A, every setup step 'Waiting on customer', go-live already breached, and ZERO notes.
What we are asking leadership to back
1. A weekly onboarding hygiene standard: every open deal must have a LOGGED MEETING (scheduled or conducted) at least every 5 days, a dated note, and a next task; stage moved at each milestone. (Meetings are currently not logged on deals at all.)
2. Make Billed Amount mandatory at deal creation so revenue-at-risk is visible.
3. A 'collections + activation' sweep on the paid-but-dormant accounts above (CRO + Onboarding).
4. De-clutter: delete test/duplicate deals (dummy, 4 'Post Sales' copies, IRA 'Copy') so reporting is real.

## 3. Owner Scorecard
Owner Scorecard - gaps for the Onboarding Head
Counts per owner across the key risk flags. Use for owner 1:1s.
Owner | Open deals | A-grade | Idle 5+ d | No notes | Go-live overdue | Not signed up | No next task | Overdue task | Key gap to address
Muntazar Mhate | 16 | 0 | 0 | 1 | 0 | 1 | 15 | 1 | Highest load (19). Several 'No movement/On hold' (Propleaf, Raado) - decide HOLD vs push.
Venkat Viswavardhan | 16 | 4 | 0 | 0 | 2 | 1 | 9 | 7 | 14 deals incl AI-Calling set stalled on Mcube; i5 & YES Proptech have no notes.
Shweta Gouda | 13 | 1 | 0 | 0 | 1 | 2 | 10 | 0 | 14 deals; many at 'pending training/lead import' - chase customers to close.
Sahil Jane | 13 | 3 | 0 | 1 | 8 | 0 | 7 | 1 | 12 deals, many brand-new with no notes/next task - log first note + kickoff.
Shubham Dubey | 7 | 0 | 6 | 6 | 5 | 1 | 6 | 1 | 5 deals = mostly Post-Sales duplicates + 'dummy'. Clean these up.
Atharva Patil | 5 | 2 | 5 | 5 | 5 | 1 | 5 | 0 | All 5 are IRIS deals, all idle 30+ d with NO notes; 2 are actually live - just not closed.
Sanket Nampalliwar | 4 | 2 | 0 | 2 | 3 | 2 | 2 | 1 | 6 deals but the most stuck: Shree Auto/Honda (Dec), Dhanvanthari, Kunwarji (150 lic, no notes).
Sourabh Sahu | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 1
Raahul Ramanan R | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 8 deals; Voora stuck since Feb in Pending-on-Customer; Calicut only has a 'timesheet' note.
TOTAL | 79 | 13 | 11 | 15 | 25 | 8 | 55 | 14

## 4. Deal-Level Tracker
Deal-Level Tracker - for the Onboarding Head to action
Cols E-F = movement vs the LAST run: Progressed / NEW / STUCK (same blocker or no activity). Stuck deals are grouped at the top. SUPER-RED = no genuine movement for 2+ consecutive runs.
Deal ID | Deal Name | Owner | Stage | Moved? (vs last run) | Movement detail (prev -> now) | Last activity | Last note date | Days since note | Has notes | Go-live overdue | Not signed up | Billed (Rs) | Licenses | Cat | Last note / status | Age (created) | Key Next Step (recommended) | Touch cadence (interim, vs 5d) | Last meeting | Next meeting | Mtg <=5d?
3343526 | B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x2] | 30+ d |  |  | No | Yes |  |  | 6 | A |  | >180 d | Close to 'Handover Complete' - already live (go-live 06-Oct); shouldn't sit in Pending. | Risk (never) | None logged | None logged | No - none logged
3347148 | Definer Properties Pvt Ltd IRIS | Atharva Patil | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x2] | 30+ d |  |  | No | Yes |  | 507400 | 10 | B |  | >180 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. (re-grade to A) | Risk (never) | None logged | None logged | No - none logged
3650857 | Greenrich Constructions LLP IRIS | Atharva Patil | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x2] | 30+ d |  |  | No | Yes |  | 705640 | 3 | C |  | 90-180 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. (re-grade to A) | Risk (never) | None logged | None logged | No - none logged
3334464 | Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x2] | 30+ d |  |  | No | Yes |  |  |  | A |  | >180 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Risk (never) | None logged | None logged | No - none logged
4197640 | Sujay Avalon IRIS | Atharva Patil | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x2] | 30+ d |  |  | No | Yes | Yes | 355652 | 3 | C |  | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | Risk (never) | None logged | None logged | No - none logged
3439810 | IRA Estate Copy post sale | Shubham Dubey | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2025-12-22 -> 2025-12-22 ¦ No new note/stage change since 2025-12-22. [stuck x2] | 30+ d | 22-Dec-25 | 185 | Yes | Yes |  |  | 9 | C | Status: Requirement Gathering. Kick-off call done 12/05. Follow-up in progress for data sharing from client. Inventory/Document receive date pending. | >180 d | De-dupe: merge into the primary deal and close this duplicate. | Risk (185d) | None logged | None logged | No - none logged
4262552 | M/S SURI DEVELOPERS Post Sales | Shubham Dubey | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x2] | 30+ d |  |  | No | Yes |  | 128384 | 2 | C |  | 30-60 d | De-dupe: merge into the primary deal and close this duplicate. | Risk (never) | None logged | None logged | No - none logged
4239798 | Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x2] | 30+ d |  |  | No | Yes | Yes | 1210680 | 15 | B |  | 30-60 d | De-dupe: merge into the primary deal and close this duplicate. | Risk (never) | None logged | None logged | No - none logged
4044687 | dummy | Shubham Dubey | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x2] | 30+ d |  |  | No | Yes |  |  | 1 | (none) |  | 60-90 d | Delete - test/dummy record. | Risk (never) | None logged | None logged | No - none logged
4325924 | Sujay Global Homes Post Sales | Shubham Dubey | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x2] | 15-30 d |  |  | No | Yes |  |  |  | C |  | 14-30 d | De-dupe: merge into the primary deal and close this duplicate. | Risk (never) | None logged | None logged | No - none logged
4262054 | Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-18 -> 2026-06-18 ¦ No new note/stage change since 2026-06-18. [stuck x2] | <=5 d | 18-Jun-26 | 7 | Yes |  |  |  |  | B | Completed: User Login, Project, Default Report, Routing, Bulk Lead, Facebook, Offline Dialer, GPS, Clock-in/out, Sales Training. Website pending. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4079157 | Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-05-25 -> 2026-05-25 ¦ No new note/stage change since 2026-05-25. [stuck x2] | <=5 d | 25-May-26 | 31 | Yes |  |  |  |  | B | Completed: User Login, Project, Default Report, Routing, Sales Training, Website, IVR (MCube). Mostly complete. | 60-90 d | Complete pending setup items and progress toward handover. | Risk (31d) | None logged | None logged | No - none logged
4196905 | Pranav Infra & Trade Ventures Pvt Ltd | Muntazar Mhate | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-25 -> 2026-05-25 ¦ No new note/stage change since 2026-05-25. [stuck x2] | <=5 d | 25-May-26 | 31 | Yes |  |  |  |  | B | Completed: User Login, Project, Default Report, Routing, 99Acres, Bulk Lead Import. Pending: Facebook Integration. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (31d) | None logged | None logged | No - none logged
4299438 | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x2] | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report, Routing, Product Briefing, WATI, Offline Dialer, GPS, Clock-in/out, Admin Training. Pending: Bulk Lead, Facebook. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4336926 | Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x2] | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | C | Kickoff Call pending from client side. Has been highlighted to the Sales POC. | 14-30 d | Chase kickoff slot; escalate to customer exec if no response in 5 days. | OK (3d) | None logged | None logged | No - none logged
3623014 | Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-02-22 -> 2026-02-22 ¦ No new note/stage change since 2026-02-22. [stuck x2] | <=5 d | 22-Feb-26 | 123 | Yes |  |  |  |  | Broker | Completed: User Login, Project, Pipeline Stages. In Progress: Bulk Lead Import. Pending: Default Report, Meta, Website, Google Ads, IVR (Acefone-dev), Wisr Parrot WhatsApp. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (123d) | None logged | None logged | No - none logged
3575524 | Voora Developers | Raahul Ramanan R | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-02-23 -> 2026-02-23 ¦ No new note/stage change since 2026-02-23. [stuck x2] | <=5 d | 23-Feb-26 | 122 | Yes |  |  |  |  | A | PFB the requirement sheet and tasks - Requirement Sheet from Voora.xlsx. Internal Handover scheduled tomorrow. | 90-180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Risk (122d) | None logged | None logged | No - none logged
4349900 | B2Day Real Estate Pvt. Ltd | Sahil Jane | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-22 ¦ Only Ai Sensi pending (customer-blocked) — unchanged two runs; otherwise ready for handover. [stuck x2] | <=5 d | 22-Jun-26 | 3 | Yes | Yes |  |  |  | C | Completed: Account/User Login, Project, Default Report, 99 Acres, Bulk Lead, Inventory, Sell.do Dialer, Sales+Admin Training. Pending: Ai Sensi. | 14-30 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4255681 | SPR Construction Pvt Ltd | Sahil Jane | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-22 ¦ Only a timesheet file again; no onboarding status update. [stuck x2] | <=5 d | 22-Jun-26 | 3 | Yes | Yes |  |  |  | A | Timesheet :- SPR Timesheet.xlsx | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (3d) | None logged | None logged | No - none logged
4313304 | Yula Globas | Sahil Jane | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-16 ¦ No new note/stage change since 2026-06-16. [stuck x2] | <=5 d | 16-Jun-26 | 9 | Yes | Yes |  |  |  | C | Completed: User Login, Project, Default Report, Facebook, Native WhatsApp. Pending: Call Routing, Property Portal (99acres,Housing,MagicBricks), Website, MCube. | 14-30 d | Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
3302998 | Times Group | Sanket Nampalliwar | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2025-11-10 -> 2025-11-10 ¦ Inventory-UAT note unchanged since Nov-2025; reclassified to Pending-on-Customer. [stuck x2] | <=5 d | 10-Nov-25 | 227 | Yes |  |  | 944000 | 50 | A | UAT of inventory still in progress; last week updated multiple fields per their suggestions. FM app final list shared, JIRA raised. | >180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Risk (227d) | None logged | None logged | No - none logged
4255693 | Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-06-15 -> 2026-06-22 ¦ Only a timesheet file again; no onboarding status; moved to Pending-on-Customer. [stuck x2] | <=5 d | 22-Jun-26 | 3 | Yes | Yes |  |  |  | A | Timesheet :- Calicut Landmark Builders Pvt. Ltd.xlsx | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (3d) | None logged | None logged | No - none logged
4364144 | Gruhshilp Construction | Shweta Gouda | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x2] | <=5 d | 19-Jun-26 | 6 | Yes |  |  |  |  | Broker | As discussed you are unavailable this week; account on HOLD until you confirm readiness for kick-off call. | 14-30 d | Log first status note and book kickoff; set a next task. | Watch | None logged | None logged | No - none logged
4177642 | NPS DEVELOPERS | Sourabh Sahu | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-22 ¦ Still WhatsApp in-progress and awaiting client user details — unchanged. [stuck x2] | <=5 d | 22-Jun-26 | 3 | Yes | Yes |  |  |  | C | Task status: User Login/Project/Default Report/Routing Done. WhatsApp In Progress (NPS call). Awaiting user details from client (2 sales + 2 telecaller). | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | OK (3d) | None logged | None logged | No - none logged
3304063 | Shree Honda | Sourabh Sahu | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2025-12-08 -> 2025-12-08 ¦ No new note/stage change since 2025-12-08. [stuck x2] | <=5 d | 08-Dec-25 | 199 | Yes |  |  | 210983 | 5 | C | We are still awaiting the details from the client to start the account setup process. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Risk (199d) | None logged | None logged | No - none logged
4144089 | Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-02 -> 2026-06-02 ¦ No new note/stage change since 2026-06-02. [stuck x2] | <=5 d | 02-Jun-26 | 23 | Yes |  |  |  |  | C | Sourcing training conducted; customer has multiple feedbacks to share. AI Calling in progress (not paid). WhatsApp blocked on customer Meta verification. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to A) | Risk (23d) | None logged | None logged | No - none logged
3968505 | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-19 -> 2026-05-19 ¦ No new note/stage change since 2026-05-19. [stuck x2] | <=5 d | 19-May-26 | 37 | Yes |  |  |  |  | A | Completed: User Login, Project, Default Report, Routing, CP Upload, Sales+Pre-sales Training, Offline Dialer, GRE Walkin Form (feedback implemented). | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (37d) | None logged | None logged | No - none logged
4233715 | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-01 -> 2026-06-01 ¦ No new note/stage change since 2026-06-01. [stuck x2] | <=5 d | 01-Jun-26 | 24 | Yes |  |  |  |  | C | BOT Shared for testing. (Awaiting Mcube number details). | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Risk (24d) | None logged | None logged | No - none logged
4233760 | Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-02 -> 2026-06-02 ¦ No new note/stage change since 2026-06-02. [stuck x2] | <=5 d | 02-Jun-26 | 23 | Yes |  |  |  |  | C | Number details shared to Sanket; once added will check with Sharayu. (AI Calling/Mcube). | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (23d) | None logged | None logged | No - none logged
4204921 | Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-18 -> 2026-05-18 ¦ No new note/stage change since 2026-05-18. [stuck x2] | <=5 d | 18-May-26 | 38 | Yes |  |  |  |  | A | Update on Onboarding Tasks: Completed User Login, Project, Default Report, Source, Routing, Meta. Pending: Bulk Lead, CP Upload, Inventory, GRE Walkin Form. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (38d) | None logged | None logged | No - none logged
4337048 | i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x2] | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | A | Update on pending pointers: Property Portal & IVR Integration - vendors emailed, no response yet; you will follow up with the property portal/IVR. | 14-30 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. | OK (3d) | None logged | None logged | No - none logged
4402390 | Navkar Realty Post Sales | Shubham Dubey | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | 7-15 d |  |  | No |  |  | 495600 | 4 | C |  | <14 d | New onboarding deal - log kickoff note + set next task. | Risk (never) | None logged | None logged | No - none logged
4310934 | 9tothrive | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-15 ¦ No new note/stage change since 2026-06-15. [stuck x1] | <=5 d | 15-Jun-26 | 10 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report, Routing, Facebook, Website, IVR (MCube). Pending: Google Ads, LinkedIn, Inventory. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
4345401 | Sangram Group | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report, Routing, IVR (MCube). Pending: Bulk Lead Import - awaiting 30-50 leads as discussed in kickoff. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4382909 | Dreams true realty | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-21 -> 2026-06-21 ¦ No new note/stage change since 2026-06-21. [stuck x1] | <=5 d | 21-Jun-26 | 4 | Yes |  |  |  |  | (none) | Completed: Project, Default Report, User Login. Pending: Call Routing, Bulk Lead Import (await file), Meta (emails initiated to poc), Sell.do Dialer. | <14 d | Customer keeps rescheduling - lock one firm slot or pause the account. | OK (4d) | None logged | None logged | No - none logged
4267898 | Kalim Premier Realty LLP | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes | Yes |  | 28320 | 2 | C | Completed: User Login, Project, Default Report, Call Routing, Bulk Lead, Mcube (tested lead 19), Sales Training. Pending: Website Integration, Inventory. | 30-60 d | New onboarding deal - log kickoff note + set next task. | Watch | None logged | None logged | No - none logged
4338510 | Mundra Housing Projects LLP | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes | Yes |  |  |  | C | Completed: User Login, Project, Default Report, Call Routing, Bulk Lead Import. Pending: Inventory, Dialer, Sales Training (23rd June), Admin Training. | 14-30 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4334932 | New Keys Real Estate | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes |  | Yes |  | 2 | Broker | Client was on Hold; received lead file 18th June, will upload & expedite. Pending: Lead import, Clock In/Out, Website Integration (API shared). | 14-30 d | New onboarding deal - log kickoff note + set next task. | Watch | None logged | None logged | No - none logged
4357586 | Pavani Infra | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes |  |  |  |  | (none) | Completed: User Login, Project, Lead Import guidance, Meta (lead #10), Default report. Pending tasks remain. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
4367528 | RUDRA REALTY | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes |  | Yes |  |  | Broker | Completed: User Login, Teams, Default Report, Lead import guidance, Meta (lead #32), 99 acres. Pending tasks remain. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
4386522 | Rana Propmart | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes |  |  |  |  | (none) | Completed: User Login, Project, Default Report, Lead import guidance, Clock In/Out. Pending: Inventories (you will add). | <14 d | Log first status note and book kickoff; set a next task. | Watch | None logged | None logged | No - none logged
4348094 | Shri Swami Samarth Assosiates Builder &Developers | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes |  |  |  |  | (none) | Completed: User Login, Project, Default Report, Property Portal 99acres/Magicbricks (#2 & #5). Pending: Real Estate India (API details shared). | 14-30 d | Log first status note and book kickoff; set a next task. | Watch | None logged | None logged | No - none logged
4321660 | Shri krishna real estate | Shweta Gouda | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ Weekly update says setup 'needs updating'; no new completion logged. [stuck x1] | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | Broker | OB WEEKLY UPDATE (22nd June 2026): Basic Setup and All Other Fields need to be updated. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4375201 | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes |  |  |  |  | Broker | Completed: User Login, Project, Default Report, Lead import guidance. Pending: Clock In/Out, Website Integration (API details shared). | <14 d | Log first status note and book kickoff; set a next task. | Watch | None logged | None logged | No - none logged
4258672 | US Associates | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes |  |  |  |  | C | Completed: User Login, Project, Pipeline stages, Default report, Lead Import guidance, Meta (lead #7). Pending: Property Portal. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
4147287 | Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes |  |  |  |  | A | Completed: User Login, Project, Default Report, Routing, Meta, Property Portal, SV Form, Website, Sales+Admin Training, WhatsApp. Pending: Bulk Lead Import. | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Watch | None logged | None logged | No - none logged
4241966 | GGC AI Calling | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes | Yes |  |  |  | C | Vinay to speak with Nilesh from GGC and provide update. Connected with customer and showcased different voices. | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Watch | None logged | None logged | No - none logged
4197691 | Raghava Elite Park | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes | Yes | Yes |  |  | B | Completed: User Login, Project, Default Report, Routing, WhatsApp, Inventory Upload (post-sales). Pending: GRE Walk-in Form (Sources). | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to A) | Watch | None logged | None logged | No - none logged
4325921 | Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x1] | <=5 d | 19-Jun-26 | 6 | Yes |  |  |  |  | C | Onboarding updates: User Login, Project, Default Report, Routing done; Bulk Lead Done. Pending: Source Creation (share list), CP Upload, Inventory Upload. | 14-30 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to B) | Watch | None logged | None logged | No - none logged
4370308 | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ Followed up on pending bulk-lead files; no customer response — same blocker. [stuck x1] | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | C | Followed up again today on pending pointers, but no response; if no response will highlight to sales. | <14 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | OK (3d) | None logged | None logged | No - none logged
4412002 | Blueroof India | Muntazar Mhate | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 23-Jun-26 | 2 | Yes |  |  |  | 2 | C | Priority Onboarding Tasks shared: User Login, Project, Default Report, Routing, Bulk Lead Import, Meta, Website, Offline Dialer, GPS, Clock-in. | <14 d | Priority tasks shared — progress integrations. | OK (2d) | None logged | None logged | No - none logged
4430582 | Sunrise Housing (GHP Group) | Muntazar Mhate | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  | Yes |  | 11 | B |  | <14 d | New deal — kickoff + sign-up; no notes yet, log first status. | Risk (never) | None logged | None logged | No - none logged
4335774 | Artha Life Spaces | Sahil Jane | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d |  |  | No | Yes |  |  | 2 | C |  | 14-30 d | No notes despite 24d age; go-live already overdue — log status & push. | Risk (never) | None logged | None logged | No - none logged
4411978 | The Bangalore Real Estate Co. | Sahil Jane | Kickoff Done | NEW this run | New in pipeline this run. | <=5 d | 23-Jun-26 | 2 | Yes |  |  | 66316 | 7 | C | Priority Onboarding Tasks shared: User Login, Project, Default Report, Sell.do Dialer, Bulk Lead Import, Website integration, Property Portal Magic Bricks, Inventory, Training. | <14 d | Kickoff done — move into onboarding, start priority tasks. | OK (2d) | None logged | None logged | No - none logged
4433052 | test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No | Yes | Yes | 1233 | 12 | Push-to-OB |  | <14 d | Junk/test deal — remove from onboarding pipeline. | Risk (never) | None logged | None logged | No - none logged
4433024 | test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No | Yes | Yes | 1233 | 12 | Push-to-OB |  | <14 d | Junk/test deal — remove from onboarding pipeline. | Risk (never) | None logged | None logged | No - none logged
4415430 | Shrimant Developers - Post Sales | Shubham Dubey | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  |  |  | 3 | C |  | <14 d | New post-sales deal — no notes; log first status & begin setup. | Risk (never) | None logged | None logged | No - none logged
4415503 | TORANDWAR DEVELOPERS | Shweta Gouda | Open | NEW this run | New in pipeline this run. | <=5 d | 23-Jun-26 | 2 | Yes |  |  |  | 7 | Broker | Kick off call scheduled on 24th June at 11:00am. | <14 d | Kick-off call scheduled 24-Jun; run it and start setup. | OK (2d) | None logged | None logged | No - none logged
4053797 | PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | Pending on Customer | NEW this run | New in pipeline this run. | <=5 d | 27-Apr-26 | 59 | Yes |  |  | 502680 | 10 | B | Completed: User Login (1 user, more post-hiring), Project, Default Report, Routing, Bulk Lead, Meta. Pending: DLT setup (Mcube telephony waiting on customer). | 60-90 d | High-value (Rs5L) Pending-on-Customer; chase customer + Mcube telephony. | Risk (59d) | None logged | None logged | No - none logged
4375344 | Aura Proptech | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-15 -> 2026-06-25 ¦ Jumped from kickoff to 7 tasks done (Bulk Lead, Dialer, Sales Training). | <=5 d | 25-Jun-26 | 0 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report, Routing, Bulk Lead Import, Offline Dialer, Sales Training. Pending: Website, Facebook, Inventory, Admin Training. | <14 d | Complete pending setup items and progress toward handover. | OK (0d) | None logged | None logged | No - none logged
4377422 | Miva Real Estate | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-23 ¦ Bulk Lead, Facebook and Sales Training completed since last run. | <=5 d | 23-Jun-26 | 2 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report, Routing, Bulk Lead Import, Facebook, Sales Training. Pending: Native WhatsApp - Meta Suite not verified; Admin Training. | <14 d | Log first status note and book kickoff; set a next task. | OK (2d) | None logged | None logged | No - none logged
4383150 | Phantom Advisory | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ Login/Project/Report/Routing completed; pending narrowed to Bulk Lead + WhatsApp. | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | Broker | Completed: User Login, Project, Default Report, Routing. Pending: Bulk Lead Import (sample shared), Native WhatsApp Integration (need Meta Suite verified). | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4364225 | Real Estate Square | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-11 -> 2026-06-22 ¦ Six tasks done (login/project/report/routing/99Acres/FB) vs task-list only. | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | Broker | Completed: User Login, Project, Default Report, Routing, 99 Acres, Facebook. Pending: Bulk Lead Import (sample shared). | 14-30 d | Complete pending setup items and progress toward handover. | OK (3d) | None logged | None logged | No - none logged
4386888 | Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ Core setup (login/project/report/routing) done; property-portal integration initiated. | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report, Routing. Pending: Property Portal (99Acres,Magicbricks) initiated from our side. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4370376 | Shrimant Developers | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-18 -> 2026-06-23 ¦ GPS + Clock-in/out completed; Website integration initiated. | <=5 d | 23-Jun-26 | 2 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report, Routing, GPS, Clock-in/out. Pending: Website Integration initiated from our side. | <14 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (2d) | None logged | None logged | No - none logged
4370391 | Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-23 ¦ Priority task plan now established for this new deal (was 'will add'). | <=5 d | 23-Jun-26 | 2 | Yes |  |  |  |  | C | Priority Onboarding Tasks shared: User Login, Project, Default Report, Routing, Bulk Lead Import, Property Portal (99Acres/Magicbricks/Housing), Facebook, Offline Dialer. | <14 d | Log first status note and book kickoff; set a next task. | OK (2d) | None logged | None logged | No - none logged
4357637 | Apex Construction | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-22 ¦ From repeated call reschedules to 6 tasks completed (Account Activation, FB). | <=5 d | 22-Jun-26 | 3 | Yes | Yes |  |  |  | C | Completed: Account Activation, User Login, Project, Default Report, Call Routing, Facebook. Pending: Native WhatsApp - website not ready yet. | 14-30 d | Customer keeps rescheduling - lock one firm slot or pause the account. | OK (3d) | None logged | None logged | No - none logged
4389674 | Axon Developer | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ FB connected, bulk-lead file + Sales Training done; pending narrowed to Routing+Hierarchy. | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | A | Completed: Account/User Login, Project, Facebook (connected, add pages), Bulk lead 1 file, Sales Training. Pending: Call Routing, Hierarchy. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
3506901 | Dhanvanthari Land Developers Pvt. Ltd. (Sameera) | Sahil Jane | Onboarding In Progress | Progressed | Stage Pending on Customer -> Onboarding In Progress ¦ Note 2026-01-04 -> 2026-01-04 ¦ Stage Pending on Customer -> Onboarding In Progress. | <=5 d | 04-Jan-26 | 172 | Yes | Yes |  | 979400 | 30 | A | The Onboarding Questionnaire document is still pending from the client's end. Once received we will complete the account setup. | >180 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. Collect balance ~Rs3.0L. | Risk (172d) | None logged | None logged | No - none logged
4389699 | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-25 ¦ Account Setup + Campaign/Source newly completed. | <=5 d | 25-Jun-26 | 0 | Yes |  |  |  |  | C | Completed: User Login, Account Setup, Project, Default Report, Campaign/Source, Routing, Facebook. Pending: Website Integration, Bulk Lead Import, WhatsApp Interakt, Mcube IVR. | <14 d | Log first status note and book kickoff; set a next task. | OK (0d) | None logged | None logged | No - none logged
4382895 | SS Salesforce | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-23 ¦ Bulk Lead Import of 3,841 leads completed — substantial progress. | <=5 d | 23-Jun-26 | 2 | Yes |  |  |  |  | C | Status update: Completed User Login, Project, Default Report, 99acres, Facebook, Bulk Lead Import 3841 leads. Progressing well. | <14 d | Complete pending setup items and progress toward handover. | OK (2d) | None logged | None logged | No - none logged
4230613 | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | Progressed | Stage Kickoff Done -> Onboarding In Progress ¦ Note no note -> 2026-06-22 ¦ Stage Kickoff Done -> Onboarding In Progress. | <=5 d | 22-Jun-26 | 3 | Yes | Yes |  |  | 150 | A | PFA the updated Project Plan; Project Plan Kunvarji Realtors.xlsx | 30-60 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | OK (3d) | None logged | None logged | No - none logged
4236338 | The Perfect Leasing | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-27 -> 2026-06-22 ¦ Lead-import call scheduled (23-Jun) to unblock the customer-side pending item. | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | Broker | Completed: User Creation, Project, Inventories (you will add via Quick Add). Pending: Lead Import - call scheduled 23rd June 4:30pm. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (3d) | None logged | None logged | No - none logged
4383383 | VIVANTA GROUP | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ User Activation + Project + Lead Import completed; only Meta pending. | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | C | Completed: User Activation, Project, Lead Import, Default report. Pending: Meta Integration - let us know once Campaign ready. | <14 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
3304062 | Shree Automotive | Sourabh Sahu | Onboarding In Progress | Progressed | Stage Pending on Customer -> Onboarding In Progress ¦ Note 2025-12-08 -> 2025-12-08 ¦ Stage Pending on Customer -> Onboarding In Progress. | <=5 d | 08-Dec-25 | 199 | Yes |  |  | 104784 | 4 | C | We are still awaiting the details from the client to start the account setup process. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Risk (199d) | None logged | None logged | No - none logged
4348936 | GARDEN OF EDEN PROPERTY DEVELOPERS PVT LTD | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ Mcube Integration newly completed since last run. | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report, Routing, Meta (#10-13), Mcube Integration. Pending: Bulk Lead - is import file ready? | 14-30 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged
4402389 | Navkar Realty | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ Logins, routing, inventory now completed vs only a task-list last run. | <=5 d | 22-Jun-26 | 3 | Yes |  |  | 495600 | 4 | C | Completed: User Login, Project, Default Report, Routing, Inventory Upload. Pending: CP Form (awaiting which form), AI Calling (awaiting details). | <14 d | New onboarding deal - log kickoff note + set next task. | OK (3d) | None logged | None logged | No - none logged
4402374 | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ User/Project/Report/Source/Routing completed; only Bulk Lead now pending. | <=5 d | 22-Jun-26 | 3 | Yes |  |  | 350000 | 15 | B | Completed: User Login, Project, Default Report, Source, Routing. Pending: Bulk Lead - file shared, you will prepare the sheet. | <14 d | New onboarding deal - log kickoff note + set next task. | OK (3d) | None logged | None logged | No - none logged
4358959 | YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-22 ¦ Property-portal integration completed; lead re-assignment automation done. | <=5 d | 22-Jun-26 | 3 | Yes |  |  |  |  | Broker | Automation setup done for lead re-assignment; Property portal integration completed. Sales Training scheduled 23rd June. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (3d) | None logged | None logged | No - none logged

## 5. Large-Stuck-Attention
Large deals, Stuck deals & Deals needing attention - for everyone
A) LARGE DEALS (value / licenses) - protect these
Deal | Owner | Stage | Billed (Rs) | Licenses | Cat | Status / note
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress | 1210680 | 15 | B
Dhanvanthari Land Developers Pvt. Ltd. (Sameera) | Sahil Jane | Onboarding In Progress | 979400 | 30 | A | The Onboarding Questionnaire document is still pending from the client's end. Once received we will complete the account setup.
Times Group | Sanket Nampalliwar | Pending on Customer | 944000 | 50 | A | UAT of inventory still in progress; last week updated multiple fields per their suggestions. FM app final list shared, JIRA raised.
Greenrich Constructions LLP IRIS | Atharva Patil | Open | 705640 | 3 | C
Definer Properties Pvt Ltd IRIS | Atharva Patil | Open | 507400 | 10 | B
PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | Pending on Customer | 502680 | 10 | B | Completed: User Login (1 user, more post-hiring), Project, Default Report, Routing, Bulk Lead, Meta. Pending: DLT setup (Mcube telephony waiting on customer).
Navkar Realty Post Sales | Shubham Dubey | Onboarding In Progress | 495600 | 4 | C
Navkar Realty | Venkat Viswavardhan | Onboarding In Progress | 495600 | 4 | C | Completed: User Login, Project, Default Report, Routing, Inventory Upload. Pending: CP Form (awaiting which form), AI Calling (awaiting details).
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 350000 | 15 | B | Completed: User Login, Project, Default Report, Source, Routing. Pending: Bulk Lead - file shared, you will prepare the sheet.
Sujay Avalon IRIS | Atharva Patil | Open | 355652 | 3 | C
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress |  | 150 | A | PFA the updated Project Plan; Project Plan Kunvarji Realtors.xlsx
B) STUCK DEALS (30+ days idle, or notes say 'no movement / on hold / call rescheduled')
Deal | Owner | Stage | Last note | Idle | Status / note
Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress |  | 30+ d
B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer |  | 30+ d
Sujay Avalon IRIS | Atharva Patil | Open |  | 30+ d
Greenrich Constructions LLP IRIS | Atharva Patil | Open |  | 30+ d
Definer Properties Pvt Ltd IRIS | Atharva Patil | Open |  | 30+ d
IRA Estate Copy post sale | Shubham Dubey | Onboarding In Progress | 22-Dec-25 | 30+ d | Status: Requirement Gathering. Kick-off call done 12/05. Follow-up in progress for data sharing from client. Inventory/Document receive date pending.
dummy | Shubham Dubey | Open |  | 30+ d
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress |  | 30+ d
M/S SURI DEVELOPERS Post Sales | Shubham Dubey | Open |  | 30+ d
Gruhshilp Construction | Shweta Gouda | Open | 19-Jun-26 | <=5 d | As discussed you are unavailable this week; account on HOLD until you confirm readiness for kick-off call.
New Keys Real Estate | Shweta Gouda | Onboarding In Progress | 19-Jun-26 | <=5 d | Client was on Hold; received lead file 18th June, will upload & expedite. Pending: Lead import, Clock In/Out, Website Integration (API shared).
C) NEEDS ATTENTION (paid but 'Yet to sign up', or large + go-live breached)
Deal | Owner | Stage | Billed (Rs) | Signed up? | Go-live overdue | Status / note
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress | 1210680 | Yet to sign up | Yes
Dhanvanthari Land Developers Pvt. Ltd. (Sameera) | Sahil Jane | Onboarding In Progress | 979400 | - | Yes | The Onboarding Questionnaire document is still pending from the client's end. Once received we will complete the account setup.
Greenrich Constructions LLP IRIS | Atharva Patil | Open | 705640 | - | Yes
Definer Properties Pvt Ltd IRIS | Atharva Patil | Open | 507400 | - | Yes
Sujay Avalon IRIS | Atharva Patil | Open | 355652 | Yet to sign up | Yes
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | 1233 | Yet to sign up | Yes
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | 1233 | Yet to sign up | Yes
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Pending on Customer |  | - | Yes | Timesheet :- Calicut Landmark Builders Pvt. Ltd.xlsx
Raghava Elite Park | Venkat Viswavardhan | Onboarding In Progress |  | Yet to sign up | Yes | Completed: User Login, Project, Default Report, Routing, WhatsApp, Inventory Upload (post-sales). Pending: GRE Walk-in Form (Sources).

## 6. Pending-on-Customer Check
'Pending on Customer' validation - is it really moving?
12 deals sit in this stage. Verdict from last 2-3 notes + activity.
Deal | Owner | Last note | Days since | Verdict | Clear next action
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | 22-Jun-26 | 3 | STUCK | Only a timesheet on file twice running — no real onboarding status. Owner must log status + next step now.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | 22-Feb-26 | 123 | STUCK | Last note Feb-22; pending dev items (Acefone IVR, Wisr WhatsApp) + customer data. Escalate or re-scope.
Voora Developers | Raahul Ramanan R | 23-Feb-26 | 122 | STUCK | Last note Feb-23; 'internal handover scheduled' never happened. Escalate or re-open kickoff.
Shree Honda | Sourabh Sahu | 08-Dec-25 | 199 | STUCK | Waiting on customer for account details since Dec-2025. Final call or move to HOLD.
Times Group | Sanket Nampalliwar | 10-Nov-25 | 227 | STUCK | Inventory UAT note unchanged since Nov-2025. Escalate; confirm if genuinely live.
Ribitto Private Limited | Muntazar Mhate | 22-Jun-26 | 3 | Stalled | Core done; Bulk Lead + Facebook pending from customer since 22-Jun. Chase customer for lead file.
Kohinoor AI Calling | Venkat Viswavardhan | 01-Jun-26 | 24 | Stalled | BOT shared (Apr); awaiting Mcube number details. Chase Mcube, set a test date or flag HOLD.
i5 Housing and Properties LLP | Venkat Viswavardhan | 22-Jun-26 | 3 | Customer-blocked | Property-portal & IVR vendor responses awaited; customer to follow up. Set a drop-dead date.
PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | 27-Apr-26 | 59 | Customer-blocked | High-value (Rs5L). Signed-up but DLT/Mcube telephony waiting on customer. Chase + set drop-dead date.
B SQUARE ASSEST Iris | Atharva Patil |  |  | Mis-staged | IRIS deal with no notes ever. Verify stage — likely mis-staged; move out of onboarding pipeline.
Dreamworks Realtors | Venkat Viswavardhan | 19-Jun-26 | 6 | Near done | Most tasks complete; only Bulk Lead Import pending from customer. Push to handover.
Gram Strategic Advisors LLP | Muntazar Mhate | 25-May-26 | 31 | Near done | Most steps complete; note stale since May. Schedule final handover this week.

## 7. Customer Category
Customer Category - usage & priority check
A/B/C/Broker should drive onboarding priority & SLA. Today it is captured but not acted on.
Distribution & risk by category
Category | Deals | % of pipe | Idle 5+ d | No notes | Not signed up | Go-live overdue
A (top priority) | 13 | 16% | 2 | 2 | 0 | 6
B | 9 | 11% | 2 | 3 | 3 | 3
C | 39 | 49% | 6 | 7 | 1 | 13
Broker | 11 | 14% | 0 | 0 | 2 | 0
Uncategorized | 5 | 6% | 1 | 1 | 0 | 1
Total | 77
What this tells us
- A-grade = your most important accounts, yet 2 of 15 have had NO activity in 5+ days and 2 have no notes at all. Priority is captured but the A's are actually the most neglected.
- Category is not used to prioritise: A deals (Kunwarji 150 lic, Times, Dhanvanthari, Sandeep) sit stuck alongside C deals with the same (lack of) attention.
- Category does not track value/size consistently: the single biggest deal, Raghava Elite Park (~Rs12.1L), is tagged B, not A; while several small C deals are routine. Re-grade against value+licenses.
- 6 deals are Uncategorized (incl. Krishvi which is already Active, plus Pavani, Rana, Dreams True) - they fall through prioritisation entirely. 'dummy' is also uncategorized.
- 52% of the pipeline (43) is tagged C. Either genuinely low-value, or default/lazy tagging - worth a quick audit so C actually means C.
- Recommendation: tie an SLA to category - A = white-glove, named owner, weekly touch + exec visibility; B = fortnightly; C/Broker = templatised. Make category mandatory and value-aligned at deal creation.
A-GRADE WATCHLIST (protect these 15 - sorted by neglect)
Deal | Owner | Stage | Idle | Last note | Billed (Rs) | Lic | Status / note
B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer | 30+ d |  |  | 6
Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress | 30+ d
Axon Developer | Sahil Jane | Onboarding In Progress | <=5 d | 22-Jun-26 |  |  | Completed: Account/User Login, Project, Facebook (connected, add pages), Bulk lead 1 file, Sales Training. Pending: Call Routing, Hierarchy.
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Pending on Customer | <=5 d | 22-Jun-26 |  |  | Timesheet :- Calicut Landmark Builders Pvt. Ltd.xlsx
Dhanvanthari Land Developers Pvt. Ltd. (Sameera) | Sahil Jane | Onboarding In Progress | <=5 d | 04-Jan-26 | 979400 | 30 | The Onboarding Questionnaire document is still pending from the client's end. Once received we will complete the account setup.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | <=5 d | 19-Jun-26 |  |  | Completed: User Login, Project, Default Report, Routing, Meta, Property Portal, SV Form, Website, Sales+Admin Training, WhatsApp. Pending: Bulk Lead Import.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 19-May-26 |  |  | Completed: User Login, Project, Default Report, Routing, CP Upload, Sales+Pre-sales Training, Offline Dialer, GRE Walkin Form (feedback implemented).
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | <=5 d | 22-Jun-26 |  | 150 | PFA the updated Project Plan; Project Plan Kunvarji Realtors.xlsx
SPR Construction Pvt Ltd | Sahil Jane | Onboarding In Progress | <=5 d | 22-Jun-26 |  |  | Timesheet :- SPR Timesheet.xlsx
Times Group | Sanket Nampalliwar | Pending on Customer | <=5 d | 10-Nov-25 | 944000 | 50 | UAT of inventory still in progress; last week updated multiple fields per their suggestions. FM app final list shared, JIRA raised.
Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 18-May-26 |  |  | Update on Onboarding Tasks: Completed User Login, Project, Default Report, Source, Routing, Meta. Pending: Bulk Lead, CP Upload, Inventory, GRE Walkin Form.
Voora Developers | Raahul Ramanan R | Pending on Customer | <=5 d | 23-Feb-26 |  |  | PFB the requirement sheet and tasks - Requirement Sheet from Voora.xlsx. Internal Handover scheduled tomorrow.
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | <=5 d | 22-Jun-26 |  |  | Update on pending pointers: Property Portal & IVR Integration - vendors emailed, no response yet; you will follow up with the property portal/IVR.

## 8. Re-grade (value+brand)
Category re-grade - value + licenses + brand/enterprise
Suggested grade = max of value, licence count, and brand/enterprise weight. Under-grading is the concern; higher-than-needed is low priority.
Summary: 13 under-graded (fix), 5 ungraded (set a grade), 1 clearly over-graded (low priority). ~8 A-deals score B on size alone (20-49 lic) - acceptable for enterprise/brand, not listed.
A) UNDER-GRADED - high value/brand but graded low (FIX THESE)
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Definer Properties Pvt Ltd IRIS | Atharva Patil | B | A | >180 d | Rs5.07L | 10 |  | billed Rs5.07L
Dhanraj Realbuild Llp | Venkat Viswavardhan | C | A | 60-90 d | Rs5-7L | <10/blank |  | billed Rs5-7L
Greenrich Constructions LLP IRIS | Atharva Patil | C | A | 90-180 d | Rs7.06L | 3 |  | billed Rs7.06L
Raghava Elite Park | Venkat Viswavardhan | B | A | 30-60 d | >=Rs7L | 10-19 | Strong | billed >=Rs7L; strong brand
Raghava Elite Park Post Sales | Shubham Dubey | B | A | 30-60 d | Rs12.11L | 15 | Strong | billed Rs12.11L; strong brand
GARDEN OF EDEN PROPERTY DEVELOPERS PVT LTD | Venkat Viswavardhan | C | B | 14-30 d | Rs2-3L | <10/blank |  | billed Rs2-3L
Kohinoor AI Calling | Venkat Viswavardhan | C | B | 30-60 d | blank/<1L | <10/blank | Known | known brand
NPS DEVELOPERS | Sourabh Sahu | C | B | 30-60 d | Rs3-5L | 10-19 |  | billed Rs3-5L
Shree Honda | Sourabh Sahu | C | B | >180 d | Rs2.11L | 5 |  | billed Rs2.11L
Sujay Avalon IRIS | Atharva Patil | C | B | 30-60 d | Rs3.56L | 3 |  | billed Rs3.56L
Sujay Global Homes | Venkat Viswavardhan | C | B | 14-30 d | Rs3-5L | <10/blank |  | billed Rs3-5L
Sujay Global Homes Post Sales | Shubham Dubey | C | B | 14-30 d | Rs3-5L | <10/blank |  | billed Rs3-5L
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | C | B | <14 d | Rs2-3L | <10/blank |  | billed Rs2-3L
B) UNGRADED - no category set (assign one)
Includes Krishvi (already Active) and the 'dummy' test record.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Rana Propmart | Shweta Gouda | (none) | C | <14 d | blank/<1L | <10/blank |  | no value/licenses captured
Dreams true realty | Sahil Jane | (none) | C | <14 d | blank/<1L | <10/blank |  | no value/licenses captured
Pavani Infra | Shweta Gouda | (none) | C | 14-30 d | blank/<1L | <10/blank |  | no value/licenses captured
Shri Swami Samarth Assosiates Builder &Developers | Shweta Gouda | (none) | C | 14-30 d | blank/<1L | 10-19 |  | small ticket (blank/<1L, 10-19 lic)
dummy | Shubham Dubey | (none) | C | 60-90 d | blank/<1L | 1 |  | no value/licenses captured
C) Clearly over-graded - review (low priority)
B Square is actually live - close it rather than re-grade.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
B SQUARE ASSEST Iris | Atharva Patil | A | C | >180 d | blank/<1L | 6 |  | no value/licenses captured

## 9. Comparison & Movement
Comparison & Movement vs previous run(s)
Run 3 (Thu 25-Jun-2026) vs 22-Jun & 18-Jun
Deal | Owner | Stage prev->now | Last note prev->now | Movement verdict | Stuck streak | Reason / action
Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-18 -> 2026-06-18 | No-touch | 2 | No new note/stage change since 2026-06-18.
B SQUARE ASSEST Iris | Atharva Patil | Pending on Customer -> Pending on Customer | - -> - | No-touch | 2 | No new note/stage change since ?.
B2Day Real Estate Pvt. Ltd | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-16 -> 2026-06-22 | Same-blocker | 2 | Only Ai Sensi pending (customer-blocked) — unchanged two runs; otherwise ready for handover.
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Onboarding In Progress -> Pending on Customer | 2026-06-15 -> 2026-06-22 | Same-blocker | 2 | Only a timesheet file again; no onboarding status; moved to Pending-on-Customer.
Definer Properties Pvt Ltd IRIS | Atharva Patil | Open -> Open | - -> - | No-touch | 2 | No new note/stage change since ?.
Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-02 -> 2026-06-02 | No-touch | 2 | No new note/stage change since 2026-06-02.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-05-19 -> 2026-05-19 | No-touch | 2 | No new note/stage change since 2026-05-19.
Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-05-25 -> 2026-05-25 | No-touch | 2 | No new note/stage change since 2026-05-25.
Greenrich Constructions LLP IRIS | Atharva Patil | Open -> Open | - -> - | No-touch | 2 | No new note/stage change since ?.
Gruhshilp Construction | Shweta Gouda | Open -> Open | 2026-06-19 -> 2026-06-19 | No-touch | 2 | No new note/stage change since 2026-06-19.
IRA Estate Copy post sale | Shubham Dubey | Onboarding In Progress -> Onboarding In Progress | 2025-12-22 -> 2025-12-22 | No-touch | 2 | No new note/stage change since 2025-12-22.
Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-01 -> 2026-06-01 | No-touch | 2 | No new note/stage change since 2026-06-01.
M/S SURI DEVELOPERS Post Sales | Shubham Dubey | Open -> Open | - -> - | No-touch | 2 | No new note/stage change since ?.
Maytri Constructions IRIS | Atharva Patil | Onboarding In Progress -> Onboarding In Progress | - -> - | No-touch | 2 | No new note/stage change since ?.
Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-02 -> 2026-06-02 | No-touch | 2 | No new note/stage change since 2026-06-02.
NPS DEVELOPERS | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-22 | Same-blocker | 2 | Still WhatsApp in-progress and awaiting client user details — unchanged.
Pranav Infra & Trade Ventures Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-05-25 -> 2026-05-25 | No-touch | 2 | No new note/stage change since 2026-05-25.
Raghava Elite Park Post Sales | Shubham Dubey | Onboarding In Progress -> Onboarding In Progress | - -> - | No-touch | 2 | No new note/stage change since ?.
Ribitto Private Limited | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-22 | No-touch | 2 | No new note/stage change since 2026-06-22.
SPR Construction Pvt Ltd | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-22 | Same-blocker | 2 | Only a timesheet file again; no onboarding status update.
Shree Honda | Sourabh Sahu | Pending on Customer -> Pending on Customer | 2025-12-08 -> 2025-12-08 | No-touch | 2 | No new note/stage change since 2025-12-08.
Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Open -> Open | 2026-06-22 -> 2026-06-22 | No-touch | 2 | No new note/stage change since 2026-06-22.
Sujay Avalon IRIS | Atharva Patil | Open -> Open | - -> - | No-touch | 2 | No new note/stage change since ?.
Sujay Global Homes Post Sales | Shubham Dubey | Open -> Open | - -> - | No-touch | 2 | No new note/stage change since ?.
Times Group | Sanket Nampalliwar | Onboarding In Progress -> Pending on Customer | 2025-11-10 -> 2025-11-10 | Same-blocker | 2 | Inventory-UAT note unchanged since Nov-2025; reclassified to Pending-on-Customer.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-02-22 -> 2026-02-22 | No-touch | 2 | No new note/stage change since 2026-02-22.
Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-05-18 -> 2026-05-18 | No-touch | 2 | No new note/stage change since 2026-05-18.
Voora Developers | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-02-23 -> 2026-02-23 | No-touch | 2 | No new note/stage change since 2026-02-23.
Yula Globas | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-16 -> 2026-06-16 | No-touch | 2 | No new note/stage change since 2026-06-16.
dummy | Shubham Dubey | Open -> Open | - -> - | No-touch | 2 | No new note/stage change since ?.
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-22 | No-touch | 2 | No new note/stage change since 2026-06-22.
9tothrive | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-15 | No-touch | 1 | No new note/stage change since 2026-06-15.
Dreams true realty | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-21 -> 2026-06-21 | No-touch | 1 | No new note/stage change since 2026-06-21.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
GGC AI Calling | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
Kalim Premier Realty LLP | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
Mundra Housing Projects LLP | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
Navkar Realty Post Sales | Shubham Dubey | Onboarding In Progress -> Onboarding In Progress | - -> - | No-touch | 1 | No new note/stage change since ?.
New Keys Real Estate | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
Pavani Infra | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
RUDRA REALTY | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
Raghava Elite Park | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
Rana Propmart | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
Sangram Group | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
Shri Swami Samarth Assosiates Builder &Developers | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
Shri krishna real estate | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Same-blocker | 1 | Weekly update says setup 'needs updating'; no new completion logged.
Strata Capital Holdings | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
US Associates | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 1 | No new note/stage change since 2026-06-19.
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Same-blocker | 1 | Followed up on pending bulk-lead files; no customer response — same blocker.
Apex Construction | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-16 -> 2026-06-22 | Progressed | 0 | From repeated call reschedules to 6 tasks completed (Account Activation, FB).
Artha Life Spaces | Sahil Jane | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
Aura Proptech | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-15 -> 2026-06-25 | Progressed | 0 | Jumped from kickoff to 7 tasks done (Bulk Lead, Dialer, Sales Training).
Axon Developer | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Progressed | 0 | FB connected, bulk-lead file + Sales Training done; pending narrowed to Routing+Hierarchy.
Blueroof India | Muntazar Mhate | NEW this run | - -> 2026-06-23 | NEW | 0 | New in pipeline this run.
Dhanvanthari Land Developers Pvt. Ltd. (Sameera) | Sahil Jane | Pending on Customer -> Onboarding In Progress | 2026-01-04 -> 2026-01-04 | Progressed | 0 | Stage Pending on Customer -> Onboarding In Progress.
GARDEN OF EDEN PROPERTY DEVELOPERS PVT LTD | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Progressed | 0 | Mcube Integration newly completed since last run.
Kunwarji Realtors | Sanket Nampalliwar | Kickoff Done -> Onboarding In Progress | - -> 2026-06-22 | Progressed | 0 | Stage Kickoff Done -> Onboarding In Progress.
Leonaara PVt LTD | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-25 | Progressed | 0 | Account Setup + Campaign/Source newly completed.
Miva Real Estate | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-23 | Progressed | 0 | Bulk Lead, Facebook and Sales Training completed since last run.
Navkar Realty | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Progressed | 0 | Logins, routing, inventory now completed vs only a task-list last run.
PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | NEW this run | - -> 2026-04-27 | NEW | 0 | New in pipeline this run.
Phantom Advisory | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Progressed | 0 | Login/Project/Report/Routing completed; pending narrowed to Bulk Lead + WhatsApp.
Real Estate Square | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-11 -> 2026-06-22 | Progressed | 0 | Six tasks done (login/project/report/routing/99Acres/FB) vs task-list only.
Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Progressed | 0 | Core setup (login/project/report/routing) done; property-portal integration initiated.
SS Salesforce | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-23 | Progressed | 0 | Bulk Lead Import of 3,841 leads completed — substantial progress.
Shree Automotive | Sourabh Sahu | Pending on Customer -> Onboarding In Progress | 2025-12-08 -> 2025-12-08 | Progressed | 0 | Stage Pending on Customer -> Onboarding In Progress.
Shrimant Developers | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-18 -> 2026-06-23 | Progressed | 0 | GPS + Clock-in/out completed; Website integration initiated.
Shrimant Developers - Post Sales | Shubham Dubey | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-23 | Progressed | 0 | Priority task plan now established for this new deal (was 'will add').
Sunrise Housing (GHP Group) | Muntazar Mhate | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
TORANDWAR DEVELOPERS | Shweta Gouda | NEW this run | - -> 2026-06-23 | NEW | 0 | New in pipeline this run.
The Bangalore Real Estate Co. | Sahil Jane | NEW this run | - -> 2026-06-23 | NEW | 0 | New in pipeline this run.
The Perfect Leasing | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-05-27 -> 2026-06-22 | Progressed | 0 | Lead-import call scheduled (23-Jun) to unblock the customer-side pending item.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Progressed | 0 | User/Project/Report/Source/Routing completed; only Bulk Lead now pending.
VIVANTA GROUP | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Progressed | 0 | User Activation + Project + Lead Import completed; only Meta pending.
YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-22 | Progressed | 0 | Property-portal integration completed; lead re-assignment automation done.
test deal Push to OB 63 Copy | Sanket Nampalliwar | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
test deal Push to OB 63 Copy | Sanket Nampalliwar | NEW this run | - -> - | NEW | 0 | New in pipeline this run.