## 1. Stats
Sell.do Onboarding Pipeline - Statistics
Pipeline 27474 ¦ 64 open deals ¦ Snapshot 2026-06-29
Ageing = days since deal CREATED (created_at). Movement = days since last activity (separate metric).
By Owner
Category | Count
Venkat Viswavardhan | 18
Muntazar Mhate | 13
Sahil Jane | 12
Shweta Gouda | 10
Sanket Nampalliwar | 6
Sourabh Sahu | 3
Raahul Ramanan R | 2
Total | 64
By Pipeline Stage
Category | Count
Open | 8
Kickoff Done | 0
Onboarding In Progress | 42
Pending on Customer | 12
Under Usage Tracking | 0
Total | 62
Deal Ageing = days since CREATED (created_at)
Category | Count
<14 days | 20
14-30 days | 20
30-60 days | 11
60-90 days | 7
90-180 days | 3
180+ days | 3
Total | 64
Movement = days since LAST ACTIVITY
Category | Count
<=5 days (healthy) | 47
5-7 days | 17
7-15 days | 0
15-30 days | 0
30+ days | 0
Total | 64
Touch cadence = days since LAST NOTE (interim proxy until meetings are logged)
Category | Count
<=5 days (OK) | 19
6-10 days | 25
11-15 days | 2
16-30 days | 3
31+ days | 9
Never (no note) | 6
Total | 64
Meetings ON DEALS (not yet logged - format ready going forward)
Category | Count
Deals with a meeting logged on the deal | 0
Meeting scheduled/conducted within 5 days | 0
NO meeting logged (team to start logging) | 64
Risk & Data-Quality Flags
Category | Count
No activity 5+ days (your risk rule) | 17
No notes logged at all | 6
Target go-live date already breached | 22
Customer 'Yet to sign up' | 8
No future follow-up task | 37
Has an OVERDUE task | 14
Billed Amount field blank | 54
Estimated Value populated | 0
Meetings linked to these onboarding deals | 0

## 2. Exec Summary (CEO-CRO)
Onboarding Pipeline - Executive Summary
For CEO & CRO ¦ 2026-06-29
The headline
83 deals are open in onboarding. Nearly half (40) are already past their committed go-live date, and 33 (40%) have had no activity in 5+ days. Onboarding is meant to run in weeks - 7 deals have been open 180+ days.
The bigger structural issue: the system is not telling the truth. 26 of 83 deals (31%) have zero notes, 80 of 83 have no healthy next task, Billed Amount is blank on 65% and Estimated Value is empty on every deal. We cannot currently see revenue-at-risk in any report.
Where the money is exposed
Cash collected but customer not live ('Yet to sign up' while paid): Raghava Elite Park ~Rs12.1L, Dhanvanthari Rs9.8L (only Rs6.8L received), Greenrich Rs7.06L, Definer Rs5.07L, Sujay Avalon Rs3.56L. Plus uncollected balances: Dhanvanthari ~Rs3.0L and Sandeep ~Rs3.2L outstanding.
Largest single account at risk: Kunwarji Realtors - 150 licenses, Category A, every setup step 'Waiting on customer', go-live already breached, and ZERO notes.
What we are asking leadership to back
1. A weekly onboarding hygiene standard: every open deal must have a LOGGED MEETING (scheduled or conducted) at least every 5 days, a dated note, and a next task; stage moved at each milestone. (Meetings are currently not logged on deals at all.)
2. Make Billed Amount mandatory at deal creation so revenue-at-risk is visible.
3. A 'collections + activation' sweep on the paid-but-dormant accounts above (CRO + Onboarding).
4. De-clutter: delete test/duplicate deals (dummy, 4 'Post Sales' copies, IRA 'Copy') so reporting is real.

## 3. Owner Scorecard
Owner Scorecard - gaps for the Onboarding Head
Counts per owner across the key risk flags. Use for owner 1:1s.
Owner | Open deals | A-grade | Idle 5+ d | No notes | Go-live overdue | Not signed up | No next task | Overdue task | Key gap to address
Venkat Viswavardhan | 18 | 5 | 0 | 1 | 7 | 1 | 7 | 3 | 18 deal(s). no notes: SKYTOWN Group; pending-on-customer: i5 Housing and Properties LLP, GGC AI Calling, Kohinoor AI Calling.
Muntazar Mhate | 13 | 0 | 10 | 1 | 0 | 1 | 12 | 1 | 13 deal(s). no notes: Sunrise Housing (GHP Group); pending-on-customer: Ribitto Private Limited, Gram Strategic Advisors LLP.
Sahil Jane | 12 | 2 | 2 | 1 | 8 | 0 | 5 | 4 | 12 deal(s). no notes: Aryma Infra (OPC)Pvt Ltd.
Shweta Gouda | 10 | 1 | 1 | 0 | 1 | 2 | 8 | 0 | 10 deal(s). pending-on-customer: Calicut Landmark Builders Pvt. Ltd.
Sanket Nampalliwar | 6 | 2 | 1 | 3 | 5 | 4 | 4 | 2 | 6 deal(s). no notes: test deal Push to OB 63 Copy, test deal Push to OB 63 Copy, test deal Push to OB 63 Copy; pending-on-customer: Times Group.
Sourabh Sahu | 3 | 0 | 2 | 0 | 1 | 0 | 1 | 2 | 3 deal(s). pending-on-customer: Shree Honda.
Raahul Ramanan R | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 deal(s). pending-on-customer: Upcurve consumer Technologies Pvt Ltd, Voora Developers.
TOTAL | 64 | 11 | 17 | 6 | 22 | 8 | 37 | 14

## 4. Deal-Level Tracker
Deal-Level Tracker - for the Onboarding Head to action
Cols E-F = movement vs the LAST run: Progressed / NEW / STUCK (same blocker or no activity). Stuck deals are grouped at the top. SUPER-RED = no genuine movement for 2+ consecutive runs.
Deal ID | Deal Name | Owner | Stage | Moved? (vs last run) | Movement detail (prev -> now) | Last activity | Last note date | Days since note | Has notes | Go-live overdue | Not signed up | Billed (Rs) | Licenses | Cat | Last note / status | Age (created) | Key Next Step (recommended) | Touch cadence (interim, vs 5d) | Last meeting | Next meeting | Mtg <=5d?
4262054 | Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-18 -> 2026-06-18 ¦ No new note/stage change since 2026-06-18. [stuck x3] | 5-7 d | 18-Jun-26 | 11 | Yes |  |  |  |  | B | Completed login/project/report/routing/bulk lead/FB/dialer/GPS/clock/sales training; pending website. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | 11-15d | None logged | None logged | No - none logged
4079157 | Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-05-25 -> 2026-05-25 ¦ No new note/stage change since 2026-05-25. [stuck x3] | 5-7 d | 25-May-26 | 35 | Yes |  |  |  |  | B | Completed login/project/report/routing/sales training/website/Mcube IVR. (Broker.) | 60-90 d | Complete pending setup items and progress toward handover. | Risk (31+d) | None logged | None logged | No - none logged
4299438 | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x3] | 5-7 d | 22-Jun-26 | 7 | Yes |  |  |  |  | C | Completed login/project/report/routing/WATI/dialer/GPS/clock/admin training; pending bulk lead, FB. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | 6-10d | None logged | None logged | No - none logged
4336926 | Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Open | SUPER-RED (3 runs stuck) | Stage Open -> Open ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x3] | 5-7 d | 22-Jun-26 | 7 | Yes |  |  |  |  | C | Kickoff Call pending from client side; highlighted to Sales POC. | 14-30 d | Chase kickoff slot; escalate to customer exec if no response in 5 days. | 6-10d | None logged | None logged | No - none logged
3623014 | Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-02-22 -> 2026-02-22 ¦ No new note/stage change since 2026-02-22. [stuck x3] | 5-7 d | 22-Feb-26 | 127 | Yes |  |  |  |  | Broker | Completed login/project/pipeline stages; in progress bulk lead; pending report/Meta/website/Google/Acefone IVR/Wisr WhatsApp. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (31+d) | None logged | None logged | No - none logged
3304063 | Shree Honda | Sourabh Sahu | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2025-12-08 -> 2025-12-08 ¦ No new note/stage change since 2025-12-08. [stuck x3] | 5-7 d | 08-Dec-25 | 203 | Yes |  |  | 210983 | 5 | C | Still awaiting details from client to start account setup. (Customization deployed; awaiting account details.) | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Risk (31+d) | None logged | None logged | No - none logged
3575524 | Voora Developers | Raahul Ramanan R | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-02-23 -> 2026-02-23 ¦ No new note/stage change since 2026-02-23. [stuck x3] | <=5 d | 23-Feb-26 | 126 | Yes |  |  |  |  | A | PFB requirement sheet; Internal Handover scheduled tomorrow. | 90-180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Risk (31+d) | None logged | None logged | No - none logged
4255681 | SPR Construction Pvt Ltd | Sahil Jane | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-26 ¦ Internal weekly note only; pending pointers unchanged. [stuck x3] | <=5 d | 26-Jun-26 | 3 | Yes | Yes |  |  |  | A | OB Weekly Update (26 Jun): Sanket to talk to client about pending pointers. (Earlier: timesheet only.) | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4313304 | Yula Globas | Sahil Jane | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-16 ¦ No new note/stage change since 2026-06-16. [stuck x3] | <=5 d | 16-Jun-26 | 13 | Yes | Yes |  |  |  | C | Completed login/project/report/FB/WhatsApp; pending routing, portals (emails initiated), website, Mcube. | 30-60 d | Complete pending setup items and progress toward handover. | 11-15d | None logged | None logged | No - none logged
3302998 | Times Group | Sanket Nampalliwar | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2025-11-10 -> 2025-11-10 ¦ No new note/stage change since 2025-11-10. [stuck x3] | <=5 d | 10-Nov-25 | 231 | Yes |  |  | 944000 | 50 | A | UAT of inventory still in progress; multiple fields updated per client suggestions. FM-app field list shared. | >180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Risk (31+d) | None logged | None logged | No - none logged
4255693 | Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-26 ¦ Internal weekly note (wrong plan shared); customer status unchanged. [stuck x3] | <=5 d | 26-Jun-26 | 3 | Yes | Yes |  |  |  | A | OB Weekly Update (26 Jun): wrong project plan shared; Sanket to share updated plan & check status; don't pitch sub-domain. (Earlier: timesheet only.) | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4177642 | NPS DEVELOPERS | Sourabh Sahu | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x3] | <=5 d | 22-Jun-26 | 7 | Yes | Yes |  |  |  | C | Task-status table: login/project/report/routing done; WhatsApp in progress (NPS call); telecaller users awaiting client details. | 60-90 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | 6-10d | None logged | None logged | No - none logged
4144089 | Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-02 -> 2026-06-02 ¦ No new note/stage change since 2026-06-02. [stuck x3] | <=5 d | 02-Jun-26 | 27 | Yes | Yes |  |  |  | C | Sourcing training done (customer feedback pending); AI Calling in progress (unpaid); WhatsApp blocked on Meta verification. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to A) | 16-30d | None logged | None logged | No - none logged
3968505 | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-19 -> 2026-05-19 ¦ No new note/stage change since 2026-05-19. [stuck x3] | <=5 d | 19-May-26 | 41 | Yes |  |  |  |  | A | Completed login/project/report/routing/CP upload/sales training/dialer/GRE form; mostly done. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (31+d) | None logged | None logged | No - none logged
4233715 | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-01 -> 2026-06-01 ¦ No new note/stage change since 2026-06-01. [stuck x3] | <=5 d | 01-Jun-26 | 28 | Yes |  |  |  |  | C | BOT shared for testing. (AI Calling.) | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | 16-30d | None logged | None logged | No - none logged
4233760 | Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-02 -> 2026-06-02 ¦ No new note/stage change since 2026-06-02. [stuck x3] | <=5 d | 02-Jun-26 | 27 | Yes | Yes |  |  |  | C | Number details shared to Sanket; once added, will check with Sharayu. (AI Calling/Mcube.) | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | 16-30d | None logged | None logged | No - none logged
4337048 | i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-26 ¦ Still awaiting vendor for portal+IVR; weekly note is internal only. [stuck x3] | <=5 d | 26-Jun-26 | 3 | Yes |  |  |  |  | A | OB Weekly Update (26 Jun): post progress to Prabhu. Pending property portal & IVR integration (awaiting vendor); awaiting lead import & inventory files. | 14-30 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. | OK (<=5d) | None logged | None logged | No - none logged
4345401 | Sangram Group | Muntazar Mhate | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x2] | 5-7 d | 22-Jun-26 | 7 | Yes |  |  |  |  | C | Completed login/project/report/routing/Mcube IVR; pending bulk lead import. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | 6-10d | None logged | None logged | No - none logged
4334932 | New Keys Real Estate | Shweta Gouda | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x2] | 5-7 d | 19-Jun-26 | 10 | Yes |  | Yes |  | 2 | Broker | Client was on hold; received lead file 18 Jun, will upload & expedite; pending lead import, clock, website. | 14-30 d | New onboarding deal - log kickoff note + set next task. | 6-10d | None logged | None logged | No - none logged
4382909 | Dreams true realty | Sahil Jane | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-21 -> 2026-06-21 ¦ No new note/stage change since 2026-06-21. [stuck x2] | <=5 d | 21-Jun-26 | 8 | Yes |  |  |  |  | C | Completed project/report/login; pending routing, bulk lead (awaiting file), Meta (emails initiated), dialer. | 14-30 d | Customer keeps rescheduling - lock one firm slot or pause the account. | 6-10d | None logged | None logged | No - none logged
4267898 | Kalim Premier Realty LLP | Sahil Jane | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x2] | <=5 d | 19-Jun-26 | 10 | Yes | Yes |  | 28320 | 2 | C | Completed login/project/report/routing/bulk lead/Mcube(#19)/sales training; pending website, inventory. (Earlier: account on hold.) | 30-60 d | New onboarding deal - log kickoff note + set next task. | 6-10d | None logged | None logged | No - none logged
4338510 | Mundra Housing Projects LLP | Sahil Jane | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x2] | <=5 d | 19-Jun-26 | 10 | Yes | Yes |  |  |  | C | Completed login/project/report/routing/bulk lead; pending inventory, dialer, sales training (23rd June). | 14-30 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | 6-10d | None logged | None logged | No - none logged
4357586 | Pavani Infra | Shweta Gouda | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-29 ¦ Same status restated; only a kick-off mention added. [stuck x2] | <=5 d | 29-Jun-26 | 0 | Yes |  |  |  |  | C | Completed login/project/lead import/Meta(#10)/report; kick-off call referenced. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4367528 | RUDRA REALTY | Shweta Gouda | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-29 ¦ Note restates the same completed/pending list as 25-Jun. [stuck x2] | <=5 d | 29-Jun-26 | 0 | Yes |  | Yes |  |  | Broker | Completed login/teams/report/lead import/Meta(#32)/99Acres; pending tasks restated. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4386522 | Rana Propmart | Shweta Gouda | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x2] | <=5 d | 19-Jun-26 | 10 | Yes |  |  |  |  | Broker | Completed login/project/report; lead-import guidance; clock-in/out; inventory pending. | <14 d | Log first status note and book kickoff; set a next task. | 6-10d | None logged | None logged | No - none logged
4348094 | Shri Swami Samarth Assosiates Builder &Developers | Shweta Gouda | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-29 ¦ Real Estate India API still the blocker; additions were guidance only. [stuck x2] | <=5 d | 29-Jun-26 | 0 | Yes |  |  |  |  | Broker | Completed login/project/report/lead-upload guidance/Quick-Add unit; pending Real Estate India API. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4147287 | Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x2] | <=5 d | 19-Jun-26 | 10 | Yes | Yes |  |  |  | A | Completed most tasks incl Meta/portals/SV form/website/training/WhatsApp; pending bulk lead import. | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | 6-10d | None logged | None logged | No - none logged
4325921 | Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-19 ¦ No new note/stage change since 2026-06-19. [stuck x2] | <=5 d | 19-Jun-26 | 10 | Yes |  |  |  |  | C | OB tasks update: bulk lead done; pending source list, CP upload, inventory. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to B) | 6-10d | None logged | None logged | No - none logged
4370308 | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-26 ¦ Still awaiting bulk-lead files from customer - same blocker. [stuck x2] | <=5 d | 26-Jun-26 | 3 | Yes |  |  |  |  | C | Completed login/project/report/routing/99Acres; pending bulk lead (awaiting files). Prior: followed up, no response, may escalate to sales. | 14-30 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4412002 | Blueroof India | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-23 ¦ No new note/stage change since 2026-06-23. [stuck x1] | 5-7 d | 23-Jun-26 | 6 | Yes |  |  |  | 2 | C | Priority OB tasks shared (login, bulk lead, Meta, website, dialer). | <14 d | Priority tasks shared — progress integrations. | 6-10d | None logged | None logged | No - none logged
4383150 | Phantom Advisory | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | 5-7 d | 22-Jun-26 | 7 | Yes |  |  |  |  | Broker | Completed login/project/report/routing; pending bulk lead (sample shared), native WhatsApp (Meta verify). | <14 d | Log first status note and book kickoff; set a next task. | 6-10d | None logged | None logged | No - none logged
4364225 | Real Estate Square | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | 5-7 d | 22-Jun-26 | 7 | Yes |  |  |  |  | Broker | Completed login/project/report/routing/99Acres/Meta; pending bulk lead (sample shared). | 14-30 d | Complete pending setup items and progress toward handover. | 6-10d | None logged | None logged | No - none logged
4370376 | Shrimant Developers | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-23 ¦ No new note/stage change since 2026-06-23. [stuck x1] | 5-7 d | 23-Jun-26 | 6 | Yes |  |  |  |  | C | Completed login/project/report/routing/GPS/clock; pending website (initiated). | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | 6-10d | None logged | None logged | No - none logged
4370391 | Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-23 ¦ No new note/stage change since 2026-06-23. [stuck x1] | 5-7 d | 23-Jun-26 | 6 | Yes |  |  |  |  | C | Priority OB tasks shared (login, bulk lead, portals, Meta, dialer). | 14-30 d | Log first status note and book kickoff; set a next task. | 6-10d | None logged | None logged | No - none logged
4389674 | Axon Developer | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | 5-7 d | 22-Jun-26 | 7 | Yes |  |  |  |  | A | Completed account/login/project, FB connected (needs pages), 1 lead file uploaded, sales training; pending routing/hierarchy. | <14 d | Log first status note and book kickoff; set a next task. | 6-10d | None logged | None logged | No - none logged
4230613 | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | 5-7 d | 22-Jun-26 | 7 | Yes | Yes |  |  | 150 | A | PFA the updated Project Plan (Kunvarji Realtors.xlsx). | 30-60 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | 6-10d | None logged | None logged | No - none logged
3304062 | Shree Automotive | Sourabh Sahu | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2025-12-08 -> 2025-12-08 ¦ No new note/stage change since 2025-12-08. [stuck x1] | 5-7 d | 08-Dec-25 | 203 | Yes |  |  | 104784 | 4 | C | Still awaiting details from client to start account setup. (Customization deployed; awaiting account details.) | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Risk (31+d) | None logged | None logged | No - none logged
4377422 | Miva Real Estate | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-23 ¦ No new note/stage change since 2026-06-23. [stuck x1] | <=5 d | 23-Jun-26 | 6 | Yes |  |  |  |  | C | Completed login/project/report/routing/bulk lead/Meta/sales training; pending native WhatsApp (Meta not verified). | 14-30 d | Log first status note and book kickoff; set a next task. | 6-10d | None logged | None logged | No - none logged
4386888 | Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | <=5 d | 22-Jun-26 | 7 | Yes |  |  |  |  | C | Completed login/project/report/routing; pending 99Acres/MagicBricks (initiated), Meta, bulk lead, website. | <14 d | Log first status note and book kickoff; set a next task. | 6-10d | None logged | None logged | No - none logged
4430582 | Sunrise Housing (GHP Group) | Muntazar Mhate | Open | STUCK - no activity | Stage Open -> Open ¦ Note no note -> no note ¦ No new note/stage change since ?. [stuck x1] | <=5 d |  |  | No |  | Yes |  | 11 | B |  | <14 d | New deal — kickoff + sign-up; no notes yet, log first status. | Risk (never) | None logged | None logged | No - none logged
4357637 | Apex Construction | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | <=5 d | 22-Jun-26 | 7 | Yes | Yes |  |  |  | C | Completed account activation/login/project/report/routing/FB; pending native WhatsApp (website not ready). | 14-30 d | Customer keeps rescheduling - lock one firm slot or pause the account. | 6-10d | None logged | None logged | No - none logged
4389699 | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-25 -> 2026-06-25 ¦ No new note/stage change since 2026-06-25. [stuck x1] | <=5 d | 25-Jun-26 | 4 | Yes | Yes |  |  |  | C | Completed login/project/report/routing/FB; pending website, bulk lead, WhatsApp Interakt, Mcube IVR. | <14 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4382895 | SS Salesforce | Sahil Jane | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-29 ¦ Only update is sales training rescheduled to Friday - no genuine movement. [stuck x1] | <=5 d | 29-Jun-26 | 0 | Yes | Yes |  |  |  | C | Sales Training was rescheduled to Friday. | 14-30 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4383383 | VIVANTA GROUP | Shweta Gouda | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-29 ¦ Note restates the same Meta/campaign blocker as 25-Jun. [stuck x1] | <=5 d | 29-Jun-26 | 0 | Yes |  |  |  |  | C | Completed user activation/project/lead import/report; pending Meta integration (awaiting campaign). | <14 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4053797 | PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-04-27 -> 2026-04-27 ¦ No new note/stage change since 2026-04-27. [stuck x1] | <=5 d | 27-Apr-26 | 63 | Yes |  |  | 502680 | 10 | B | Completed login(1 user)/project/report/routing/bulk lead/Meta; pending DLT setup. | 60-90 d | High-value (Rs5L) Pending-on-Customer; chase customer + Mcube telephony. | Risk (31+d) | None logged | None logged | No - none logged
4402374 | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | <=5 d | 22-Jun-26 | 7 | Yes |  |  | 350000 | 15 | B | Accounts activated; completed login/project/report/source/routing; pending bulk lead (awaiting sheet). | <14 d | New onboarding deal - log kickoff note + set next task. | 6-10d | None logged | None logged | No - none logged
4358959 | YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | <=5 d | 22-Jun-26 | 7 | Yes | Yes |  |  |  | Broker | Automation for lead re-assignment done; property portal integration completed; sales training 23rd June. | 14-30 d | Log first status note and book kickoff; set a next task. | 6-10d | None logged | None logged | No - none logged
4437383 | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  |  | 100000 |  | C |  | <14 d | New deal - log first onboarding note / confirm kickoff. | Risk (never) | None logged | None logged | No - none logged
4447083 | test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | NEW this run | New in pipeline this run. | <=5 d | 29-Jun-26 | 0 | Yes | Yes | Yes | 1234 |  | Push-to-OB | test 3 (junk/test deal) | <14 d | Junk/test deal - remove from onboarding pipeline. | OK (<=5d) | None logged | None logged | No - none logged
4446933 | test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No | Yes | Yes | 1234 |  | Push-to-OB |  | <14 d | Junk/test deal - remove from onboarding pipeline. | Risk (never) | None logged | None logged | No - none logged
4446930 | test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No | Yes | Yes | 1234 |  | Push-to-OB |  | <14 d | Junk/test deal - remove from onboarding pipeline. | Risk (never) | None logged | None logged | No - none logged
4446926 | test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No | Yes | Yes | 1234 |  | Push-to-OB |  | <14 d | Junk/test deal - remove from onboarding pipeline. | Risk (never) | None logged | None logged | No - none logged
4438366 | Yashoda Infra Developer | Shweta Gouda | Open | NEW this run | New in pipeline this run. | <=5 d | 26-Jun-26 | 3 | Yes |  |  |  | 50 | (none) | Kick-off call scheduled 29th June 3pm. | <14 d | New deal; categorize the account and log first onboarding note. | OK (<=5d) | None logged | None logged | No - none logged
4446753 | SKYTOWN Group | Venkat Viswavardhan | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  |  | 500000 | 10 | A |  | <14 d | New deal - log first onboarding note / confirm kickoff. | Risk (never) | None logged | None logged | No - none logged
4435090 | SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 26-Jun-26 | 3 | Yes |  |  | 200000 | 10 | Broker | Priority OB tasks shared (login, project, Magic Bricks integration, etc.). | <14 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
4411978 | The Bangalore Real Estate Co. | Sahil Jane | Onboarding In Progress | Progressed | Stage Kickoff Done -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-23 ¦ Stage Kickoff Done -> Onboarding In Progress. | 5-7 d | 23-Jun-26 | 6 | Yes |  |  | 66316 | 7 | C | Priority OB tasks shared (login, dialer, Magic Bricks, training). | <14 d | Kickoff done — move into onboarding, start priority tasks. | 6-10d | None logged | None logged | No - none logged
4335774 | Artha Life Spaces | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> 2026-06-29 ¦ First real note logged; came off hold, now awaiting inventory decision. | <=5 d | 29-Jun-26 | 0 | Yes | Yes |  |  | 2 | C | Waiting for client response on inventory — whether to move ahead with or without it. (Earlier: on hold until SV form ready.) | 14-30 d | No notes despite 24d age; go-live already overdue — log status & push. | OK (<=5d) | None logged | None logged | No - none logged
4375201 | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-29 ¦ Inventories now uploaded since last run. | <=5 d | 29-Jun-26 | 0 | Yes |  |  |  |  | Broker | Completed login/project/report; lead-import guidance; inventories uploaded; pending clock-in/out, website (API shared). | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4415503 | TORANDWAR DEVELOPERS | Shweta Gouda | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-28 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 28-Jun-26 | 1 | Yes |  |  |  | 7 | Broker | Completed login/project/report; lead-import guidance given; inventory Quick-Add pending. | <14 d | Kick-off call scheduled 24-Jun; run it and start setup. | OK (<=5d) | None logged | None logged | No - none logged
4348936 | GARDEN OF EDEN PROPERTY DEVELOPERS PVT LTD | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-29 ¦ WhatsApp integration completed; now pending webhook - moved forward. | <=5 d | 29-Jun-26 | 0 | Yes |  |  |  |  | C | Completed login/project/report/routing/Meta/Mcube/WhatsApp; pending webhook integration. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4241966 | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-06-19 -> 2026-06-26 ¦ Moved toward handover/feedback stage with Siddharth. | <=5 d | 26-Jun-26 | 3 | Yes | Yes |  |  |  | C | OB Weekly Update (26 Jun): update contacts/tasks; follow up Vinay daily; get client feedback then discuss handover with Siddharth. | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (<=5d) | None logged | None logged | No - none logged
4402389 | Navkar Realty | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-29 ¦ Meta integration now active; callback API payload being built - new substance. | <=5 d | 29-Jun-26 | 0 | Yes |  |  | 495600 | 4 | C | Following up to confirm availability for Meta integration; callback API payload in progress (EOD). | <14 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4197691 | Raghava Elite Park | Venkat Viswavardhan | Under Usage Tracking | Progressed | Stage Onboarding In Progress -> Under Usage Tracking ¦ Note 2026-06-19 -> 2026-06-19 ¦ Stage Onboarding In Progress -> Under Usage Tracking. | <=5 d | 19-Jun-26 | 10 | Yes | Yes | Yes |  |  | B | Completed login/project/report/routing/WhatsApp/inventory; AI Calling setup done (awaiting feedback); pending GRE walk-in form. | 60-90 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to A) | 6-10d | None logged | None logged | No - none logged
4204921 | Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking | Progressed | Stage Onboarding In Progress -> Under Usage Tracking ¦ Note 2026-05-18 -> 2026-05-18 ¦ Stage Onboarding In Progress -> Under Usage Tracking. | <=5 d | 18-May-26 | 42 | Yes | Yes |  |  |  | A | Onboarding tasks update: completed login/project/report/source/routing/Meta; pending bulk lead, CP, inventory. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Risk (31+d) | None logged | None logged | No - none logged

## 5. Large-Stuck-Attention
Large deals, Stuck deals & Deals needing attention - for everyone
A) LARGE DEALS (value / licenses) - protect these
Deal | Owner | Stage | Billed (Rs) | Licenses | Cat | Status / note
Times Group | Sanket Nampalliwar | Pending on Customer | 944000 | 50 | A | UAT of inventory still in progress; multiple fields updated per client suggestions. FM-app field list shared.
PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | Pending on Customer | 502680 | 10 | B | Completed login(1 user)/project/report/routing/bulk lead/Meta; pending DLT setup.
SKYTOWN Group | Venkat Viswavardhan | Open | 500000 | 10 | A
Navkar Realty | Venkat Viswavardhan | Onboarding In Progress | 495600 | 4 | C | Following up to confirm availability for Meta integration; callback API payload in progress (EOD).
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 350000 | 15 | B | Accounts activated; completed login/project/report/source/routing; pending bulk lead (awaiting sheet).
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress |  | 150 | A | PFA the updated Project Plan (Kunvarji Realtors.xlsx).
Yashoda Infra Developer | Shweta Gouda | Open |  | 50 | (none) | Kick-off call scheduled 29th June 3pm.
B) STUCK DEALS (30+ days idle, or notes say 'no movement / on hold / call rescheduled')
Deal | Owner | Stage | Last note | Idle | Status / note
New Keys Real Estate | Shweta Gouda | Onboarding In Progress | 19-Jun-26 | 5-7 d | Client was on hold; received lead file 18 Jun, will upload & expedite; pending lead import, clock, website.
Kalim Premier Realty LLP | Sahil Jane | Onboarding In Progress | 19-Jun-26 | <=5 d | Completed login/project/report/routing/bulk lead/Mcube(#19)/sales training; pending website, inventory. (Earlier: account on hold.)
Artha Life Spaces | Sahil Jane | Onboarding In Progress | 29-Jun-26 | <=5 d | Waiting for client response on inventory — whether to move ahead with or without it. (Earlier: on hold until SV form ready.)
SS Salesforce | Sahil Jane | Onboarding In Progress | 29-Jun-26 | <=5 d | Sales Training was rescheduled to Friday.
C) NEEDS ATTENTION (paid but 'Yet to sign up', or large + go-live breached)
Deal | Owner | Stage | Billed (Rs) | Signed up? | Go-live overdue | Status / note
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | 1234 | Yet to sign up | Yes | test 3 (junk/test deal)
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | 1234 | Yet to sign up | Yes
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | 1234 | Yet to sign up | Yes
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | 1234 | Yet to sign up | Yes
New Keys Real Estate | Shweta Gouda | Onboarding In Progress |  | Yet to sign up |  | Client was on hold; received lead file 18 Jun, will upload & expedite; pending lead import, clock, website.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress |  | - | Yes | PFA the updated Project Plan (Kunvarji Realtors.xlsx).
Raghava Elite Park | Venkat Viswavardhan | Under Usage Tracking |  | Yet to sign up | Yes | Completed login/project/report/routing/WhatsApp/inventory; AI Calling setup done (awaiting feedback); pending GRE walk-in form.

## 6. Pending-on-Customer Check
'Pending on Customer' validation - is it really moving?
12 deals sit in this stage. Verdict from last 2-3 notes + activity.
Deal | Owner | Last note | Days since | Verdict | Clear next action
i5 Housing and Properties LLP | Venkat Viswavardhan | 26-Jun-26 | 3 | STUCK | Awaiting vendor for portal+IVR & client files since mid-Jun; weekly note is internal only. Escalate, set drop-dead date.
Ribitto Private Limited | Muntazar Mhate | 22-Jun-26 | 7 | STUCK | No genuine note movement in 3 runs; pending bulk lead + FB from customer. Escalate / chase lead file.
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | 26-Jun-26 | 3 | STUCK | Wrong project plan shared; Sanket to re-share & confirm. No real customer movement in 3 runs.
Kohinoor AI Calling | Venkat Viswavardhan | 01-Jun-26 | 28 | STUCK | BOT shared for testing; awaiting Mcube number from customer since ~May. Chase; set test date.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | 22-Feb-26 | 127 | STUCK | Last real note Feb-26; many integrations pending. Re-open kickoff or escalate.
Voora Developers | Raahul Ramanan R | 23-Feb-26 | 126 | STUCK | Handover scheduled in Feb never happened. Escalate; re-open.
Shree Honda | Sourabh Sahu | 08-Dec-25 | 203 | STUCK | Awaiting client details since Dec to start setup. Final call or move to HOLD.
Times Group | Sanket Nampalliwar | 10-Nov-25 | 231 | STUCK | Inventory UAT dragging since Nov. Escalate to close UAT and sign off.
PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | 27-Apr-26 | 63 | Customer-blocked | Pending DLT setup; awaiting customer. Re-confirm and set a date.
GGC AI Calling | Venkat Viswavardhan | 26-Jun-26 | 3 | Moving slowly | Approaching handover; awaiting client feedback. Get feedback then handover with Siddharth.
Dreamworks Realtors | Venkat Viswavardhan | 19-Jun-26 | 10 | Near done | Almost all tasks complete; only bulk lead import pending. Close out & handover.
Gram Strategic Advisors LLP | Muntazar Mhate | 25-May-26 | 35 | Near done | Most complete (Broker). Schedule final handover this week.

## 7. Customer Category
Customer Category - usage & priority check
A/B/C/Broker should drive onboarding priority & SLA. Today it is captured but not acted on.
Distribution & risk by category
Category | Deals | % of pipe | Idle 5+ d | No notes | Not signed up | Go-live overdue
A (top priority) | 11 | 17% | 2 | 1 | 0 | 5
B | 6 | 9% | 2 | 1 | 2 | 1
C | 31 | 48% | 9 | 1 | 0 | 11
Broker | 11 | 17% | 4 | 0 | 2 | 1
Uncategorized | 1 | 2% | 0 | 0 | 0 | 0
Total | 60
What this tells us
- A-grade = your most important accounts, yet 2 of 15 have had NO activity in 5+ days and 1 have no notes at all. Priority is captured but the A's are actually the most neglected.
- Category is not used to prioritise: A deals (Kunwarji 150 lic, Times, Dhanvanthari, Sandeep) sit stuck alongside C deals with the same (lack of) attention.
- Category does not track value/size consistently: the single biggest deal, Raghava Elite Park (~Rs12.1L), is tagged B, not A; while several small C deals are routine. Re-grade against value+licenses.
- 6 deals are Uncategorized (incl. Krishvi which is already Active, plus Pavani, Rana, Dreams True) - they fall through prioritisation entirely. 'dummy' is also uncategorized.
- 52% of the pipeline (43) is tagged C. Either genuinely low-value, or default/lazy tagging - worth a quick audit so C actually means C.
- Recommendation: tie an SLA to category - A = white-glove, named owner, weekly touch + exec visibility; B = fortnightly; C/Broker = templatised. Make category mandatory and value-aligned at deal creation.
A-GRADE WATCHLIST (protect these 15 - sorted by neglect)
Deal | Owner | Stage | Idle | Last note | Billed (Rs) | Lic | Status / note
Axon Developer | Sahil Jane | Onboarding In Progress | 5-7 d | 22-Jun-26 |  |  | Completed account/login/project, FB connected (needs pages), 1 lead file uploaded, sales training; pending routing/hierarchy.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | 5-7 d | 22-Jun-26 |  | 150 | PFA the updated Project Plan (Kunvarji Realtors.xlsx).
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Pending on Customer | <=5 d | 26-Jun-26 |  |  | OB Weekly Update (26 Jun): wrong project plan shared; Sanket to share updated plan & check status; don't pitch sub-domain. (Earlier: timesheet only.)
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | <=5 d | 19-Jun-26 |  |  | Completed most tasks incl Meta/portals/SV form/website/training/WhatsApp; pending bulk lead import.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 19-May-26 |  |  | Completed login/project/report/routing/CP upload/sales training/dialer/GRE form; mostly done.
SKYTOWN Group | Venkat Viswavardhan | Open | <=5 d |  | 500000 | 10
SPR Construction Pvt Ltd | Sahil Jane | Onboarding In Progress | <=5 d | 26-Jun-26 |  |  | OB Weekly Update (26 Jun): Sanket to talk to client about pending pointers. (Earlier: timesheet only.)
Times Group | Sanket Nampalliwar | Pending on Customer | <=5 d | 10-Nov-25 | 944000 | 50 | UAT of inventory still in progress; multiple fields updated per client suggestions. FM-app field list shared.
Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking | <=5 d | 18-May-26 |  |  | Onboarding tasks update: completed login/project/report/source/routing/Meta; pending bulk lead, CP, inventory.
Voora Developers | Raahul Ramanan R | Pending on Customer | <=5 d | 23-Feb-26 |  |  | PFB requirement sheet; Internal Handover scheduled tomorrow.
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | <=5 d | 26-Jun-26 |  |  | OB Weekly Update (26 Jun): post progress to Prabhu. Pending property portal & IVR integration (awaiting vendor); awaiting lead import & inventory files.

## 8. Re-grade (value+brand)
Category re-grade - value + licenses + brand/enterprise
Suggested grade = max of value, licence count, and brand/enterprise weight. Under-grading is the concern; higher-than-needed is low priority.
Summary: 8 under-graded (fix), 5 ungraded (set a grade), 0 clearly over-graded (low priority). ~8 A-deals score B on size alone (20-49 lic) - acceptable for enterprise/brand, not listed.
A) UNDER-GRADED - high value/brand but graded low (FIX THESE)
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Dhanraj Realbuild Llp | Venkat Viswavardhan | C | A | 60-90 d | Rs5-7L | <10/blank |  | billed Rs5-7L
Raghava Elite Park | Venkat Viswavardhan | B | A | 60-90 d | >=Rs7L | 10-19 | Strong | billed >=Rs7L; strong brand
GARDEN OF EDEN PROPERTY DEVELOPERS PVT LTD | Venkat Viswavardhan | C | B | 14-30 d | Rs2-3L | <10/blank |  | billed Rs2-3L
Kohinoor AI Calling | Venkat Viswavardhan | C | B | 30-60 d | blank/<1L | <10/blank | Known | known brand
NPS DEVELOPERS | Sourabh Sahu | C | B | 60-90 d | Rs3-5L | 10-19 |  | billed Rs3-5L
Shree Honda | Sourabh Sahu | C | B | >180 d | Rs2.11L | 5 |  | billed Rs2.11L
Sujay Global Homes | Venkat Viswavardhan | C | B | 30-60 d | Rs3-5L | <10/blank |  | billed Rs3-5L
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | C | B | 14-30 d | Rs2-3L | <10/blank |  | billed Rs2-3L
B) UNGRADED - no category set (assign one)
Includes Krishvi (already Active) and the 'dummy' test record.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Yashoda Infra Developer | Shweta Gouda | (none) | C | <14 d | (blank) | 50+ | Yashoda Infra Developer | uncategorized - new deal
Rana Propmart | Shweta Gouda | Broker | C | <14 d | blank/<1L | <10/blank |  | no value/licenses captured
Dreams true realty | Sahil Jane | C | C | 14-30 d | blank/<1L | <10/blank |  | no value/licenses captured
Pavani Infra | Shweta Gouda | C | C | 14-30 d | blank/<1L | <10/blank |  | no value/licenses captured
Shri Swami Samarth Assosiates Builder &Developers | Shweta Gouda | Broker | C | 14-30 d | blank/<1L | 10-19 |  | small ticket (blank/<1L, 10-19 lic)
C) Clearly over-graded - review (low priority)
B Square is actually live - close it rather than re-grade.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why

## 9. Comparison & Movement
Comparison & Movement vs previous run(s)
Run 4 (Mon 29-Jun-2026) vs 25-Jun & 22-Jun
Deal | Owner | Stage prev->now | Last note prev->now | Movement verdict | Stuck streak | Reason / action
Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-18 -> 2026-06-18 | No-touch | 3 | No new note/stage change since 2026-06-18.
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-26 | Same-blocker | 3 | Internal weekly note (wrong plan shared); customer status unchanged.
Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-02 -> 2026-06-02 | No-touch | 3 | No new note/stage change since 2026-06-02.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-05-19 -> 2026-05-19 | No-touch | 3 | No new note/stage change since 2026-05-19.
Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-05-25 -> 2026-05-25 | No-touch | 3 | No new note/stage change since 2026-05-25.
Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-01 -> 2026-06-01 | No-touch | 3 | No new note/stage change since 2026-06-01.
Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-02 -> 2026-06-02 | No-touch | 3 | No new note/stage change since 2026-06-02.
NPS DEVELOPERS | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 3 | No new note/stage change since 2026-06-22.
Ribitto Private Limited | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-22 | No-touch | 3 | No new note/stage change since 2026-06-22.
SPR Construction Pvt Ltd | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-26 | Same-blocker | 3 | Internal weekly note only; pending pointers unchanged.
Shree Honda | Sourabh Sahu | Pending on Customer -> Pending on Customer | 2025-12-08 -> 2025-12-08 | No-touch | 3 | No new note/stage change since 2025-12-08.
Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Open -> Open | 2026-06-22 -> 2026-06-22 | No-touch | 3 | No new note/stage change since 2026-06-22.
Times Group | Sanket Nampalliwar | Pending on Customer -> Pending on Customer | 2025-11-10 -> 2025-11-10 | No-touch | 3 | No new note/stage change since 2025-11-10.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-02-22 -> 2026-02-22 | No-touch | 3 | No new note/stage change since 2026-02-22.
Voora Developers | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-02-23 -> 2026-02-23 | No-touch | 3 | No new note/stage change since 2026-02-23.
Yula Globas | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-16 -> 2026-06-16 | No-touch | 3 | No new note/stage change since 2026-06-16.
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-26 | Same-blocker | 3 | Still awaiting vendor for portal+IVR; weekly note is internal only.
Dreams true realty | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-21 -> 2026-06-21 | No-touch | 2 | No new note/stage change since 2026-06-21.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-19 -> 2026-06-19 | No-touch | 2 | No new note/stage change since 2026-06-19.
Kalim Premier Realty LLP | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 2 | No new note/stage change since 2026-06-19.
Mundra Housing Projects LLP | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 2 | No new note/stage change since 2026-06-19.
New Keys Real Estate | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 2 | No new note/stage change since 2026-06-19.
Pavani Infra | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-29 | Same-blocker | 2 | Same status restated; only a kick-off mention added.
RUDRA REALTY | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-29 | Same-blocker | 2 | Note restates the same completed/pending list as 25-Jun.
Rana Propmart | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 2 | No new note/stage change since 2026-06-19.
Sangram Group | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 2 | No new note/stage change since 2026-06-22.
Shri Swami Samarth Assosiates Builder &Developers | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-29 | Same-blocker | 2 | Real Estate India API still the blocker; additions were guidance only.
Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-19 | No-touch | 2 | No new note/stage change since 2026-06-19.
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-26 | Same-blocker | 2 | Still awaiting bulk-lead files from customer - same blocker.
Apex Construction | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
Axon Developer | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
Blueroof India | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-23 | No-touch | 1 | No new note/stage change since 2026-06-23.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
Leonaara PVt LTD | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-25 -> 2026-06-25 | No-touch | 1 | No new note/stage change since 2026-06-25.
Miva Real Estate | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-23 | No-touch | 1 | No new note/stage change since 2026-06-23.
PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-04-27 -> 2026-04-27 | No-touch | 1 | No new note/stage change since 2026-04-27.
Phantom Advisory | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
Real Estate Square | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
SS Salesforce | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-29 | Same-blocker | 1 | Only update is sales training rescheduled to Friday - no genuine movement.
Shree Automotive | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2025-12-08 -> 2025-12-08 | No-touch | 1 | No new note/stage change since 2025-12-08.
Shrimant Developers | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-23 | No-touch | 1 | No new note/stage change since 2026-06-23.
Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-23 | No-touch | 1 | No new note/stage change since 2026-06-23.
Sunrise Housing (GHP Group) | Muntazar Mhate | Open -> Open | - -> - | No-touch | 1 | No new note/stage change since ?.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
VIVANTA GROUP | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-29 | Same-blocker | 1 | Note restates the same Meta/campaign blocker as 25-Jun.
YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
Artha Life Spaces | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | - -> 2026-06-29 | Progressed | 0 | First real note logged; came off hold, now awaiting inventory decision.
Aryma Infra (OPC)Pvt Ltd | Sahil Jane | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
GARDEN OF EDEN PROPERTY DEVELOPERS PVT LTD | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-29 | Progressed | 0 | WhatsApp integration completed; now pending webhook - moved forward.
GGC AI Calling | Venkat Viswavardhan | Onboarding In Progress -> Pending on Customer | 2026-06-19 -> 2026-06-26 | Progressed | 0 | Moved toward handover/feedback stage with Siddharth.
Navkar Realty | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-29 | Progressed | 0 | Meta integration now active; callback API payload being built - new substance.
Raghava Elite Park | Venkat Viswavardhan | Onboarding In Progress -> Under Usage Tracking | 2026-06-19 -> 2026-06-19 | Progressed | 0 | Stage Onboarding In Progress -> Under Usage Tracking.
SKYTOWN Group | Venkat Viswavardhan | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | NEW this run | - -> 2026-06-26 | NEW | 0 | New in pipeline this run.
Strata Capital Holdings | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-29 | Progressed | 0 | Inventories now uploaded since last run.
TORANDWAR DEVELOPERS | Shweta Gouda | Open -> Onboarding In Progress | 2026-06-23 -> 2026-06-28 | Progressed | 0 | Stage Open -> Onboarding In Progress.
The Bangalore Real Estate Co. | Sahil Jane | Kickoff Done -> Onboarding In Progress | 2026-06-23 -> 2026-06-23 | Progressed | 0 | Stage Kickoff Done -> Onboarding In Progress.
Vascon Engineers | Venkat Viswavardhan | Onboarding In Progress -> Under Usage Tracking | 2026-05-18 -> 2026-05-18 | Progressed | 0 | Stage Onboarding In Progress -> Under Usage Tracking.
Yashoda Infra Developer | Shweta Gouda | NEW this run | - -> 2026-06-26 | NEW | 0 | New in pipeline this run.
test deal Push to OB 63 Copy | Sanket Nampalliwar | NEW this run | - -> 2026-06-29 | NEW | 0 | New in pipeline this run.
test deal Push to OB 63 Copy | Sanket Nampalliwar | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
test deal Push to OB 63 Copy | Sanket Nampalliwar | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
test deal Push to OB 63 Copy | Sanket Nampalliwar | NEW this run | - -> - | NEW | 0 | New in pipeline this run.