## 1. Stats
Sell.do Onboarding Pipeline - Statistics
Pipeline 27474 ¦ 67 open deals ¦ Snapshot 2026-07-02
Ageing = days since deal CREATED (created_at). Movement = days since last activity (separate metric).
By Owner
Category | Count
Venkat Viswavardhan | 18
Sahil Jane | 15
Muntazar Mhate | 15
Shweta Gouda | 12
Sourabh Sahu | 3
Sanket Nampalliwar | 2
Raahul Ramanan R | 2
Total | 67
By Pipeline Stage
Category | Count
Open | 3
Kickoff Done | 3
Onboarding In Progress | 47
Pending on Customer | 12
Under Usage Tracking | 0
Total | 65
Deal Ageing = days since CREATED (created_at)
Category | Count
<14 days | 17
14-30 days | 21
30-60 days | 15
60-90 days | 7
90-180 days | 3
180+ days | 4
Total | 67
Movement = days since LAST ACTIVITY
Category | Count
<=5 days (healthy) | 60
5-7 days | 3
7-15 days | 4
15-30 days | 0
30+ days | 0
Total | 67
Touch cadence = days since LAST NOTE (interim proxy until meetings are logged)
Category | Count
<=5 days (OK) | 54
6-10 days | 9
11-15 days | 0
16-30 days | 0
31+ days | 0
Never (no note) | 4
Total | 67
Meetings ON DEALS (not yet logged - format ready going forward)
Category | Count
Deals with a meeting logged on the deal | 0
Meeting scheduled/conducted within 5 days | 0
NO meeting logged (team to start logging) | 67
Risk & Data-Quality Flags
Category | Count
No activity 5+ days (your risk rule) | 7
No notes logged at all | 4
Target go-live date already breached | 21
Customer 'Yet to sign up' | 8
No future follow-up task | 39
Has an OVERDUE task | 17
Billed Amount field blank | 52
Estimated Value populated | 0
Meetings linked to these onboarding deals | 0

## 2. Exec Summary (CEO-CRO)
Onboarding Pipeline - Executive Summary
For CEO & CRO ¦ 2026-07-02
The headline (movement this run)
67 deals are open in onboarding. Comparing today vs the last run: 34 have GENUINELY PROGRESSED, but 25 have NOT moved (17 restate the same blocker, 8 had no activity at all) and 21 of those have now been stuck for 2+ consecutive runs (SUPER-RED - see Sheet 9). 8 deals are new this run. 21 deals (31%) are already past their committed go-live date.
Data hygiene is still the structural issue: Billed Amount is blank on 52 of 67 deals (78%), Estimated Value is empty on every deal, 39 of 67 have no next task, and 4 deals still have zero notes. Revenue-at-risk remains invisible in standard reports.
Where the money is exposed
Cash collected but customer still 'Yet to sign up': VRUSHABADRI Developers Rs2.42L, Supreme Vision (Augusta Realty) Rs1.48L, VASTU Infinity Rs33k - all fully received but not activated. Push these to sign-up now.
Largest accounts by value: Times Group Rs9.44L (Pending-on-Customer - client UAT feedback overdue since 23-Jun), PRABHUKRUPA Rs5.03L, SKYTOWN Rs5.0L, Navkar Rs4.96L. Largest by licences: Kunwarji Realtors - 150 licences, Category A, go-live breached, only a single 'project plan' note and no next task.
What we are asking leadership to back
1. A weekly onboarding hygiene standard: every open deal must have a LOGGED MEETING (scheduled or conducted) at least every 5 days, a dated note, and a next task; stage moved at each milestone. (Meetings are still not logged on deals at all.)
2. Make Billed Amount mandatory at deal creation so revenue-at-risk is visible (blank on 78% today).
3. A weekly SUPER-RED review: 21 deals have not genuinely moved for 2+ runs - most are stuck 'pending on customer'. Set drop-dead dates or move to HOLD.
4. A 'collections + activation' sweep on the paid-but-dormant accounts above (CRO + Onboarding).

## 3. Owner Scorecard
Owner Scorecard - gaps for the Onboarding Head
Counts per owner across the key risk flags. Use for owner 1:1s.
Owner | Open deals | A-grade | Idle 5+ d | No notes | Go-live overdue | Not signed up | No next task | Overdue task | Key gap to address
Venkat Viswavardhan | 18 | 5 | 0 | 0 | 4 | 1 | 6 | 4 | 18 deal(s). pending-on-customer: i5 Housing and Properties LLP, GGC AI Calling, Kohinoor AI Calling, Dreamworks Realtors, PRABHUKRUPA REALTIES PVT. LTD.
Sahil Jane | 15 | 2 | 1 | 2 | 9 | 2 | 10 | 4 | 15 deal(s). no notes: VRUSHABADRI DEVELOPERS, VASTU INFINITY AND VENTURES LLP.
Muntazar Mhate | 15 | 0 | 0 | 0 | 0 | 2 | 15 | 0 | 15 deal(s). pending-on-customer: Ribitto Private Limited, Gram Strategic Advisors LLP.
Shweta Gouda | 12 | 1 | 0 | 2 | 6 | 3 | 7 | 3 | 12 deal(s). no notes: Supreme Vision Infrabuild Private Limited (Augusta Realty), PROPKART4U. pending-on-customer: Calicut Landmark Builders Pvt. Ltd.
Sourabh Sahu | 3 | 0 | 3 | 0 | 1 | 0 | 1 | 2 | 3 deal(s). pending-on-customer: Shree Honda.
Sanket Nampalliwar | 2 | 2 | 1 | 0 | 1 | 0 | 0 | 2 | 2 deal(s). pending-on-customer: Times Group.
Raahul Ramanan R | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 2 deal(s). pending-on-customer: Upcurve consumer Technologies Pvt Ltd, Voora Developers.
TOTAL | 67 | 11 | 7 | 4 | 21 | 8 | 39 | 17

## 4. Deal-Level Tracker
Deal-Level Tracker - for the Onboarding Head to action
Cols E-F = movement vs the LAST run: Progressed / NEW / STUCK (same blocker or no activity). Stuck deals are grouped at the top. SUPER-RED = no genuine movement for 2+ consecutive runs.
Deal ID | Deal Name | Owner | Stage | Moved? (vs last run) | Movement detail (prev -> now) | Last activity | Last note date | Days since note | Has notes | Go-live overdue | Not signed up | Billed (Rs) | Licenses | Cat | Last note / status | Age (created) | Key Next Step (recommended) | Touch cadence (interim, vs 5d) | Last meeting | Next meeting | Mtg <=5d?
3623014 | Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer | SUPER-RED (4 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-02-22 -> 2026-06-22 ¦ Escalated & on Pause - POC unresponsive; deteriorating. [stuck x4] | 7-15 d | 22-Jun-26 | 10 | Yes |  |  |  |  | Broker | Escalated account; Onboarding on Pause as POC is unresponsive. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
3575524 | Voora Developers | Raahul Ramanan R | Pending on Customer | SUPER-RED (4 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-02-23 -> 2026-06-26 ¦ Stuck since Feb; still aligning MD meeting/handover - no genuine movement. [stuck x4] | 5-7 d | 26-Jun-26 | 6 | Yes |  |  |  |  | A | OB Weekly Update (26-Jun): update notes w/ timelines; check Chennai team visit; Sanket to call MD and align meeting. | 90-180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4255681 | SPR Construction Pvt Ltd | Sahil Jane | Onboarding In Progress | SUPER-RED (4 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-26 -> 2026-06-26 ¦ No new note/stage change since 2026-06-26. [stuck x4] | 5-7 d | 26-Jun-26 | 6 | Yes | Yes |  |  |  | A | OB Weekly Update (26-Jun): Sanket to talk to client about pending pointers. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4262054 | Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress | SUPER-RED (4 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-18 -> 2026-06-30 ¦ Website integration still the only pending item; unchanged - no movement. [stuck x4] | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | B | Completed login/project/report/routing/bulk lead/FB/dialer/GPS/sales training; pending website integration. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4079157 | Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer | SUPER-RED (4 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-05-25 -> 2026-06-30 ¦ Setup long done; now only awaiting client to confirm onsite-visit date - no task completed. [stuck x4] | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | B | Client to check team availability and confirm day for an onsite visit. | 60-90 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4299438 | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | SUPER-RED (4 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-30 ¦ Identical pending items (bulk lead, FB); no movement - 4 runs stuck. [stuck x4] | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | Completed login/project/report/routing/WATI/dialer/GPS/admin training; pending bulk lead, FB. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
3302998 | Times Group | Sanket Nampalliwar | Pending on Customer | SUPER-RED (4 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2025-11-10 -> 2026-06-22 ¦ Still in client UAT (feedback due 23-Jun, now overdue); no new note since - stalled. [stuck x4] | <=5 d | 22-Jun-26 | 10 | Yes |  |  | 944000 | 50 | A | Unit data uploaded to demo account, dashboards ready; client doing UAT, feedback by 23-Jun EOD. | >180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4255693 | Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Pending on Customer | SUPER-RED (4 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-26 -> 2026-06-30 ¦ Only a timesheet/plan update; lead import, hierarchy approval & inventory still pending on customer. [stuck x4] | <=5 d | 30-Jun-26 | 2 | Yes | Yes |  |  |  | A | Updated timesheet; pending lead import (client doing), hierarchy approval, inventory. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4144089 | Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (4 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-02 -> 2026-06-30 ¦ Still blocked on virtual-number pricing / AI-calling payment / Meta verification; only MIS report shared. [stuck x4] | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | Followed up with Ankur on virtual number pricing (awaiting); MIS report shared, customer to revert. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to A) | OK (<=5d) | None logged | None logged | No - none logged
3968505 | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (4 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-05-19 -> 2026-07-01 ¦ Still awaiting GRE-form dev + Re-OB; only Jira updated - no customer-facing progress. [stuck x4] | <=5 d | 01-Jul-26 | 1 | Yes |  |  |  |  | A | Requirement received and JIRA updated; awaiting update from team. (Flagged Re-OB, plan go-live). | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4233715 | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | SUPER-RED (4 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-01 -> 2026-06-30 ¦ Still awaiting customer to test outgoing AI calls; only a smartlist Jira added. [stuck x4] | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | Jira raised for smartlist creation; customer checking outgoing calls. | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4345401 | Sangram Group | Muntazar Mhate | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-07-01 ¦ Bulk lead still pending; now also awaiting client's WhatsApp number - no task completed. [stuck x3] | <=5 d | 01-Jul-26 | 1 | Yes |  |  |  |  | C | Client will update tomorrow re new number for WhatsApp integration and bulk lead import. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4357586 | Pavani Infra | Shweta Gouda | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-06-29 ¦ No new note/stage change since 2026-06-29. [stuck x3] | <=5 d | 29-Jun-26 | 3 | Yes | Yes |  |  |  | C | Completed login/project/report/Meta (#10); guided lead import; kickoff call done. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4367528 | RUDRA REALTY | Shweta Gouda | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-06-29 ¦ No new note/stage change since 2026-06-29. [stuck x3] | <=5 d | 29-Jun-26 | 3 | Yes |  | Yes |  |  | Broker | Completed login/teams/report/Meta (lead #32); guided lead import; pending remaining setup. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4348094 | Shri Swami Samarth Assosiates Builder &Developers | Shweta Gouda | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-06-29 ¦ No new note/stage change since 2026-06-29. [stuck x3] | <=5 d | 29-Jun-26 | 3 | Yes | Yes |  |  |  | Broker | Completed login/project/report/portal(99acres,magicbricks); guided lead upload; quick-add unit; pending Real Estate India API. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4230613 | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x2] | 7-15 d | 22-Jun-26 | 10 | Yes | Yes |  |  | 150 | A | PFA the updated Project Plan (Kunvarji Realtors.xlsx). | 30-60 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Watch | None logged | None logged | No - none logged
4383150 | Phantom Advisory | Muntazar Mhate | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-30 ¦ Identical pending items (bulk lead, WhatsApp/Meta verification). [stuck x2] | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | B | Completed login/project/report/routing; pending bulk lead, native WhatsApp (Meta suite verification). | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4386888 | Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-30 ¦ Portals still only 'initiated'; nothing newly completed. [stuck x2] | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | Completed login/project/report/routing; property portal (99acres, magicbricks) integrations initiated. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4370376 | Shrimant Developers | Muntazar Mhate | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-30 ¦ Website still only 'initiated'; identical to last run. [stuck x2] | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | Completed login/project/report/routing/GPS/clock-in; pending website integration (initiated). | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4370391 | Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-30 ¦ Note explicitly says 'no movement from client side'. [stuck x2] | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | No movement from client side. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4383383 | VIVANTA GROUP | Shweta Gouda | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-06-29 ¦ No new note/stage change since 2026-06-29. [stuck x2] | <=5 d | 29-Jun-26 | 3 | Yes |  |  |  |  | C | Completed user activation/project/lead import/report; pending Meta integration (awaiting campaign). | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4335774 | Artha Life Spaces | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-06-29 ¦ No new note/stage change since 2026-06-29. [stuck x1] | <=5 d | 29-Jun-26 | 3 | Yes | Yes |  |  | 2 | C | Waiting for client response on inventory - whether to move ahead with or without inventory. | 30-60 d | No notes despite 24d age; go-live already overdue — log status & push. | OK (<=5d) | None logged | None logged | No - none logged
4437383 | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> 2026-06-30 ¦ On hold till Monday per client request - no active progress. [stuck x1] | <=5 d | 30-Jun-26 | 2 | Yes |  |  | 100000 |  | C | Account on hold till Monday as per client request. | <14 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
4415503 | TORANDWAR DEVELOPERS | Shweta Gouda | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-28 -> 2026-06-28 ¦ No new note/stage change since 2026-06-28. [stuck x1] | <=5 d | 28-Jun-26 | 4 | Yes |  |  |  | 7 | Broker | Completed login/project/report; guided lead import; inventory quick-add discussed. | <14 d | Kick-off call scheduled 24-Jun; run it and start setup. | OK (<=5d) | None logged | None logged | No - none logged
4435090 | SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-26 -> 2026-06-30 ¦ Still awaiting details from customer; only a follow-up since last run. [stuck x1] | <=5 d | 30-Jun-26 | 2 | Yes |  |  | 200000 | 10 | Broker | Followed up with customer; they will share details today. | <14 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
4457232 | Growthx Estates | Muntazar Mhate | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 01-Jul-26 | 1 | Yes |  | Yes |  | 10 | Broker | Priority onboarding task list shared (login, project, report, routing, bulk lead, portals, FB, Google). | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4449587 | Rajparis Civil Construction | Muntazar Mhate | Kickoff Done | NEW this run | New in pipeline this run. | <=5 d | 01-Jul-26 | 1 | Yes |  | Yes |  | 15 | B | Priority onboarding tasks shared; awaiting POC email to share portal API details. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4458749 | Properties Boutique | Sahil Jane | Kickoff Done | NEW this run | New in pipeline this run. | <=5 d | 01-Jul-26 | 1 | Yes |  |  | 61360 | 7 | C | Priority onboarding task list shared (login, project, report, Meta, portals, dialer, training). | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4458766 | VASTU INFINITY AND VENTURES LLP | Sahil Jane | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  | Yes | 33000 | 5 | C |  | <14 d | Log first note + confirm kickoff / next milestone. | No note | None logged | None logged | No - none logged
4458771 | VRUSHABADRI DEVELOPERS | Sahil Jane | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  | Yes | 241900 | 8 | C |  | <14 d | Log first note + confirm kickoff / next milestone. | No note | None logged | None logged | No - none logged
3417644 | House of Colours | Shweta Gouda | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 25-Jun-26 | 7 | Yes | Yes |  |  |  | C | Account on Hold - client does not want to proceed due to Magicbricks listing tagging concern. | >180 d | Log first note + confirm kickoff / next milestone. | Watch | None logged | None logged | No - none logged
4449855 | PROPKART4U | Shweta Gouda | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  |  |  |  | Broker |  | <14 d | Log first note + confirm kickoff / next milestone. | No note | None logged | None logged | No - none logged
4453288 | Supreme Vision Infrabuild Private Limited (Augusta Realty) | Shweta Gouda | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  | Yes | 147500 | 4 | C |  | <14 d | Log first note + confirm kickoff / next milestone. | No note | None logged | None logged | No - none logged
3304062 | Shree Automotive | Sourabh Sahu | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2025-12-08 -> 2026-06-22 ¦ DND & NDNC details finally received from client; Mcube setup next - real unblock. | 7-15 d | 22-Jun-26 | 10 | Yes |  |  | 104784 | 4 | C | DND & NDNC details received from client; will set up Mcube tomorrow. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Watch | None logged | None logged | No - none logged
3304063 | Shree Honda | Sourabh Sahu | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2025-12-08 -> 2026-06-22 ¦ DND & NDNC details finally received from client; Mcube setup next - real unblock. | 7-15 d | 22-Jun-26 | 10 | Yes |  |  | 210983 | 5 | C | DND & NDNC details received from client; will set up Mcube tomorrow. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Watch | None logged | None logged | No - none logged
4177642 | NPS DEVELOPERS | Sourabh Sahu | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-26 ¦ WhatsApp & Mcube setup completed vs in-progress last run. | 5-7 d | 26-Jun-26 | 6 | Yes | Yes |  |  |  | C | OB Weekly Update (26-Jun): WhatsApp & Mcube setup completed; Sourabh to check with client re post-sales Re-OB. | 60-90 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | Watch | None logged | None logged | No - none logged
4412002 | Blueroof India | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-30 ¦ Login/project/report/routing/GPS/clock-in now completed vs task-list only. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  | 2 | C | Completed login/project/report/routing/GPS/clock-in; pending bulk lead, Meta, website. | <14 d | Priority tasks shared — progress integrations. | OK (<=5d) | None logged | None logged | No - none logged
4377422 | Miva Real Estate | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-30 ¦ Property-portal integration initiated + Meta/FB done; active work continuing. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | Completed login/project/report/routing/bulk lead/FB/Meta; property portal (magicbricks, 99acres) initiated. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4364225 | Real Estate Square | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-30 ¦ Admin training completed since last run; bulk lead still pending. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | Broker | Completed login/project/report/routing/99acres/FB/admin training; pending bulk lead (sample shared). | 14-30 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4336926 | Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-30 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | Priority onboarding tasks now shared (login/project/report/routing/bulk lead/website) after kickoff-pending phase. | 30-60 d | Chase kickoff slot; escalate to customer exec if no response in 5 days. | OK (<=5d) | None logged | None logged | No - none logged
4430582 | Sunrise Housing (GHP Group) | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-06-30 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  | 11 | B | Priority onboarding tasks shared (login/project/report/routing/bulk lead/Meta/website/WhatsApp). | <14 d | New deal — kickoff + sign-up; no notes yet, log first status. | OK (<=5d) | None logged | None logged | No - none logged
4357637 | Apex Construction | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-30 ¦ Bulk lead, sales training & inventory completed since last run. | <=5 d | 30-Jun-26 | 2 | Yes | Yes |  |  |  | C | Completed account activation/login/project/report/routing/FB/bulk lead/sales training/inventory; pending dialer. | 14-30 d | Customer keeps rescheduling - lock one firm slot or pause the account. | OK (<=5d) | None logged | None logged | No - none logged
4389674 | Axon Developer | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-29 ¦ Hierarchy, routing & bulk lead now completed vs pending last run. | <=5 d | 29-Jun-26 | 3 | Yes |  |  |  |  | A | Completed account/login/project/hierarchy/routing/bulk lead/FB; pending workflow setup, Meta pixel. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4382909 | Dreams true realty | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-21 -> 2026-06-30 ¦ Meta integration + sales training completed; now only admin training awaiting client. | <=5 d | 30-Jun-26 | 2 | Yes | Yes |  |  |  | C | No response from client end for admin training. | 14-30 d | Customer keeps rescheduling - lock one firm slot or pause the account. | OK (<=5d) | None logged | None logged | No - none logged
4267898 | Kalim Premier Realty LLP | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-30 ¦ Inventory completed + website integration email sent vs pending last run. | <=5 d | 30-Jun-26 | 2 | Yes | Yes |  | 28320 | 2 | C | Completed login/project/report/routing/bulk lead/Mcube(#19)/inventory/sales training; pending website (email sent). | 30-60 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4389699 | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-25 -> 2026-06-30 ¦ Campaign/source creation + first lead file uploaded since last run. | <=5 d | 30-Jun-26 | 2 | Yes | Yes |  |  |  | C | Completed login/account/project/report/campaign/routing/FB; 1 lead file uploaded; pending website, bulk lead, WhatsApp, Mcube. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4338510 | Mundra Housing Projects LLP | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-30 ¦ Dialer + sales + admin training completed since last run. | <=5 d | 30-Jun-26 | 2 | Yes | Yes |  |  |  | C | Completed account/login/project/report/routing/bulk lead/dialer/sales+admin training; pending property portal. | 14-30 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4382895 | SS Salesforce | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-07-01 ¦ Bulk lead (3841), dialer, inventory & sales training completed since last run. | <=5 d | 01-Jul-26 | 1 | Yes | Yes |  |  |  | C | Completed login/project/report/portal/FB/bulk lead (3841 leads)/dialer/inventory/sales training; pending website. | 14-30 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4411978 | The Bangalore Real Estate Co. | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-23 -> 2026-06-30 ¦ Bulk lead/Magic Bricks/inventory + sales training completed vs task-list last run. | <=5 d | 30-Jun-26 | 2 | Yes |  |  | 66316 | 7 | C | Completed login/project/report/bulk lead/Magic Bricks/inventory; pending website integ, dialer; sales training on G-meet (no recording). | <14 d | Kickoff done — move into onboarding, start priority tasks. | OK (<=5d) | None logged | None logged | No - none logged
4313304 | Yula Globas | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-16 -> 2026-06-29 ¦ Portals/website/routing/Mcube completed vs pending last run (IRIS/usage still a watch). | <=5 d | 29-Jun-26 | 3 | Yes | Yes |  |  |  | C | Completed login/project/report/FB/WhatsApp/portals/website/routing/Mcube; on hold earlier pending CP leads/IRIS, low usage. | 30-60 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4334932 | New Keys Real Estate | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-29 ¦ Lead import now completed (uploaded) vs pending last run. | <=5 d | 29-Jun-26 | 3 | Yes | Yes | Yes |  | 2 | Broker | Completed login/project/lead uploaded/report; pending clock-in/out, website integration. | 30-60 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4375201 | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-07-02 ¦ Blocker changed: customer buying IVR directly & choosing vendor; sales training to follow. | <=5 d | 02-Jul-26 | 0 | Yes | Yes |  |  |  | Broker | Customer purchasing IVR directly from Mcube & exploring other vendors; will proceed with sales training once done. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4438366 | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note 2026-06-26 -> 2026-06-30 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  | 50 | C | Completed login/project/report; guided lead import; pending Meta (activate admin user), inventory file awaited. | <14 d | New deal; categorize the account and log first onboarding note. | OK (<=5d) | None logged | None logged | No - none logged
4147287 | Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-19 -> 2026-06-30 ¦ Bulk lead import completed; now awaiting inventory files. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | A | Lead import completed; awaiting inventory file for Velmore & remaining projects. | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (<=5d) | None logged | None logged | No - none logged
4348936 | GARDEN OF EDEN PROPERTY DEVELOPERS PVT LTD | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-07-02 ¦ Sales training completed; only webhook integration pending. | <=5 d | 02-Jul-26 | 0 | Yes |  |  |  |  | C | Completed login/project/report/routing/Meta/Mcube/WhatsApp/sales training; pending webhook integration. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4241966 | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-26 -> 2026-06-30 ¦ Active follow-ups; call scheduled to close remaining report items toward handover. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | Call scheduled for today 5 PM (AI calling progressing; earlier feedback loop with Vinay/Netram). | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (<=5d) | None logged | None logged | No - none logged
4233760 | Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-02 -> 2026-06-30 ¦ Call numbers configured & shared for customer testing; feedback implemented. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | C | Incoming/outgoing call mobile numbers configured & shared with customer to test; customer to check by tomorrow. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4402389 | Navkar Realty | Venkat Viswavardhan | Kickoff Done | Progressed | Stage Onboarding In Progress -> Kickoff Done ¦ Note 2026-06-29 -> 2026-07-02 ¦ Stage Onboarding In Progress -> Kickoff Done. | <=5 d | 02-Jul-26 | 0 | Yes |  |  | 495600 | 4 | C | AI bot shared for testing, awaiting their feedback. (Meta integration completed 26-Jun). | <14 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4053797 | PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-04-27 -> 2026-07-02 ¦ Sales training completed; DLT/WhatsApp templates + NDNC still pending on customer. | <=5 d | 02-Jul-26 | 0 | Yes |  |  | 502680 | 10 | B | Completed login/project/report/routing/bulk lead/Meta; sales training completed; DLT/WhatsApp templates & NDNC pending. | 60-90 d | High-value (Rs5L) Pending-on-Customer; chase customer + Mcube telephony. | OK (<=5d) | None logged | None logged | No - none logged
4197691 | Raghava Elite Park | Venkat Viswavardhan | Under Usage Tracking | Progressed | Stage Under Usage Tracking -> Under Usage Tracking ¦ Note 2026-06-19 -> 2026-06-30 ¦ In usage tracking; only AI-voice pricing pending; go-live targeted 30-Jun. | <=5 d | 30-Jun-26 | 2 | Yes | Yes | Yes |  |  | B | Sent email to customer with AI voice pricing; awaiting update. (Rest done; AI calling pending; post-sales/IRIS go-live 30-Jun). | 60-90 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to A) | OK (<=5d) | None logged | None logged | No - none logged
4446753 | SKYTOWN Group | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-07-02 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 02-Jul-26 | 0 | Yes |  |  | 500000 | 10 | A | Completed login/project/report/routing; Mcube outgoing set (incoming raised w/ Mcube); Meta integration in progress. | <14 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
4325921 | Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-19 -> 2026-06-29 ¦ Portals, Mcube & FB completed; handover planned next week. | <=5 d | 29-Jun-26 | 3 | Yes | Yes |  |  |  | C | Completed login/project/report/routing/bulk lead/portals/Mcube/FB; pending WhatsApp. (Handover planned next week). | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4370308 | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-26 -> 2026-07-02 ¦ Bulk-lead file now received (fixing errors) + Housing/MagicBricks integrations done. | <=5 d | 02-Jul-26 | 0 | Yes |  |  |  |  | C | Bulk upload file received but has errors; informed client, they will re-share today. | 14-30 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4402374 | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-30 ¦ Meta, inventory & website integration completed since last run. | <=5 d | 30-Jun-26 | 2 | Yes |  |  | 350000 | 15 | B | Meta integrated, inventory uploaded, website integ done; WhatsApp integ issue, customer to fix by 1-Jul. | <14 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4204921 | Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking | Progressed | Stage Under Usage Tracking -> Under Usage Tracking ¦ Note 2026-05-18 -> 2026-06-30 ¦ Now in usage tracking; cost sheet delivered; handover planned next week. | <=5 d | 30-Jun-26 | 2 | Yes | Yes |  |  |  | A | Cost sheet delivered, customer checking, will update today. (In usage tracking; handover next week). | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4358959 | YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-30 ¦ Admin training + workflow setup completed; handover targeted next week. | <=5 d | 30-Jun-26 | 2 | Yes |  |  |  |  | Broker | Admin training completed, workflow setup done. (Handover targeted next week). | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4337048 | i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-26 -> 2026-06-29 ¦ 99acres/CommonFloor done + inventory file received vs awaiting vendor/files last run. | <=5 d | 29-Jun-26 | 3 | Yes | Yes |  |  |  | A | Completed login/project/report/routing/Meta/99acres/common floor; pending bulk lead (await file), inventory (received, working). | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. | OK (<=5d) | None logged | None logged | No - none logged

## 5. Large-Stuck-Attention
Large deals, Stuck deals & Deals needing attention - for everyone
A) LARGE DEALS (value / licenses) - protect these
Deal | Owner | Stage | Billed (Rs) | Licenses | Cat | Status / note
Times Group | Sanket Nampalliwar | Pending on Customer | 944000 | 50 | A | Unit data uploaded to demo account, dashboards ready; client doing UAT, feedback by 23-Jun EOD.
PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | Pending on Customer | 502680 | 10 | B | Completed login/project/report/routing/bulk lead/Meta; sales training completed; DLT/WhatsApp templates & NDNC pending.
SKYTOWN Group | Venkat Viswavardhan | Onboarding In Progress | 500000 | 10 | A | Completed login/project/report/routing; Mcube outgoing set (incoming raised w/ Mcube); Meta integration in progress.
Navkar Realty | Venkat Viswavardhan | Kickoff Done | 495600 | 4 | C | AI bot shared for testing, awaiting their feedback. (Meta integration completed 26-Jun).
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 350000 | 15 | B | Meta integrated, inventory uploaded, website integ done; WhatsApp integ issue, customer to fix by 1-Jul.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress |  | 150 | A | PFA the updated Project Plan (Kunvarji Realtors.xlsx).
Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress |  | 50 | C | Completed login/project/report; guided lead import; pending Meta (activate admin user), inventory file awaited.
B) STUCK DEALS (30+ days idle, or notes say 'no movement / on hold / call rescheduled')
Deal | Owner | Stage | Last note | Idle | Status / note
Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress | 30-Jun-26 | <=5 d | No movement from client side.
Yula Globas | Sahil Jane | Onboarding In Progress | 29-Jun-26 | <=5 d | Completed login/project/report/FB/WhatsApp/portals/website/routing/Mcube; on hold earlier pending CP leads/IRIS, low usage.
Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | 30-Jun-26 | <=5 d | Account on hold till Monday as per client request.
House of Colours | Shweta Gouda | Onboarding In Progress | 25-Jun-26 | <=5 d | Account on Hold - client does not want to proceed due to Magicbricks listing tagging concern.
C) NEEDS ATTENTION (paid but 'Yet to sign up', or large + go-live breached)
Deal | Owner | Stage | Billed (Rs) | Signed up? | Go-live overdue | Status / note
VRUSHABADRI DEVELOPERS | Sahil Jane | Open | 241900 | Yet to sign up
Supreme Vision Infrabuild Private Limited (Augusta Realty) | Shweta Gouda | Open | 147500 | Yet to sign up
VASTU INFINITY AND VENTURES LLP | Sahil Jane | Open | 33000 | Yet to sign up
New Keys Real Estate | Shweta Gouda | Onboarding In Progress |  | Yet to sign up | Yes | Completed login/project/lead uploaded/report; pending clock-in/out, website integration.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress |  | - | Yes | PFA the updated Project Plan (Kunvarji Realtors.xlsx).
Raghava Elite Park | Venkat Viswavardhan | Under Usage Tracking |  | Yet to sign up | Yes | Sent email to customer with AI voice pricing; awaiting update. (Rest done; AI calling pending; post-sales/IRIS go-live 30-Jun).

## 6. Pending-on-Customer Check
'Pending on Customer' validation - is it really moving?
12 deals sit in this stage. Verdict from last 2-3 notes + activity.
Deal | Owner | Last note | Days since | Verdict | Clear next action
i5 Housing and Properties LLP | Venkat Viswavardhan | 29-Jun-26 | 3 | STUCK | Awaiting vendor for portal+IVR & client files since mid-Jun; weekly note is internal only. Escalate, set drop-dead date.
Ribitto Private Limited | Muntazar Mhate | 30-Jun-26 | 2 | STUCK | No genuine note movement in 3 runs; pending bulk lead + FB from customer. Escalate / chase lead file.
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | 30-Jun-26 | 2 | STUCK | Wrong project plan shared; Sanket to re-share & confirm. No real customer movement in 3 runs.
Kohinoor AI Calling | Venkat Viswavardhan | 30-Jun-26 | 2 | STUCK | BOT shared for testing; awaiting Mcube number from customer since ~May. Chase; set test date.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | 22-Jun-26 | 10 | STUCK | Last real note Feb-26; many integrations pending. Re-open kickoff or escalate.
Voora Developers | Raahul Ramanan R | 26-Jun-26 | 6 | STUCK | Handover scheduled in Feb never happened. Escalate; re-open.
Shree Honda | Sourabh Sahu | 22-Jun-26 | 10 | STUCK | Awaiting client details since Dec to start setup. Final call or move to HOLD.
Times Group | Sanket Nampalliwar | 22-Jun-26 | 10 | STUCK | Inventory UAT dragging since Nov. Escalate to close UAT and sign off.
PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | 02-Jul-26 | 0 | Customer-blocked | Pending DLT setup; awaiting customer. Re-confirm and set a date.
GGC AI Calling | Venkat Viswavardhan | 30-Jun-26 | 2 | Moving slowly | Approaching handover; awaiting client feedback. Get feedback then handover with Siddharth.
Dreamworks Realtors | Venkat Viswavardhan | 30-Jun-26 | 2 | Near done | Almost all tasks complete; only bulk lead import pending. Close out & handover.
Gram Strategic Advisors LLP | Muntazar Mhate | 30-Jun-26 | 2 | Near done | Most complete (Broker). Schedule final handover this week.

## 7. Customer Category
Customer Category - usage & priority check
A/B/C/Broker should drive onboarding priority & SLA. Today it is captured but not acted on.
Distribution & risk by category
Category | Deals | % of pipe | Idle 5+ d | No notes | Not signed up | Go-live overdue
A (top priority) | 11 | 16% | 3 | 0 | 0 | 5
B | 8 | 12% | 0 | 0 | 2 | 1
C | 37 | 55% | 3 | 3 | 3 | 12
Broker | 11 | 16% | 1 | 1 | 3 | 3
Uncategorized | 0 | 0% | 0 | 0 | 0 | 0
Total | 67
What this tells us
- A-grade = your most important accounts (11 deals). 3 have had NO activity in 5+ days and 0 have no notes at all - cadence on the A's has improved, keep it tight.
- Category is still not used to prioritise: A deals (Kunwarji 150 lic, Times, i5, Raghava) sit alongside C deals with the same attention. Tie an SLA to grade.
- Value is not tracked consistently: the biggest billed deal, Times Group (~Rs9.4L), is Category A, but Billed Amount is blank on 52 of 67 deals - populate it and re-grade against value + licences.
- 0 deals are uncategorized this run (good) - keep category mandatory at creation so nothing falls through prioritisation.
- 55% of the pipeline (37) is tagged C. Either genuinely low-value, or default tagging - worth a quick audit so C actually means C.
- Recommendation: tie an SLA to category - A = white-glove, named owner, weekly touch + exec visibility; B = fortnightly; C/Broker = templatised. Make category mandatory and value-aligned at deal creation.
A-GRADE WATCHLIST (protect these 15 - sorted by neglect)
Deal | Owner | Stage | Idle | Last note | Billed (Rs) | Lic | Status / note
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | 7-15 d | 22-Jun-26 |  | 150 | PFA the updated Project Plan (Kunvarji Realtors.xlsx).
SPR Construction Pvt Ltd | Sahil Jane | Onboarding In Progress | 5-7 d | 26-Jun-26 |  |  | OB Weekly Update (26-Jun): Sanket to talk to client about pending pointers.
Voora Developers | Raahul Ramanan R | Pending on Customer | 5-7 d | 26-Jun-26 |  |  | OB Weekly Update (26-Jun): update notes w/ timelines; check Chennai team visit; Sanket to call MD and align meeting.
Axon Developer | Sahil Jane | Onboarding In Progress | <=5 d | 29-Jun-26 |  |  | Completed account/login/project/hierarchy/routing/bulk lead/FB; pending workflow setup, Meta pixel.
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Pending on Customer | <=5 d | 30-Jun-26 |  |  | Updated timesheet; pending lead import (client doing), hierarchy approval, inventory.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | <=5 d | 30-Jun-26 |  |  | Lead import completed; awaiting inventory file for Velmore & remaining projects.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 01-Jul-26 |  |  | Requirement received and JIRA updated; awaiting update from team. (Flagged Re-OB, plan go-live).
SKYTOWN Group | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 02-Jul-26 | 500000 | 10 | Completed login/project/report/routing; Mcube outgoing set (incoming raised w/ Mcube); Meta integration in progress.
Times Group | Sanket Nampalliwar | Pending on Customer | <=5 d | 22-Jun-26 | 944000 | 50 | Unit data uploaded to demo account, dashboards ready; client doing UAT, feedback by 23-Jun EOD.
Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking | <=5 d | 30-Jun-26 |  |  | Cost sheet delivered, customer checking, will update today. (In usage tracking; handover next week).
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer | <=5 d | 29-Jun-26 |  |  | Completed login/project/report/routing/Meta/99acres/common floor; pending bulk lead (await file), inventory (received, working).

## 8. Re-grade (value+brand)
Category re-grade - value + licenses + brand/enterprise
Suggested grade = max of value, licence count, and brand/enterprise weight. Under-grading is the concern; higher-than-needed is low priority.
Summary: 8 under-graded (fix), 4 ungraded (set a grade), 0 clearly over-graded (low priority). ~8 A-deals score B on size alone (20-49 lic) - acceptable for enterprise/brand, not listed.
A) UNDER-GRADED - high value/brand but graded low (FIX THESE)
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Dhanraj Realbuild Llp | Venkat Viswavardhan | C | A | 60-90 d | blank | <10/blank |  | billed Rs5-7L
Raghava Elite Park | Venkat Viswavardhan | B | A | 60-90 d | blank | <10/blank | Strong | billed >=Rs7L; strong brand
GARDEN OF EDEN PROPERTY DEVELOPERS PVT LTD | Venkat Viswavardhan | C | B | 14-30 d | blank | <10/blank |  | billed Rs2-3L
Kohinoor AI Calling | Venkat Viswavardhan | C | B | 30-60 d | blank | <10/blank | Known | known brand
NPS DEVELOPERS | Sourabh Sahu | C | B | 60-90 d | blank | <10/blank |  | billed Rs3-5L
Shree Honda | Sourabh Sahu | C | B | >180 d | 2-3L | <10/blank |  | billed Rs2.11L
Sujay Global Homes | Venkat Viswavardhan | C | B | 30-60 d | blank | <10/blank |  | billed Rs3-5L
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | C | B | 14-30 d | blank | <10/blank |  | billed Rs2-3L
B) UNGRADED - no category set (assign one)
Includes Krishvi (already Active) and the 'dummy' test record.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Yashoda Infra Developer | Shweta Gouda | C | C | <14 d | blank | >=50 | Yashoda Infra Developer | uncategorized - new deal
Dreams true realty | Sahil Jane | C | C | 14-30 d | blank | <10/blank |  | no value/licenses captured
Pavani Infra | Shweta Gouda | C | C | 14-30 d | blank | <10/blank |  | no value/licenses captured
Shri Swami Samarth Assosiates Builder &Developers | Shweta Gouda | Broker | C | 14-30 d | blank | <10/blank |  | small ticket (blank/<1L, 10-19 lic)
C) Clearly over-graded - review (low priority)
B Square is actually live - close it rather than re-grade.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why

## 9. Comparison & Movement
Comparison & Movement vs previous run(s)
Run 5 (Thu 02-Jul-2026) vs 29-Jun & 25-Jun
Deal | Owner | Stage prev->now | Last note prev->now | Movement verdict | Stuck streak | Reason / action
Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-18 -> 2026-06-30 | Same-blocker | 4 | Website integration still the only pending item; unchanged - no movement.
Calicut Landmark Builders Pvt. Ltd | Shweta Gouda | Pending on Customer -> Pending on Customer | 2026-06-26 -> 2026-06-30 | Same-blocker | 4 | Only a timesheet/plan update; lead import, hierarchy approval & inventory still pending on customer.
Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-02 -> 2026-06-30 | Same-blocker | 4 | Still blocked on virtual-number pricing / AI-calling payment / Meta verification; only MIS report shared.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-05-19 -> 2026-07-01 | Same-blocker | 4 | Still awaiting GRE-form dev + Re-OB; only Jira updated - no customer-facing progress.
Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-05-25 -> 2026-06-30 | Same-blocker | 4 | Setup long done; now only awaiting client to confirm onsite-visit date - no task completed.
Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-01 -> 2026-06-30 | Same-blocker | 4 | Still awaiting customer to test outgoing AI calls; only a smartlist Jira added.
Ribitto Private Limited | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-30 | Same-blocker | 4 | Identical pending items (bulk lead, FB); no movement - 4 runs stuck.
SPR Construction Pvt Ltd | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-26 -> 2026-06-26 | No-touch | 4 | No new note/stage change since 2026-06-26.
Times Group | Sanket Nampalliwar | Pending on Customer -> Pending on Customer | 2025-11-10 -> 2026-06-22 | Same-blocker | 4 | Still in client UAT (feedback due 23-Jun, now overdue); no new note since - stalled.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-02-22 -> 2026-06-22 | Same-blocker | 4 | Escalated & on Pause - POC unresponsive; deteriorating.
Voora Developers | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-02-23 -> 2026-06-26 | Same-blocker | 4 | Stuck since Feb; still aligning MD meeting/handover - no genuine movement.
Pavani Infra | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-06-29 | No-touch | 3 | No new note/stage change since 2026-06-29.
RUDRA REALTY | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-06-29 | No-touch | 3 | No new note/stage change since 2026-06-29.
Sangram Group | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-07-01 | Same-blocker | 3 | Bulk lead still pending; now also awaiting client's WhatsApp number - no task completed.
Shri Swami Samarth Assosiates Builder &Developers | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-06-29 | No-touch | 3 | No new note/stage change since 2026-06-29.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 2 | No new note/stage change since 2026-06-22.
Phantom Advisory | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-30 | Same-blocker | 2 | Identical pending items (bulk lead, WhatsApp/Meta verification).
Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-30 | Same-blocker | 2 | Portals still only 'initiated'; nothing newly completed.
Shrimant Developers | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-30 | Same-blocker | 2 | Website still only 'initiated'; identical to last run.
Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-30 | Same-blocker | 2 | Note explicitly says 'no movement from client side'.
VIVANTA GROUP | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-06-29 | No-touch | 2 | No new note/stage change since 2026-06-29.
Artha Life Spaces | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-06-29 | No-touch | 1 | No new note/stage change since 2026-06-29.
Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | - -> 2026-06-30 | Same-blocker | 1 | On hold till Monday per client request - no active progress.
SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-26 -> 2026-06-30 | Same-blocker | 1 | Still awaiting details from customer; only a follow-up since last run.
TORANDWAR DEVELOPERS | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-28 -> 2026-06-28 | No-touch | 1 | No new note/stage change since 2026-06-28.
Apex Construction | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-30 | Progressed | 0 | Bulk lead, sales training & inventory completed since last run.
Axon Developer | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-29 | Progressed | 0 | Hierarchy, routing & bulk lead now completed vs pending last run.
Blueroof India | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-30 | Progressed | 0 | Login/project/report/routing/GPS/clock-in now completed vs task-list only.
Dreams true realty | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-21 -> 2026-06-30 | Progressed | 0 | Meta integration + sales training completed; now only admin training awaiting client.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-19 -> 2026-06-30 | Progressed | 0 | Bulk lead import completed; now awaiting inventory files.
GARDEN OF EDEN PROPERTY DEVELOPERS PVT LTD | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-07-02 | Progressed | 0 | Sales training completed; only webhook integration pending.
GGC AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-26 -> 2026-06-30 | Progressed | 0 | Active follow-ups; call scheduled to close remaining report items toward handover.
Growthx Estates | Muntazar Mhate | NEW this run | - -> 2026-07-01 | NEW | 0 | New in pipeline this run.
House of Colours | Shweta Gouda | NEW this run | - -> 2026-06-25 | NEW | 0 | New in pipeline this run.
Kalim Premier Realty LLP | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-30 | Progressed | 0 | Inventory completed + website integration email sent vs pending last run.
Leonaara PVt LTD | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-25 -> 2026-06-30 | Progressed | 0 | Campaign/source creation + first lead file uploaded since last run.
Miva Real Estate | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-30 | Progressed | 0 | Property-portal integration initiated + Meta/FB done; active work continuing.
Mundra Housing Projects LLP | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-30 | Progressed | 0 | Dialer + sales + admin training completed since last run.
Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-02 -> 2026-06-30 | Progressed | 0 | Call numbers configured & shared for customer testing; feedback implemented.
NPS DEVELOPERS | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-26 | Progressed | 0 | WhatsApp & Mcube setup completed vs in-progress last run.
Navkar Realty | Venkat Viswavardhan | Onboarding In Progress -> Kickoff Done | 2026-06-29 -> 2026-07-02 | Progressed | 0 | Stage Onboarding In Progress -> Kickoff Done.
New Keys Real Estate | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-29 | Progressed | 0 | Lead import now completed (uploaded) vs pending last run.
PRABHUKRUPA REALTIES PVT. LTD | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-04-27 -> 2026-07-02 | Progressed | 0 | Sales training completed; DLT/WhatsApp templates + NDNC still pending on customer.
PROPKART4U | Shweta Gouda | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
Properties Boutique | Sahil Jane | NEW this run | - -> 2026-07-01 | NEW | 0 | New in pipeline this run.
Raghava Elite Park | Venkat Viswavardhan | Under Usage Tracking -> Under Usage Tracking | 2026-06-19 -> 2026-06-30 | Progressed | 0 | In usage tracking; only AI-voice pricing pending; go-live targeted 30-Jun.
Rajparis Civil Construction | Muntazar Mhate | NEW this run | - -> 2026-07-01 | NEW | 0 | New in pipeline this run.
Real Estate Square | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-30 | Progressed | 0 | Admin training completed since last run; bulk lead still pending.
SKYTOWN Group | Venkat Viswavardhan | Open -> Onboarding In Progress | - -> 2026-07-02 | Progressed | 0 | Stage Open -> Onboarding In Progress.
SS Salesforce | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-07-01 | Progressed | 0 | Bulk lead (3841), dialer, inventory & sales training completed since last run.
Shree Automotive | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2025-12-08 -> 2026-06-22 | Progressed | 0 | DND & NDNC details finally received from client; Mcube setup next - real unblock.
Shree Honda | Sourabh Sahu | Pending on Customer -> Pending on Customer | 2025-12-08 -> 2026-06-22 | Progressed | 0 | DND & NDNC details finally received from client; Mcube setup next - real unblock.
Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Open -> Onboarding In Progress | 2026-06-22 -> 2026-06-30 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Strata Capital Holdings | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-07-02 | Progressed | 0 | Blocker changed: customer buying IVR directly & choosing vendor; sales training to follow.
Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-19 -> 2026-06-29 | Progressed | 0 | Portals, Mcube & FB completed; handover planned next week.
Sunrise Housing (GHP Group) | Muntazar Mhate | Open -> Onboarding In Progress | - -> 2026-06-30 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Supreme Vision Infrabuild Private Limited (Augusta Realty) | Shweta Gouda | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
The Bangalore Real Estate Co. | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-23 -> 2026-06-30 | Progressed | 0 | Bulk lead/Magic Bricks/inventory + sales training completed vs task-list last run.
VASTU INFINITY AND VENTURES LLP | Sahil Jane | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-26 -> 2026-07-02 | Progressed | 0 | Bulk-lead file now received (fixing errors) + Housing/MagicBricks integrations done.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-30 | Progressed | 0 | Meta, inventory & website integration completed since last run.
VRUSHABADRI DEVELOPERS | Sahil Jane | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking -> Under Usage Tracking | 2026-05-18 -> 2026-06-30 | Progressed | 0 | Now in usage tracking; cost sheet delivered; handover planned next week.
YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-30 | Progressed | 0 | Admin training + workflow setup completed; handover targeted next week.
Yashoda Infra Developer | Shweta Gouda | Open -> Onboarding In Progress | 2026-06-26 -> 2026-06-30 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Yula Globas | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-16 -> 2026-06-29 | Progressed | 0 | Portals/website/routing/Mcube completed vs pending last run (IRIS/usage still a watch).
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-26 -> 2026-06-29 | Progressed | 0 | 99acres/CommonFloor done + inventory file received vs awaiting vendor/files last run.