## 1. Stats
Sell.do Onboarding Pipeline - Statistics
Pipeline 27474 ¦ 58 open deals ¦ Snapshot 2026-07-07
Ageing = days since deal CREATED (created_at). Movement = days since last activity (separate metric).
By Owner
Category | Count
Muntazar Mhate | 15
Venkat Viswavardhan | 15
Sahil Jane | 10
Shweta Gouda | 9
Raahul Ramanan R | 5
Sanket Nampalliwar | 2
Sourabh Sahu | 2
Total | 58
By Pipeline Stage
Category | Count
Open | 1
Kickoff Done | 1
Onboarding In Progress | 44
Pending on Customer | 11
Under Usage Tracking | 0
Total | 57
Deal Ageing = days since CREATED (created_at)
Category | Count
<14 days | 15
14-30 days | 18
30-60 days | 10
60-90 days | 8
90-180 days | 3
180+ days | 4
Total | 58
Movement = days since LAST ACTIVITY
Category | Count
<=5 days (healthy) | 50
5-7 days | 2
7-15 days | 6
15-30 days | 0
30+ days | 0
Total | 58
Touch cadence = days since LAST NOTE (interim proxy until meetings are logged)
Category | Count
<=5 days (OK) | 49
6-10 days | 2
11-15 days | 7
16-30 days | 0
31+ days | 0
Never (no note) | 0
Total | 58
Meetings ON DEALS (not yet logged - format ready going forward)
Category | Count
Deals with a meeting logged on the deal | 0
Meeting scheduled/conducted within 5 days | 0
NO meeting logged (team to start logging) | 58
Risk & Data-Quality Flags
Category | Count
No activity 5+ days (your risk rule) | 8
No notes logged at all | 0
Target go-live date already breached | 11
Customer 'Yet to sign up' | 1
No future follow-up task | 29
Has an OVERDUE task | 19
Billed Amount field blank | 52
Estimated Value populated | 0
Meetings linked to these onboarding deals | 0

## 2. Exec Summary (CEO-CRO)
Onboarding Pipeline - Executive Summary
For CEO & CRO ¦ 2026-07-07
The headline (movement this run)
67 deals are open in onboarding. Comparing today vs the last run: 34 have GENUINELY PROGRESSED, but 25 have NOT moved (17 restate the same blocker, 8 had no activity at all) and 21 of those have now been stuck for 2+ consecutive runs (SUPER-RED - see Sheet 9). 8 deals are new this run. 21 deals (31%) are already past their committed go-live date.
Data hygiene is still the structural issue: Billed Amount is blank on 52 of 67 deals (78%), Estimated Value is empty on every deal, 39 of 67 have no next task, and 4 deals still have zero notes. Revenue-at-risk remains invisible in standard reports.
Where the money is exposed
Cash collected but customer still 'Yet to sign up': VRUSHABADRI Developers Rs2.42L, Supreme Vision (Augusta Realty) Rs1.48L, VASTU Infinity Rs33k - all fully received but not activated. Push these to sign-up now.
Largest accounts by value: Times Group Rs9.44L (Pending-on-Customer - client UAT feedback overdue since 23-Jun), PRABHUKRUPA Rs5.03L, SKYTOWN Rs5.0L, Navkar Rs4.96L. Largest by licences: Kunwarji Realtors - 150 licences, Category A, go-live breached, only a single 'project plan' note and no next task.
What we are asking leadership to back
1. A weekly onboarding hygiene standard: every open deal must have a LOGGED MEETING (scheduled or conducted) at least every 5 days, a dated note, and a next task; stage moved at each milestone. (Meetings are still not logged on deals at all.)
2. Make Billed Amount mandatory at deal creation so revenue-at-risk is visible (blank on 78% today).
3. A weekly SUPER-RED review: 21 deals have not genuinely moved for 2+ runs - most are stuck 'pending on customer'. Set drop-dead dates or move to HOLD.
4. A 'collections + activation' sweep on the paid-but-dormant accounts above (CRO + Onboarding).

## 3. Owner Scorecard
Owner Scorecard - gaps for the Onboarding Head
Counts per owner across the key risk flags. Use for owner 1:1s.
Owner | Open deals | A-grade | Idle 5+ d | No notes | Go-live overdue | Not signed up | No next task | Overdue task | Key gap to address
Muntazar Mhate | 15 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 15 deal(s). pending-on-customer: Ribitto Private Limited, Gram Strategic Advisors LLP.
Venkat Viswavardhan | 15 | 5 | 1 | 0 | 5 | 0 | 8 | 6 | 15 deal(s). pending-on-customer: GGC AI Calling, Kohinoor AI Calling, Dreamworks Realtors, Dhanraj Realbuild Llp.
Sahil Jane | 10 | 1 | 1 | 0 | 1 | 0 | 1 | 3 | 10 deal(s).
Shweta Gouda | 9 | 0 | 0 | 0 | 0 | 1 | 5 | 4 | 9 deal(s).
Raahul Ramanan R | 5 | 3 | 2 | 0 | 3 | 0 | 3 | 2 | 5 deal(s). pending-on-customer: Calicut Landmark Builders Pvt. Ltd, Upcurve consumer Technologies Pvt Ltd, Voora Developers.
Sanket Nampalliwar | 2 | 2 | 2 | 0 | 2 | 0 | 0 | 2 | 2 deal(s). pending-on-customer: Times Group.
Sourabh Sahu | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 2 deal(s). pending-on-customer: Shree Honda.
TOTAL | 58 | 11 | 8 | 0 | 11 | 1 | 29 | 19

## 4. Deal-Level Tracker
Deal-Level Tracker - for the Onboarding Head to action
Cols E-F = movement vs the LAST run: Progressed / NEW / STUCK (same blocker or no activity). Stuck deals are grouped at the top. SUPER-RED = no genuine movement for 2+ consecutive runs.
Deal ID | Deal Name | Owner | Stage | Moved? (vs last run) | Movement detail (prev -> now) | Last activity | Last note date | Days since note | Has notes | Go-live overdue | Not signed up | Billed (Rs) | Licenses | Cat | Last note / status | Age (created) | Key Next Step (recommended) | Touch cadence (interim, vs 5d) | Last meeting | Next meeting | Mtg <=5d?
3623014 | Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer | SUPER-RED (5 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x5] | 7-15 d | 22-Jun-26 | 15 | Yes |  |  |  |  | Broker | Escalated account, Onboarding will go on Pause as POC is unresponsive. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Stale | None logged | None logged | No - none logged
3575524 | Voora Developers | Raahul Ramanan R | Pending on Customer | SUPER-RED (5 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-26 -> 2026-06-26 ¦ No new note/stage change since 2026-06-26. [stuck x5] | 7-15 d | 26-Jun-26 | 11 | Yes | Yes |  |  |  | A | OB Weekly Update (26 Jun): Update Kylas notes with timelines. Check with Manoj if Chennai Team can visit. Sanket to call the MD and align the meeting. | 90-180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Stale | None logged | None logged | No - none logged
3302998 | Times Group | Sanket Nampalliwar | Pending on Customer | SUPER-RED (5 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x5] | 7-15 d | 22-Jun-26 | 15 | Yes | Yes |  | 944000 | 50 | A | Unit data uploaded to demo account, all dashboards ready. Client performing UAT and will share feedback by tomorrow (23 Jun) EOD. | >180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Stale | None logged | None logged | No - none logged
4262054 | Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress | SUPER-RED (5 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Website integration still the only pending item; unchanged - 5 runs stuck. [stuck x5] | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | B | Completed: User Login, Project, Default Report Config, Routing, Bulk Lead Import, Facebook, Offline Dialer, GPS, Clock-in/out, Sales/Presales Training. Pending: Website Integration. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4299438 | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | SUPER-RED (5 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-30 -> 2026-07-06 ¦ Identical (bulk lead + FB pending); no movement - 5 runs stuck. [stuck x5] | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report Config, Routing, Product Briefing, WATI Integration, Offline Dialer, GPS, Clock-in/out, Admin Training. Pending: Bulk Lead Import (Excel), Facebook Integration. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4255693 | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | SUPER-RED (5 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-30 -> 2026-07-03 ¦ Meta/WhatsApp call rescheduled at client request; lead import/hierarchy/inventory still pending on customer. [stuck x5] | <=5 d | 03-Jul-26 | 4 | Yes | Yes |  |  |  | A | Updates on Onboarding shared. Meta Integration & Native WhatsApp call scheduled today 2:15 PM but rescheduled to next week per client request. Lead import/hierarchy/inventory still pending on customer. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4255681 | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | SUPER-RED (5 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-26 -> 2026-07-06 ¦ Client instructed HOLD until calling integration done - no implementation progress; 5 runs stuck. [stuck x5] | <=5 d | 06-Jul-26 | 1 | Yes | Yes |  |  |  | A | The client has specifically instructed us not to proceed with the implementation until the calling integration is completed. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4144089 | Dhanraj Realbuild Llp | Venkat Viswavardhan | Pending on Customer | SUPER-RED (5 runs stuck) | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-06-30 -> 2026-07-03 ¦ Escalating: concall arranged over pricing/false-promise dispute (GRE form/post-sales); moved to Pending-on-Customer, no progress. [stuck x5] | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | C | Have to arrange a concall with Ankur and Customer on Monday, as customer feels false promise was shared regarding GRE form and post sales. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to A) | OK (<=5d) | None logged | None logged | No - none logged
3968505 | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (5 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-01 -> 2026-07-03 ¦ Same: requirement/JIRA awaiting dev deploy (now ETA 8 Jul); no customer-facing progress - 5 runs stuck. [stuck x5] | <=5 d | 03-Jul-26 | 4 | Yes | Yes |  |  |  | A | Requirement received and JIRA updated. Awaiting update from team. ETA for JIRA deploy by 8th July. Will connect with customer after testing. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4233715 | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | SUPER-RED (5 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-30 -> 2026-07-03 ¦ Still blocked on bulk outgoing-call testing (ESTATE-21040, ETA 11.2); no resolution - 5 runs stuck. [stuck x5] | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | C | [ESTATE-21040] bulk call list Jira - timeline 11.2. Customer facing challenge in bulk outgoing calls (no cross-check for duplicate leads). Feedback shared with tech. | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4230613 | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x3] | 7-15 d | 22-Jun-26 | 15 | Yes | Yes |  |  | 150 | A | PFA the updated Project Plan; Project Plan Kunvarji Realtors.xlsx | 60-90 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Stale | None logged | None logged | No - none logged
4383150 | Phantom Advisory | Muntazar Mhate | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ No task completed; original bulk-lead/WhatsApp blockers unresolved, now awaiting internal Tejas on a sourcing ask. [stuck x3] | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | B | Awaiting Tejas update to take this ahead. Client requesting Sourcing Set-up within the current contract. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4370376 | Shrimant Developers | Muntazar Mhate | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Website integration still only 'initiated' (the blocker); only an offline-dialer doc added. [stuck x3] | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report Config, Routing, GPS Tracking, Clock-in/out, Offline Dialer. Pending: Website Integration - initiated from our side. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4437383 | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-06-30 ¦ No new note/stage change since 2026-06-30. [stuck x2] | 5-7 d | 30-Jun-26 | 7 | Yes |  |  | 100000 |  | C | The account is on hold till Monday as per client request. | <14 d | New deal - log first onboarding note / confirm kickoff. | Watch | None logged | None logged | No - none logged
4415503 | TORANDWAR DEVELOPERS | Shweta Gouda | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-28 -> 2026-07-03 ¦ Note restates same completions + lead file still awaited from client; nothing newly done. [stuck x2] | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  | 7 | Broker | Completed: User Login, Project, Default Report Config, Lead Import (guided). Inventory management - Quick Add Unit as discussed. | <14 d | Kick-off call scheduled 24-Jun; run it and start setup. | OK (<=5d) | None logged | None logged | No - none logged
3304062 | Shree Automotive | Sourabh Sahu | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | 7-15 d | 22-Jun-26 | 15 | Yes |  |  | 104784 | 4 | C | DND & NDNC details received from the client. Will setup the Mcube by tomorrow. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Stale | None logged | None logged | No - none logged
3304063 | Shree Honda | Sourabh Sahu | Pending on Customer | STUCK - no activity | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-22 ¦ No new note/stage change since 2026-06-22. [stuck x1] | 7-15 d | 22-Jun-26 | 15 | Yes |  |  | 210983 | 5 | C | DND & NDNC details received from the client. Will setup the Mcube by tomorrow. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Stale | None logged | None logged | No - none logged
4204921 | Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking | STUCK - no activity | Stage Under Usage Tracking -> Under Usage Tracking ¦ Note 2026-06-30 -> 2026-06-30 ¦ No new note/stage change since 2026-06-30. [stuck x1] | 5-7 d | 30-Jun-26 | 7 | Yes | Yes |  |  |  | A | Cost sheet delivered, customer checking and will update by today. (In usage tracking; handover next week.) | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Watch | None logged | None logged | No - none logged
4177642 | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-26 -> 2026-06-26 ¦ No new note/stage change since 2026-06-26. [stuck x1] | <=5 d | 26-Jun-26 | 11 | Yes |  |  |  |  | C | OB Weekly Update (26 Jun): WhatsApp Setup Completed, Mcube Setup Completed. Sourabh to check with client for Post-sales Re-OB. | 60-90 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | Stale | None logged | None logged | No - none logged
4357637 | Apex Construction | Sahil Jane | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Identical completed list; dialer still the only pending item - unchanged. [stuck x1] | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: Account/User Login, Project, Default Report Config, Call Routing, Facebook, Bulk Lead Import, Sales/Presales Training, Inventory. Pending: Dialer (in Sales training). | 14-30 d | Customer keeps rescheduling - lock one firm slot or pause the account. | OK (<=5d) | None logged | None logged | No - none logged
4382895 | SS Salesforce | Sahil Jane | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-01 -> 2026-07-06 ¦ Identical completed list; website integration still the only pending item - unchanged. [stuck x1] | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report Config, Property portal (99acres), Facebook, Bulk Lead Import (3841 leads uploaded), Dialer, Inventory, Sales/Presales Training. Pending: Website Integration. | 14-30 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4313304 | Yula Globas | Sahil Jane | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-07-05 ¦ Identical completed list; IRIS/usage still the watch item - unchanged. [stuck x1] | <=5 d | 05-Jul-26 | 2 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report Config, Facebook, Native WhatsApp, Property Portal (99acres/MagicBricks/Housing), Website, Call Routing, MCube Integration. IRIS/usage still watched. | 30-60 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4375201 | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-02 -> 2026-07-03 ¦ Still waiting on client's direct Mcube purchase before integrations - unchanged. [stuck x1] | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | Broker | Client opted for Mcube directly (not billable to sell.do); that setup in progress, once done client will proceed with Integrations. Base tasks completed. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4241966 | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | STUCK - same blocker | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-30 -> 2026-07-03 ¦ Customer no-showed the call; reschedule next week - no progress. [stuck x1] | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | C | Customer didn't join the call. Call to be scheduled next week with customer on the same. | 30-60 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (<=5d) | None logged | None logged | No - none logged
4446753 | SKYTOWN Group | Venkat Viswavardhan | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-02 -> 2026-07-02 ¦ No new note/stage change since 2026-07-02. [stuck x1] | <=5 d | 02-Jul-26 | 5 | Yes | Yes |  | 500000 | 10 | A | Completed: User Login, Project, Default Report Config, Routing. Mcube: outgoing set, incoming raised with Mcube, awaiting customer confirmation. Meta Integration in progress. | <14 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
4325921 | Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-07-06 ¦ Identical completed list; WhatsApp still pending, handover still 'planned' - unchanged. [stuck x1] | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report Config, Routing, Bulk Lead: Done, Property Portal (99acres/magicbricks/housing): Done, Mcube: Done, Facebook: Done. WhatsApp Integration pending. Handover planned. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4402374 | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-03 ¦ Meta verification still in progress & WhatsApp still pending on customer - no net completion. [stuck x1] | <=5 d | 03-Jul-26 | 4 | Yes |  |  | 350000 | 15 | B | Meta account verification still in progress, expected next week. Next week: complete Whatsapp integration, schedule sales and Admin training. | 14-30 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4472721 | Salahrealty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  | 2 | C | Priority Onboarding Tasks: User Login, Project, Default Report Config, Default Routing, Offline Dialer, Inventory Set-up (Tentative - sample shared), Sales/Presales Training, Admin Training. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4461524 | DhanVed Consultants | Shweta Gouda | Open | NEW this run | New in pipeline this run. | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | Broker | Kick Off Call scheduled on 6th of July at 3:00pm. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4412002 | Blueroof India | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Offline Dialer now completed since last run (bulk lead/Meta/website still pending). | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  | 2 | C | Completed: User Login, Project, Default Report Config, Routing, GPS Tracking, Clock-in/out, Offline Dialer. Pending items remain. | 14-30 d | Priority tasks shared — progress integrations. | OK (<=5d) | None logged | None logged | No - none logged
4079157 | Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-30 -> 2026-07-06 ¦ Onsite visit now scheduled for tomorrow to complete pending trainings - the awaited confirmation arrived. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | B | As discussed with client, the onsite visit is scheduled for tomorrow to complete the pending trainings. | 60-90 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4457232 | Growthx Estates | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-01 -> 2026-07-06 ¦ Login/project/report/routing/GPS/clock-in now completed vs task-list only last run. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  | 10 | Broker | Completed: User Login, Project, Default Report Config, Routing, GPS Tracking, Clock-in/out. Pending: Bulk Lead Import (Excel) - sample file shared for reference. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4449587 | Rajparis Civil Construction | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Kickoff Done -> Onboarding In Progress ¦ Note 2026-07-01 -> 2026-07-06 ¦ Stage Kickoff Done -> Onboarding In Progress. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  | 15 | B | Completed: User Login, Project, Default Report Config, Routing, Bulk Lead Import (Excel). Pending: Property Portal Integration (99Acres, India Residential) - initiated from our side; awaiting POC email. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4364225 | Real Estate Square | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Offline Dialer + Sales Training completed since last run; bulk lead still pending. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | Broker | Completed: User Login, Project, Default Report Config, Routing, Property Portal (99 Acres), Facebook, Admin Training, Offline Dialer, Sales Training. Pending: Bulk Lead Import. | 14-30 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4386888 | Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Property portals (99acres/Magicbricks) + website completed vs 'initiated' last run; Meta verification applied. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report Config, Routing, Property Portal (99Acres, Magicbricks), Website. Client applied for Meta Business verification, expected today. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4345401 | Sangram Group | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-01 -> 2026-07-06 ¦ IVR (MCube) + Facebook now completed vs waiting-on-client last run; only bulk lead pending. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report Config, Routing, IVR (MCube) Integration - Sangram Group, Facebook. Pending: Bulk Lead Import (Excel). | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4336926 | Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Base setup completed vs kickoff/task-list-only phase last run. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report Config, Routing. Pending: Bulk Lead Import (Excel) sample shared; Website Integration - awaiting developer email. | 30-60 d | Chase kickoff slot; escalate to customer exec if no response in 5 days. | OK (<=5d) | None logged | None logged | No - none logged
4370391 | Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Routing + sample lead/inventory imports now completed vs 'no movement from client' last run. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: User Login, Project, Default Report Config, Routing, Sample Lead & Inventory Import. Pending: Bulk Lead Import, Property Portals (99Acres/Magicbricks/Housing), Facebook. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4430582 | Sunrise Housing (GHP Group) | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Base setup (login/project/report/routing) completed vs task-list only last run. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  | 11 | B | Completed: User Login, Project, Default Report Config, Default Routing. Pending: Bulk Lead Import (Excel) sample shared, Facebook (Meta) Integration, Native WhatsApp, Website Integration. | <14 d | New deal — kickoff + sign-up; no notes yet, log first status. | OK (<=5d) | None logged | None logged | No - none logged
4389674 | Axon Developer | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-07-05 ¦ Sales/Presales Training completed since last run. | <=5 d | 05-Jul-26 | 2 | Yes | Yes |  |  |  | A | Completed: Account/User Login, Project, Hierarchy, Routing, Bulk Lead Import, Facebook, Sales/Presales Training. Pending: Call Routing, Workflow Setup, Capi Integration. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4389699 | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Bulk Lead Import now completed vs pending last run. | <=5 d | 06-Jul-26 | 1 | Yes |  |  |  |  | C | Completed: User Login, Account Setup, Project, Default Report Config, Campaign/Source, Call Routing, Facebook, Bulk Lead Import. Pending: Website Integration, WhatsApp Interakt, Mcube IVR. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4458749 | Properties Boutique | Sahil Jane | Onboarding In Progress | Progressed | Stage Kickoff Done -> Onboarding In Progress ¦ Note 2026-07-01 -> 2026-07-05 ¦ Stage Kickoff Done -> Onboarding In Progress. | <=5 d | 05-Jul-26 | 2 | Yes |  |  | 61360 | 7 | C | Completed: Account/User Login, Project, Default Report Config. Pending: Meta Integration (call scheduled Monday), Inventory, Dialer, Sales/Presales & Admin Training; Property Portal Housing/MagicBricks. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4411978 | The Bangalore Real Estate Co. | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-06 ¦ Sales/Presales & Mobile Training + Sell.do Dialer completed since last run. | <=5 d | 06-Jul-26 | 1 | Yes |  |  | 66316 | 7 | C | Completed: User Login, Project, Default Report Config, Bulk Lead Import, Property Portal Magic Bricks, Inventory Manual upload, Sales/Presales & Mobile Training, Sell.do Dialer. Website integration pending. | 14-30 d | Kickoff done — move into onboarding, start priority tasks. | OK (<=5d) | None logged | None logged | No - none logged
4458766 | VASTU INFINITY AND VENTURES LLP | Sahil Jane | Kickoff Done | Progressed | Stage Open -> Kickoff Done ¦ Note no note -> 2026-07-06 ¦ Stage Open -> Kickoff Done. | <=5 d | 06-Jul-26 | 1 | Yes |  |  | 33000 | 5 | C | Priority Onboarding Tasks: User Login, Project Creation, Default Report Config, Call Routing, Bulk Lead Import, Meta Integration, Sales/Presales & Admin Training; Inventory, Website integration, Property Portal Housing. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4458771 | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-07-05 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 05-Jul-26 | 2 | Yes |  |  | 241900 | 8 | C | Priority Onboarding Tasks: User Login Creation, Project Creation, Default Report Config, Call Routing, Property Portal (99acres, Housing, MagicBricks), Facebook, Native WhatsApp, Website Integration, CP Form, Dialer, Sales/Presales & Admin Training. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
3417644 | House of Colours | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-25 -> 2026-07-03 ¦ Reactivated from HOLD: user activation, fresh lead import, revised sales training, admin training, dashboards all completed. | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | C | Completed: User Activation, Lead Import (fresh leads), Default Report Config, Pipeline stages, Revised Sales Training, Custom Sales Dashboard, Quick Add Unit, Routing, Admin Training. Pending: Magic bricks. | >180 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4449855 | PROPKART4U | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> 2026-07-03 ¦ First real progress logged: login/project/report done, lead import guided, Meta lead captured. | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | Broker | Completed: User Login, Project, Default Report Config. Lead import - guided; awaiting lead file. Meta Integration - lead captured. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4357586 | Pavani Infra | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-07-03 ¦ Leads now actually uploaded (partial, date-format fixes) vs guided-only last run. | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | C | Completed: User Login, Project, Lead Import (uploaded except Meta leads - date format/lead stages incorrect), Kick Off Call, Meta Integration. Meta & website discussion continuing. | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4453288 | Supreme Vision Infrabuild Private Limited (Augusta Realty) | Shweta Gouda | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-07-03 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 03-Jul-26 | 4 | Yes |  | Yes | 147500 | 4 | C | Priority Onboarding Tasks: User Login, Project, Default Report Config, Lead Import, Meta Integration, Inventory (Post sales team), Website Integration, Admin & Sales training. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4383383 | VIVANTA GROUP | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-07-03 ¦ Meta campaign + website integration completed; blocker moved to Mcube NDNC/URLs. | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | C | Client completed Meta campaign setup, website integration & changes per Mcube guidelines. Awaiting NDNC letters and website URLs for Mcube setup to proceed to Sales training. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4438366 | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-03 ¦ Lead import completed + 99acres portal lead captured (#7) vs pending last run. | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  | 50 | C | Completed: User Login, Project, Default Report Config, Lead Import, Property Portal 99acres (lead #7). Pending: Meta Integration - awaiting digital marketing member availability. | <14 d | New deal; categorize the account and log first onboarding note. | OK (<=5d) | None logged | None logged | No - none logged
4147287 | Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-30 -> 2026-07-03 ¦ User hierarchy setup completed; CP-data upload guided (Mon), WhatsApp workflow expected 6-7 Jul. | <=5 d | 03-Jul-26 | 4 | Yes | Yes |  |  |  | A | Connected with customer on user hierarchy setup - completed. Explained CP data upload, Rupali to upload by Monday. Expect WhatsApp workflow by 6-7 July. | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (<=5d) | None logged | None logged | No - none logged
4233760 | Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-03 ¦ Call testing completed; feedback moved to internal tech (Sharayu) vs awaiting customer test last run. | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | C | Call testing done, feedback shared with Sharayu, awaiting feedback from her. Will follow up on Monday. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4402389 | Navkar Realty | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Kickoff Done -> Onboarding In Progress ¦ Note 2026-07-02 -> 2026-07-03 ¦ Stage Kickoff Done -> Onboarding In Progress. | <=5 d | 03-Jul-26 | 4 | Yes |  |  | 495600 | 4 | C | Whatsapp Integration completed. Awaiting details from customer to share the whatsapp template dump and feedback on AI calling. | 14-30 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4435090 | SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-03 ¦ Customer shared project import file (to upload Mon) - the awaited detail arrived. | <=5 d | 03-Jul-26 | 4 | Yes |  |  | 200000 | 10 | Broker | Project import file shared by customer, will be uploaded by Monday EOD. | <14 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
4370308 | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-02 -> 2026-07-03 ¦ Moved past bulk-lead error to next-week plan (connect meta/whatsapp, schedule training). | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | C | Action for next week: Connect meta and whatsapp account. Schedule sales and Admin Training. | 14-30 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4358959 | YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-30 -> 2026-07-03 ¦ Customer verifying full setup, confirmation by Monday then handover to support - nearing handover. | <=5 d | 03-Jul-26 | 4 | Yes |  |  |  |  | Broker | Customer cross checking all setup and will give confirmation by Monday, then will handover this to support. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4337048 | i5 Housing and Properties LLP | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Pending on Customer -> Onboarding In Progress ¦ Note 2026-06-29 -> 2026-07-03 ¦ Stage Pending on Customer -> Onboarding In Progress. | <=5 d | 03-Jul-26 | 4 | Yes | Yes |  |  |  | A | Admin training completed. | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. | OK (<=5d) | None logged | None logged | No - none logged

## 5. Large-Stuck-Attention
Large deals, Stuck deals & Deals needing attention - for everyone
A) LARGE DEALS (value / licenses) - protect these
Deal | Owner | Stage | Billed (Rs) | Licenses | Cat | Status / note
Times Group | Sanket Nampalliwar | Pending on Customer | 944000 | 50 | A | Unit data uploaded to demo account, all dashboards ready. Client performing UAT and will share feedback by tomorrow (23 Jun) EOD.
SKYTOWN Group | Venkat Viswavardhan | Onboarding In Progress | 500000 | 10 | A | Completed: User Login, Project, Default Report Config, Routing. Mcube: outgoing set, incoming raised with Mcube, awaiting customer confirmation. Meta Integration in progress.
Navkar Realty | Venkat Viswavardhan | Onboarding In Progress | 495600 | 4 | C | Whatsapp Integration completed. Awaiting details from customer to share the whatsapp template dump and feedback on AI calling.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 350000 | 15 | B | Meta account verification still in progress, expected next week. Next week: complete Whatsapp integration, schedule sales and Admin training.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress |  | 150 | A | PFA the updated Project Plan; Project Plan Kunvarji Realtors.xlsx
Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress |  | 50 | C | Completed: User Login, Project, Default Report Config, Lead Import, Property Portal 99acres (lead #7). Pending: Meta Integration - awaiting digital marketing member availability.
B) STUCK DEALS (30+ days idle, or notes say 'no movement / on hold / call rescheduled')
Deal | Owner | Stage | Last note | Idle | Status / note
Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | 30-Jun-26 | 5-7 d | The account is on hold till Monday as per client request.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | 03-Jul-26 | <=5 d | Updates on Onboarding shared. Meta Integration & Native WhatsApp call scheduled today 2:15 PM but rescheduled to next week per client request. Lead import/hierarchy/inventory still pending on customer.
C) NEEDS ATTENTION (paid but 'Yet to sign up', or large + go-live breached)
Deal | Owner | Stage | Billed (Rs) | Signed up? | Go-live overdue | Status / note
Times Group | Sanket Nampalliwar | Pending on Customer | 944000 | - | Yes | Unit data uploaded to demo account, all dashboards ready. Client performing UAT and will share feedback by tomorrow (23 Jun) EOD.
SKYTOWN Group | Venkat Viswavardhan | Onboarding In Progress | 500000 | - | Yes | Completed: User Login, Project, Default Report Config, Routing. Mcube: outgoing set, incoming raised with Mcube, awaiting customer confirmation. Meta Integration in progress.
Supreme Vision Infrabuild Private Limited (Augusta Realty) | Shweta Gouda | Onboarding In Progress | 147500 | Yet to sign up |  | Priority Onboarding Tasks: User Login, Project, Default Report Config, Lead Import, Meta Integration, Inventory (Post sales team), Website Integration, Admin & Sales training.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress |  | - | Yes | PFA the updated Project Plan; Project Plan Kunvarji Realtors.xlsx

## 6. Pending-on-Customer Check
'Pending on Customer' validation - is it really moving?
11 deals sit in this stage. Verdict from last 2-3 notes + activity.
Deal | Owner | Last note | Days since | Verdict | Clear next action
Ribitto Private Limited | Muntazar Mhate | 06-Jul-26 | 1 | STUCK | No genuine note movement in 3 runs; pending bulk lead + FB from customer. Escalate / chase lead file.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | 03-Jul-26 | 4 | STUCK | Wrong project plan shared; Sanket to re-share & confirm. No real customer movement in 3 runs.
Kohinoor AI Calling | Venkat Viswavardhan | 03-Jul-26 | 4 | STUCK | BOT shared for testing; awaiting Mcube number from customer since ~May. Chase; set test date.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | 22-Jun-26 | 15 | STUCK | Last real note Feb-26; many integrations pending. Re-open kickoff or escalate.
Voora Developers | Raahul Ramanan R | 26-Jun-26 | 11 | STUCK | Handover scheduled in Feb never happened. Escalate; re-open.
Shree Honda | Sourabh Sahu | 22-Jun-26 | 15 | STUCK | Awaiting client details since Dec to start setup. Final call or move to HOLD.
Times Group | Sanket Nampalliwar | 22-Jun-26 | 15 | STUCK | Inventory UAT dragging since Nov. Escalate to close UAT and sign off.
Dhanraj Realbuild Llp | Venkat Viswavardhan | 03-Jul-26 | 4 | Customer-blocked | Concall with Ankur + customer Mon on virtual-number pricing / GRE-form expectations; MIS shared. AI calling unpaid, Meta verification pending.
GGC AI Calling | Venkat Viswavardhan | 03-Jul-26 | 4 | Moving slowly | Approaching handover; awaiting client feedback. Get feedback then handover with Siddharth.
Dreamworks Realtors | Venkat Viswavardhan | 03-Jul-26 | 4 | Near done | Almost all tasks complete; only bulk lead import pending. Close out & handover.
Gram Strategic Advisors LLP | Muntazar Mhate | 06-Jul-26 | 1 | Near done | Most complete (Broker). Schedule final handover this week.

## 7. Customer Category
Customer Category - usage & priority check
A/B/C/Broker should drive onboarding priority & SLA. Today it is captured but not acted on.
Distribution & risk by category
Category | Deals | % of pipe | Idle 5+ d | No notes | Not signed up | Go-live overdue
A (top priority) | 11 | 19% | 4 | 0 | 0 | 11
B | 6 | 10% | 0 | 0 | 0 | 0
C | 32 | 55% | 3 | 0 | 1 | 0
Broker | 9 | 16% | 1 | 0 | 0 | 0
Uncategorized | 0 | 0% | 0 | 0 | 0 | 0
Total | 58
What this tells us
- A-grade = your most important accounts (11 deals). 4 have had NO activity in 5+ days and 0 have no notes at all - cadence on the A's has improved, keep it tight.
- Category is still not used to prioritise: A deals (Kunwarji 150 lic, Times, i5, Raghava) sit alongside C deals with the same attention. Tie an SLA to grade.
- Value is not tracked consistently: the biggest billed deal, Times Group (~Rs9.4L), is Category A, but Billed Amount is blank on 52 of 67 deals - populate it and re-grade against value + licences.
- 0 deals are uncategorized this run (good) - keep category mandatory at creation so nothing falls through prioritisation.
- 55% of the pipeline (37) is tagged C. Either genuinely low-value, or default tagging - worth a quick audit so C actually means C.
- Recommendation: tie an SLA to category - A = white-glove, named owner, weekly touch + exec visibility; B = fortnightly; C/Broker = templatised. Make category mandatory and value-aligned at deal creation.
A-GRADE WATCHLIST (protect these 15 - sorted by neglect)
Deal | Owner | Stage | Idle | Last note | Billed (Rs) | Lic | Status / note
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | 7-15 d | 22-Jun-26 |  | 150 | PFA the updated Project Plan; Project Plan Kunvarji Realtors.xlsx
Times Group | Sanket Nampalliwar | Pending on Customer | 7-15 d | 22-Jun-26 | 944000 | 50 | Unit data uploaded to demo account, all dashboards ready. Client performing UAT and will share feedback by tomorrow (23 Jun) EOD.
Voora Developers | Raahul Ramanan R | Pending on Customer | 7-15 d | 26-Jun-26 |  |  | OB Weekly Update (26 Jun): Update Kylas notes with timelines. Check with Manoj if Chennai Team can visit. Sanket to call the MD and align the meeting.
Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking | 5-7 d | 30-Jun-26 |  |  | Cost sheet delivered, customer checking and will update by today. (In usage tracking; handover next week.)
Axon Developer | Sahil Jane | Onboarding In Progress | <=5 d | 05-Jul-26 |  |  | Completed: Account/User Login, Project, Hierarchy, Routing, Bulk Lead Import, Facebook, Sales/Presales Training. Pending: Call Routing, Workflow Setup, Capi Integration.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | <=5 d | 03-Jul-26 |  |  | Updates on Onboarding shared. Meta Integration & Native WhatsApp call scheduled today 2:15 PM but rescheduled to next week per client request. Lead import/hierarchy/inventory still pending on customer.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | <=5 d | 03-Jul-26 |  |  | Connected with customer on user hierarchy setup - completed. Explained CP data upload, Rupali to upload by Monday. Expect WhatsApp workflow by 6-7 July.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 03-Jul-26 |  |  | Requirement received and JIRA updated. Awaiting update from team. ETA for JIRA deploy by 8th July. Will connect with customer after testing.
SKYTOWN Group | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 02-Jul-26 | 500000 | 10 | Completed: User Login, Project, Default Report Config, Routing. Mcube: outgoing set, incoming raised with Mcube, awaiting customer confirmation. Meta Integration in progress.
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | <=5 d | 06-Jul-26 |  |  | The client has specifically instructed us not to proceed with the implementation until the calling integration is completed.
i5 Housing and Properties LLP | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 03-Jul-26 |  |  | Admin training completed.

## 8. Re-grade (value+brand)
Category re-grade - value + licenses + brand/enterprise
Suggested grade = max of value, licence count, and brand/enterprise weight. Under-grading is the concern; higher-than-needed is low priority.
Summary: 6 under-graded (fix), 2 ungraded (set a grade), 0 clearly over-graded (low priority). ~8 A-deals score B on size alone (20-49 lic) - acceptable for enterprise/brand, not listed.
A) UNDER-GRADED - high value/brand but graded low (FIX THESE)
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Dhanraj Realbuild Llp | Venkat Viswavardhan | C | A | 60-90 d | blank | <10/blank |  | billed Rs5-7L
Kohinoor AI Calling | Venkat Viswavardhan | C | B | 60-90 d | blank | <10/blank | Known | known brand
NPS DEVELOPERS | Raahul Ramanan R | C | B | 60-90 d | blank | <10/blank |  | billed Rs3-5L
Shree Honda | Sourabh Sahu | C | B | >180 d | 2-3L | <10/blank |  | billed Rs2.11L
Sujay Global Homes | Venkat Viswavardhan | C | B | 30-60 d | blank | <10/blank |  | billed Rs3-5L
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | C | B | 14-30 d | blank | <10/blank |  | billed Rs2-3L
B) UNGRADED - no category set (assign one)
Includes Krishvi (already Active) and the 'dummy' test record.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Yashoda Infra Developer | Shweta Gouda | C | C | <14 d | blank | >=50 | Yashoda Infra Developer | uncategorized - new deal
Pavani Infra | Shweta Gouda | C | C | 14-30 d | blank | <10/blank |  | no value/licenses captured
C) Clearly over-graded - review (low priority)
B Square is actually live - close it rather than re-grade.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why

## 9. Comparison & Movement
Comparison & Movement vs previous run(s)
Run 6 (Tue 07-Jul-2026, refreshed) vs 02-Jul & 29-Jun
Deal | Owner | Stage prev->now | Last note prev->now | Movement verdict | Stuck streak | Reason / action
Ashtavinayak Construction | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Same-blocker | 5 | Website integration still the only pending item; unchanged - 5 runs stuck.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-06-30 -> 2026-07-03 | Same-blocker | 5 | Meta/WhatsApp call rescheduled at client request; lead import/hierarchy/inventory still pending on customer.
Dhanraj Realbuild Llp | Venkat Viswavardhan | Onboarding In Progress -> Pending on Customer | 2026-06-30 -> 2026-07-03 | Same-blocker | 5 | Escalating: concall arranged over pricing/false-promise dispute (GRE form/post-sales); moved to Pending-on-Customer, no progress.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-01 -> 2026-07-03 | Same-blocker | 5 | Same: requirement/JIRA awaiting dev deploy (now ETA 8 Jul); no customer-facing progress - 5 runs stuck.
Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-30 -> 2026-07-03 | Same-blocker | 5 | Still blocked on bulk outgoing-call testing (ESTATE-21040, ETA 11.2); no resolution - 5 runs stuck.
Ribitto Private Limited | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-06-30 -> 2026-07-06 | Same-blocker | 5 | Identical (bulk lead + FB pending); no movement - 5 runs stuck.
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-06-26 -> 2026-07-06 | Same-blocker | 5 | Client instructed HOLD until calling integration done - no implementation progress; 5 runs stuck.
Times Group | Sanket Nampalliwar | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-22 | No-touch | 5 | No new note/stage change since 2026-06-22.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-22 | No-touch | 5 | No new note/stage change since 2026-06-22.
Voora Developers | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-06-26 -> 2026-06-26 | No-touch | 5 | No new note/stage change since 2026-06-26.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 3 | No new note/stage change since 2026-06-22.
Phantom Advisory | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Same-blocker | 3 | No task completed; original bulk-lead/WhatsApp blockers unresolved, now awaiting internal Tejas on a sourcing ask.
Shrimant Developers | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Same-blocker | 3 | Website integration still only 'initiated' (the blocker); only an offline-dialer doc added.
Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-06-30 | No-touch | 2 | No new note/stage change since 2026-06-30.
TORANDWAR DEVELOPERS | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-28 -> 2026-07-03 | Same-blocker | 2 | Note restates same completions + lead file still awaited from client; nothing newly done.
Apex Construction | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Same-blocker | 1 | Identical completed list; dialer still the only pending item - unchanged.
GGC AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-30 -> 2026-07-03 | Same-blocker | 1 | Customer no-showed the call; reschedule next week - no progress.
NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-06-26 -> 2026-06-26 | No-touch | 1 | No new note/stage change since 2026-06-26.
SKYTOWN Group | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-02 -> 2026-07-02 | No-touch | 1 | No new note/stage change since 2026-07-02.
SS Salesforce | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-01 -> 2026-07-06 | Same-blocker | 1 | Identical completed list; website integration still the only pending item - unchanged.
Shree Automotive | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
Shree Honda | Sourabh Sahu | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-22 | No-touch | 1 | No new note/stage change since 2026-06-22.
Strata Capital Holdings | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-02 -> 2026-07-03 | Same-blocker | 1 | Still waiting on client's direct Mcube purchase before integrations - unchanged.
Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-07-06 | Same-blocker | 1 | Identical completed list; WhatsApp still pending, handover still 'planned' - unchanged.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-03 | Same-blocker | 1 | Meta verification still in progress & WhatsApp still pending on customer - no net completion.
Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking -> Under Usage Tracking | 2026-06-30 -> 2026-06-30 | No-touch | 1 | No new note/stage change since 2026-06-30.
Yula Globas | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-07-05 | Same-blocker | 1 | Identical completed list; IRIS/usage still the watch item - unchanged.
Axon Developer | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-07-05 | Progressed | 0 | Sales/Presales Training completed since last run.
Blueroof India | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Progressed | 0 | Offline Dialer now completed since last run (bulk lead/Meta/website still pending).
DhanVed Consultants | Shweta Gouda | NEW this run | - -> 2026-07-03 | NEW | 0 | New in pipeline this run.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-06-30 -> 2026-07-03 | Progressed | 0 | User hierarchy setup completed; CP-data upload guided (Mon), WhatsApp workflow expected 6-7 Jul.
Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-06-30 -> 2026-07-06 | Progressed | 0 | Onsite visit now scheduled for tomorrow to complete pending trainings - the awaited confirmation arrived.
Growthx Estates | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-01 -> 2026-07-06 | Progressed | 0 | Login/project/report/routing/GPS/clock-in now completed vs task-list only last run.
House of Colours | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-25 -> 2026-07-03 | Progressed | 0 | Reactivated from HOLD: user activation, fresh lead import, revised sales training, admin training, dashboards all completed.
Leonaara PVt LTD | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Progressed | 0 | Bulk Lead Import now completed vs pending last run.
Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-03 | Progressed | 0 | Call testing completed; feedback moved to internal tech (Sharayu) vs awaiting customer test last run.
Navkar Realty | Venkat Viswavardhan | Kickoff Done -> Onboarding In Progress | 2026-07-02 -> 2026-07-03 | Progressed | 0 | Stage Kickoff Done -> Onboarding In Progress.
PROPKART4U | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | - -> 2026-07-03 | Progressed | 0 | First real progress logged: login/project/report done, lead import guided, Meta lead captured.
Pavani Infra | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-07-03 | Progressed | 0 | Leads now actually uploaded (partial, date-format fixes) vs guided-only last run.
Properties Boutique | Sahil Jane | Kickoff Done -> Onboarding In Progress | 2026-07-01 -> 2026-07-05 | Progressed | 0 | Stage Kickoff Done -> Onboarding In Progress.
Rajparis Civil Construction | Muntazar Mhate | Kickoff Done -> Onboarding In Progress | 2026-07-01 -> 2026-07-06 | Progressed | 0 | Stage Kickoff Done -> Onboarding In Progress.
Real Estate Square | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Progressed | 0 | Offline Dialer + Sales Training completed since last run; bulk lead still pending.
Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Progressed | 0 | Property portals (99acres/Magicbricks) + website completed vs 'initiated' last run; Meta verification applied.
SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-03 | Progressed | 0 | Customer shared project import file (to upload Mon) - the awaited detail arrived.
Salahrealty Pvt Ltd | Muntazar Mhate | NEW this run | - -> 2026-07-06 | NEW | 0 | New in pipeline this run.
Sangram Group | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-01 -> 2026-07-06 | Progressed | 0 | IVR (MCube) + Facebook now completed vs waiting-on-client last run; only bulk lead pending.
Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Progressed | 0 | Base setup completed vs kickoff/task-list-only phase last run.
Sohum Estate Agency (Smeer Chheda) | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Progressed | 0 | Routing + sample lead/inventory imports now completed vs 'no movement from client' last run.
Sunrise Housing (GHP Group) | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Progressed | 0 | Base setup (login/project/report/routing) completed vs task-list only last run.
Supreme Vision Infrabuild Private Limited (Augusta Realty) | Shweta Gouda | Open -> Onboarding In Progress | - -> 2026-07-03 | Progressed | 0 | Stage Open -> Onboarding In Progress.
The Bangalore Real Estate Co. | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-06 | Progressed | 0 | Sales/Presales & Mobile Training + Sell.do Dialer completed since last run.
VASTU INFINITY AND VENTURES LLP | Sahil Jane | Open -> Kickoff Done | - -> 2026-07-06 | Progressed | 0 | Stage Open -> Kickoff Done.
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-02 -> 2026-07-03 | Progressed | 0 | Moved past bulk-lead error to next-week plan (connect meta/whatsapp, schedule training).
VIVANTA GROUP | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-29 -> 2026-07-03 | Progressed | 0 | Meta campaign + website integration completed; blocker moved to Mcube NDNC/URLs.
VRUSHABADRI DEVELOPERS | Sahil Jane | Open -> Onboarding In Progress | - -> 2026-07-05 | Progressed | 0 | Stage Open -> Onboarding In Progress.
YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-03 | Progressed | 0 | Customer verifying full setup, confirmation by Monday then handover to support - nearing handover.
Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-06-30 -> 2026-07-03 | Progressed | 0 | Lead import completed + 99acres portal lead captured (#7) vs pending last run.
i5 Housing and Properties LLP | Venkat Viswavardhan | Pending on Customer -> Onboarding In Progress | 2026-06-29 -> 2026-07-03 | Progressed | 0 | Stage Pending on Customer -> Onboarding In Progress.