## 1. Stats
Sell.do Onboarding Pipeline - Statistics
Pipeline 27474 ¦ 61 open deals ¦ Snapshot 2026-07-10
Ageing = days since deal CREATED (created_at). Movement = days since last activity (separate metric).
By Owner
Category | Count
Venkat Viswavardhan | 16
Muntazar Mhate | 14
Sahil Jane | 11
Shweta Gouda | 9
Raahul Ramanan R | 5
Sanket Nampalliwar | 2
Sourabh Sahu | 2
Shubham Dubey | 1
Ganesh Vamsee | 1
Total | 61
By Pipeline Stage
Category | Count
Open | 6
Kickoff Done | 2
Onboarding In Progress | 38
Pending on Customer | 14
Under Usage Tracking | 0
Total | 60
Deal Ageing = days since CREATED (created_at)
Category | Count
<14 days | 18
14-30 days | 15
30-60 days | 12
60-90 days | 9
90-180 days | 3
180+ days | 4
Total | 61
Movement = days since LAST ACTIVITY
Category | Count
<=5 days (healthy) | 60
5-7 days | 1
7-15 days | 0
15-30 days | 0
30+ days | 0
Total | 61
Touch cadence = days since LAST NOTE (interim proxy until meetings are logged)
Category | Count
<=5 days (OK) | 55
6-10 days | 1
11-15 days | 1
16-30 days | 2
31+ days | 0
Never (no note) | 2
Total | 61
Meetings ON DEALS (not yet logged - format ready going forward)
Category | Count
Deals with a meeting logged on the deal | 0
Meeting scheduled/conducted within 5 days | 0
NO meeting logged (team to start logging) | 61
Risk & Data-Quality Flags
Category | Count
No activity 5+ days (your risk rule) | 1
No notes logged at all | 2
Target go-live date already breached | 26
Customer 'Yet to sign up' | 1
No future follow-up task | 38
Has an OVERDUE task | 10
Billed Amount field blank | 52
Estimated Value populated | 0
Meetings linked to these onboarding deals | 0

## 2. Exec Summary (CEO-CRO)
Onboarding Pipeline - Executive Summary
For CEO & CRO ¦ 2026-07-10
The headline (movement this run)
61 deals are open in onboarding. Comparing today vs the last run: 20 have GENUINELY PROGRESSED, but 33 have NOT moved (26 restate the same blocker, 7 had no activity at all) and 16 of those have now been stuck for 2+ consecutive runs (SUPER-RED - see Sheet 9); 9 of those have been stuck 6 runs in a row. 8 deals are new this run. 26 deals (43%) are already past their committed go-live date.
Data hygiene is still the structural issue: Billed Amount is blank on 43 of 61 deals (70%), Estimated Value is empty on every deal, 38 of 61 have no next task, and 2 (both new) deals still have zero notes. Note that get_deal_notes returns notes unsorted, so several stale deals' newest note had to be recovered via a larger fetch. Revenue-at-risk remains largely invisible in standard reports.
Where the money is exposed
Cash collected but customer still 'Yet to sign up': Doff Estate Post Sales - Rs5.24L fully received but not activated (new deal this run). Push to sign-up now.
Largest accounts by value: Times Group Rs9.44L (Pending-on-Customer - client UAT feedback overdue since 23-Jun, stuck 6 runs), Doff Estate & Doff Estate Post Sales Rs5.24L each (new, Open), SKYTOWN Rs5.0L (moved to Pending-on-Customer), Navkar Rs4.96L (Pending-on-Customer). Largest by licences: Kunwarji Realtors - 150 licences, Category A, go-live breached; client escalated rollout delays on 3-Jul in a meeting with the CEO and requested onsite support.
What we are asking leadership to back
1. A weekly onboarding hygiene standard: every open deal must have a LOGGED MEETING (scheduled or conducted) at least every 5 days, a dated note, and a next task; stage moved at each milestone. (Meetings are still not logged on deals at all.)
2. Make Billed Amount mandatory at deal creation so revenue-at-risk is visible (blank on 78% today).
3. A weekly SUPER-RED review: 16 deals have not genuinely moved for 2+ runs (9 of them for 6 runs straight) - most are stuck 'pending on customer'. Set drop-dead dates or move to HOLD.
4. A 'collections + activation' sweep on the paid-but-dormant accounts above (CRO + Onboarding).

## 3. Owner Scorecard
Owner Scorecard - gaps for the Onboarding Head
Counts per owner across the key risk flags. Use for owner 1:1s.
Owner | Open deals | A-grade | Idle 5+ d | No notes | Go-live overdue | Not signed up | No next task | Overdue task | Key gap to address
Venkat Viswavardhan | 16 | 6 | 1 | 0 | 9 | 0 | 9 | 3 | 16 deal(s). pending-on-customer: SKYTOWN Group, Navkar Realty, VAZHRAA NIRMAAN PRIVATE LIMITED, GGC AI Calling, Mythri Builder AI Calling.
Muntazar Mhate | 14 | 0 | 0 | 1 | 6 | 0 | 14 | 0 | 14 deal(s). no notes: Palli Developers and Consultants LLP. pending-on-customer: Ribitto Private Limited, Gram Strategic Advisors LLP.
Sahil Jane | 11 | 1 | 0 | 0 | 5 | 0 | 4 | 0 | 11 deal(s).
Shweta Gouda | 9 | 0 | 0 | 0 | 3 | 0 | 5 | 4 | 9 deal(s).
Raahul Ramanan R | 5 | 3 | 0 | 0 | 2 | 0 | 2 | 3 | 5 deal(s). pending-on-customer: Calicut Landmark Builders Pvt. Ltd, Upcurve consumer Technologies Pvt Ltd, Voora Developers.
Sanket Nampalliwar | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 2 deal(s). pending-on-customer: Times Group.
Sourabh Sahu | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 deal(s).
Shubham Dubey | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 deal(s). no notes: Doff Estate Post Sales.
Ganesh Vamsee | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 deal(s).
TOTAL | 61 | 13 | 1 | 2 | 26 | 1 | 38 | 10

## 4. Deal-Level Tracker
Deal-Level Tracker - for the Onboarding Head to action
Cols E-F = movement vs the LAST run: Progressed / NEW / STUCK (same blocker or no activity). Stuck deals are grouped at the top. SUPER-RED = no genuine movement for 2+ consecutive runs.
Deal ID | Deal Name | Owner | Stage | Moved? (vs last run) | Movement detail (prev -> now) | Last activity | Last note date | Days since note | Has notes | Go-live overdue | Not signed up | Billed (Rs) | Licenses | Cat | Last note / status | Age (created) | Key Next Step (recommended) | Touch cadence (interim, vs 5d) | Last meeting | Next meeting | Mtg <=5d?
4299438 | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | SUPER-RED (6 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-06 -> 2026-07-06 ¦ Bulk lead + Facebook still pending on customer, unchanged. [stuck x6] | <=5 d | 06-Jul-26 | 4 | Yes | Yes |  |  |  | C | Completed: User Login, Project, Default Report Config, Routing, Product Briefing, WATI Integration, Offline Dialer, GPS, Clock-in/out, Admin Training. Pending: Bulk Lead Import (Excel), Facebook Integration. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4255693 | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | SUPER-RED (6 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-03 -> 2026-07-03 ¦ Still customer-blocked (lead/hierarchy/inventory); project-plan rework pending. [stuck x6] | <=5 d | 03-Jul-26 | 7 | Yes |  |  |  |  | A | Updates on Onboarding shared. Meta Integration & Native WhatsApp call scheduled today 2:15 PM but rescheduled to next week per client request. Lead import/hierarchy/inventory still pending on customer. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Watch | None logged | None logged | No - none logged
4255681 | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | SUPER-RED (6 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ Client still holding implementation until calling integration done. [stuck x6] | <=5 d | 06-Jul-26 | 4 | Yes | Yes |  |  |  | A | The client has specifically instructed us not to proceed with the implementation until the calling integration is completed. | 30-60 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
3623014 | Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer | SUPER-RED (6 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-22 ¦ OB still on pause; POC unresponsive. [stuck x6] | <=5 d | 22-Jun-26 | 18 | Yes |  |  |  |  | Broker | Escalated account, Onboarding on Pause as POC unresponsive. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | Stale | None logged | None logged | No - none logged
3575524 | Voora Developers | Raahul Ramanan R | Pending on Customer | SUPER-RED (6 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-26 -> 2026-07-07 ¦ Still awaiting EPR docs / external handover; long-stalled. [stuck x6] | <=5 d | 07-Jul-26 | 3 | Yes | Yes |  |  |  | A | Follow-up with AM team on new tasks; plan handover post EPR docs confirmation. | 90-180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
3302998 | Times Group | Sanket Nampalliwar | Pending on Customer | SUPER-RED (6 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-06-22 -> 2026-06-22 ¦ Still awaiting client UAT feedback on inventory; no movement since June. [stuck x6] | <=5 d | 22-Jun-26 | 18 | Yes |  |  | 944000 | 50 | A | Unit data uploaded to demo, dashboards ready; client UAT, feedback due 23 Jun EOD. | >180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Stale | None logged | None logged | No - none logged
4144089 | Dhanraj Realbuild Llp | Venkat Viswavardhan | Pending on Customer | SUPER-RED (6 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-03 -> 2026-07-08 ¦ Same GRE-form / post-sales dispute; Ankur + customer call again today. [stuck x6] | <=5 d | 08-Jul-26 | 2 | Yes |  |  |  |  | C | Call scheduled today 11 AM with Ankur and customer to discuss further. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to A) | OK (<=5d) | None logged | None logged | No - none logged
3968505 | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (6 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-08 ¦ Same GRE-form JIRA deploy blocker, only day-shifted. [stuck x6] | <=5 d | 08-Jul-26 | 2 | Yes |  |  |  |  | A | GRE-form feedback expected to deploy today EOD; will share with customer after testing. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4233715 | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | SUPER-RED (6 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-03 -> 2026-07-08 ¦ Same bulk-outgoing-call issue; 7-Jul call rescheduled again. [stuck x6] | <=5 d | 08-Jul-26 | 2 | Yes | Yes |  |  |  | C | Call to be scheduled to discuss issues customer facing. 7th July call rescheduled; awaiting their availability. | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4370376 | Shrimant Developers | Muntazar Mhate | Onboarding In Progress | SUPER-RED (4 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note since last run; website integration still the sole open task. [stuck x4] | <=5 d | 06-Jul-26 | 4 | Yes | Yes |  |  |  | C | Completed incl Offline Dialer; Pending Website Integration (initiated). | 14-30 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4177642 | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-26 -> 2026-06-26 ¦ No new note since last run; WhatsApp / post-sales re-OB still pending on client details. [stuck x2] | <=5 d | 26-Jun-26 | 14 | Yes |  |  |  |  | C | OB Weekly Update (26 Jun): WhatsApp Setup Completed, Mcube Setup Completed. Sourabh to check with client for Post-sales Re-OB. | 60-90 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | Stale | None logged | None logged | No - none logged
4382895 | SS Salesforce | Sahil Jane | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-08 ¦ No task newly completed; website pending, admin training only scheduled. [stuck x2] | <=5 d | 08-Jul-26 | 2 | Yes | Yes |  |  |  | C | Completed: user/project/report config, 99acres, Facebook, 3841 leads uploaded, dialer, inventory. Admin training scheduled this week. | 14-30 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4313304 | Yula Globas | Sahil Jane | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-05 -> 2026-07-05 ¦ No new note since last run; low usage / IRIS issue persists. [stuck x2] | <=5 d | 05-Jul-26 | 5 | Yes | Yes |  |  |  | C | Completed incl Property Portal, Website, Routing, MCube; low usage/IRIS watched. | 30-60 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
3304062 | Shree Automotive | Sourabh Sahu | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-07-07 ¦ Mcube setup still not done; only a re-initiation meeting scheduled. [stuck x2] | <=5 d | 07-Jul-26 | 3 | Yes |  |  | 104784 | 4 | C | Scheduled meeting 8th July with POC Mithilesh & Director Abhishek to re-initiate OB; review status, discuss pending. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (<=5d) | None logged | None logged | No - none logged
4325921 | Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-08 ¦ Near handover but nothing newly completed; only requesting admin-training slots. [stuck x2] | <=5 d | 08-Jul-26 | 2 | Yes | Yes |  |  |  | C | Requested slots for Admin training; ETA to schedule by tomorrow. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4204921 | Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking | SUPER-RED (2 runs stuck) | Stage Under Usage Tracking -> Under Usage Tracking ¦ Note 2026-06-30 -> 2026-07-07 ¦ Still awaiting customer cost-sheet feedback; handover call not yet held. [stuck x2] | <=5 d | 07-Jul-26 | 3 | Yes | Yes |  |  |  | A | Awaiting customer update on cost sheet; handover call to be scheduled this week. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4412002 | Blueroof India | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note/stage change since 2026-07-06. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes |  |  |  | 2 | C | Completed: user/project/report config, routing, GPS/clock-in, offline dialer. Pending: Bulk Lead Import, Facebook. | 14-30 d | Priority tasks shared — progress integrations. | OK (<=5d) | None logged | None logged | No - none logged
4079157 | Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer | STUCK - same blocker | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note since last run; onsite training visit still not scheduled. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes | Yes |  |  |  | B | As discussed with client, the onsite visit is scheduled for tomorrow to complete the pending trainings. | 60-90 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4457232 | Growthx Estates | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note/stage change since 2026-07-06. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes |  |  |  | 10 | Broker | Completed: user/project/report config, routing, GPS/clock-in. Pending: Bulk Lead Import (sample shared), portal/Meta/Google, WhatsApp. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4449587 | Rajparis Civil Construction | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note/stage change since 2026-07-06. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes |  |  |  | 15 | B | Completed: user/project/report config, routing, bulk lead. Pending: Property Portal (99Acres/India Residential) initiated - awaiting POC email. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4364225 | Real Estate Square | Muntazar Mhate | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note since last run; bulk lead import still pending. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes | Yes |  |  |  | Broker | Completed incl Admin Training, Offline Dialer, Sales training; Pending Bulk Lead Import. | 30-60 d | Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4386888 | Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note since last run; Meta Business verification still awaited. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes | Yes |  |  |  | C | Completed incl website; client applied Meta Business verification, expected today. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4472721 | Salahrealty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note/stage change since 2026-07-06. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes |  |  |  | 2 | C | Priority Onboarding Tasks logged: user/project creation, routing, offline dialer, inventory (tentative), trainings. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4345401 | Sangram Group | Muntazar Mhate | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note since last run; WhatsApp number & bulk lead still pending on customer. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes | Yes |  |  |  | C | Completed: User Login, Project, Default Report Config, Routing, IVR (MCube) Integration - Sangram Group, Facebook. Pending: Bulk Lead Import (Excel). | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4336926 | Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note since last run; bulk lead + website still pending. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes |  |  |  |  | C | Completed user/project/report/routing; Pending Bulk Lead (sample shared) + Website (awaiting dev email). | 30-60 d | Chase kickoff slot; escalate to customer exec if no response in 5 days. | OK (<=5d) | None logged | None logged | No - none logged
4370391 | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note/stage change since 2026-07-06. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes |  |  |  |  | C | Completed: user/project/report config, routing, sample lead & inventory. Pending: Bulk Lead, portal, Facebook. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4430582 | Sunrise Housing (GHP Group) | Muntazar Mhate | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-06 ¦ No new note/stage change since 2026-07-06. [stuck x1] | <=5 d | 06-Jul-26 | 4 | Yes |  |  |  | 11 | B | Completed: user/project/report config, routing. Pending: Bulk Lead Import (sample shared), Facebook (Meta) Integration. | 14-30 d | New deal — kickoff + sign-up; no notes yet, log first status. | OK (<=5d) | None logged | None logged | No - none logged
4389674 | Axon Developer | Sahil Jane | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-05 -> 2026-07-08 ¦ CAPI integration still pending; only a Monday meeting scheduled. [stuck x1] | <=5 d | 08-Jul-26 | 2 | Yes | Yes |  |  |  | A | Completed: account/user/project, hierarchy, routing, bulk lead, Facebook, sales training. CAPI integration meeting Monday; admin pending. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4389699 | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-08 ¦ WhatsApp (Interakt) + IVR (Airtel) still pending, now blocked on our end. [stuck x1] | <=5 d | 08-Jul-26 | 2 | Yes | Yes |  |  |  | C | WhatsApp & IVR integrations pending from our end - Interakt not sending outgoing msgs; Airtel IVR setup not yet completed. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4411978 | The Bangalore Real Estate Co. | Sahil Jane | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-08 ¦ Same completed set; website integration still the open gap. [stuck x1] | <=5 d | 08-Jul-26 | 2 | Yes | Yes |  | 66316 | 7 | C | Completed: user/project/report config, bulk lead, Magic Bricks portal, inventory, sales/presales & mobile training, dialer. | 14-30 d | Kickoff done — move into onboarding, start priority tasks. | OK (<=5d) | None logged | None logged | No - none logged
4458771 | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | STUCK - no activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-05 -> 2026-07-05 ¦ No new note/stage change since 2026-07-05. [stuck x1] | <=5 d | 05-Jul-26 | 5 | Yes |  |  | 241900 | 8 | C | Priority Onboarding Tasks logged: user/project creation, routing, property portal, Meta, native WhatsApp, website, CP form, dialer, trainings. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4357586 | Pavani Infra | Shweta Gouda | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-07 ¦ Same status: Meta leads blocked on bad date/stage format; website discussion ongoing. [stuck x1] | <=5 d | 07-Jul-26 | 3 | Yes | Yes |  |  |  | C | Completed: user/project, lead import (except Meta leads - bad date format/stages), Meta lead #10, website discussion. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4383383 | VIVANTA GROUP | Shweta Gouda | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-07 ¦ Website & Meta integration still pending; only a call scheduled. [stuck x1] | <=5 d | 07-Jul-26 | 3 | Yes |  |  |  |  | C | Call scheduled 8th July for website & Meta integration. Completed: user activation, project creation, lead import guided. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4481260 | Urbanyx Infra | Ganesh Vamsee | Open | NEW this run | New in pipeline this run. | <=5 d | 10-Jul-26 | 0 | Yes |  |  |  | 5 | (none) | No response to calls. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4480069 | Palli Developers and Consultants LLP | Muntazar Mhate | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  |  | 153400 | 5 | C |  | <14 d | Log first note + confirm kickoff / next milestone. | No note | None logged | None logged | No - none logged
4479594 | Apex Realty Hub | Sahil Jane | Kickoff Done | NEW this run | New in pipeline this run. | <=5 d | 07-Jul-26 | 3 | Yes |  |  | 81420 | 5 | C | Priority Onboarding Tasks logged: user/project creation, bulk lead, native WhatsApp, dialer, website, property portal, Meta, inventory, trainings. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4479599 | Propnsafe Realty LLP | Sahil Jane | Kickoff Done | NEW this run | New in pipeline this run. | <=5 d | 07-Jul-26 | 3 | Yes |  |  | 172516 | 3 | C | Priority Onboarding Tasks logged: account/user/project creation, routing, Mcube, native WhatsApp, bulk lead import, trainings. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4491940 | Doff Estate Post Sales | Shubham Dubey | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  | Yes | 523919 | 29 | A |  | <14 d | Log first note + confirm kickoff / next milestone. | No note | None logged | None logged | No - none logged
4478489 | PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Open | NEW this run | New in pipeline this run. | <=5 d | 07-Jul-26 | 3 | Yes |  |  |  |  | (none) | Kick Off Call scheduled on 9th July at 11:00am. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4482197 | Scanon Realty | Shweta Gouda | Open | NEW this run | New in pipeline this run. | <=5 d | 08-Jul-26 | 2 | Yes |  |  | 11328 | 2 | Broker | Kick Off Call scheduled on 10th July at 1:00pm. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4482302 | Doff Estate | Venkat Viswavardhan | Open | NEW this run | New in pipeline this run. | <=5 d | 10-Jul-26 | 0 | Yes |  |  | 523919 | 29 | A | Priority Onboarding Tasks; Inventory upload to be handled in Post sales; Sales/Presales & Admin training pending; Website integration. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4233760 | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-07-03 -> 2026-07-08 ¦ AI-calling feedback implemented & tested; awaiting customer confirmation. | 5-7 d | 08-Jul-26 | 2 | Yes | Yes |  |  |  | C | Feedback implemented and tested; looks fine. Awaiting customer to confirm. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4357637 | Apex Construction | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-08 ¦ Workflow-clarity calls completed with client; sales training scheduled Friday. | <=5 d | 08-Jul-26 | 2 | Yes |  |  |  |  | C | Completed 2-3 workflow discussion calls with client (lacked clarity). Sales training scheduled Friday. | 30-60 d | Customer keeps rescheduling - lock one firm slot or pause the account. | OK (<=5d) | None logged | None logged | No - none logged
4458749 | Properties Boutique | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-05 -> 2026-07-08 ¦ Dialer + sales training now completed (were pending); Meta call still Monday. | <=5 d | 08-Jul-26 | 2 | Yes |  |  | 61360 | 7 | C | Completed: account/user/project/report config, dialer, sales training. Meta call scheduled Monday; inventory & admin training pending. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4458766 | VASTU INFINITY AND VENTURES LLP | Sahil Jane | Onboarding In Progress | Progressed | Stage Kickoff Done -> Onboarding In Progress ¦ Note 2026-07-06 -> 2026-07-08 ¦ Stage Kickoff Done -> Onboarding In Progress. | <=5 d | 08-Jul-26 | 2 | Yes |  |  | 33000 | 5 | C | Completed: user/project/report config. Pending: Meta on hold (POC unavailable 2 weeks); Bulk Lead file received today; trainings; dialer. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4230613 | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-07-07 ¦ Client escalation meeting held (CEO + Siddharth); rollout-timeline concerns & onsite ask raised. | <=5 d | 07-Jul-26 | 3 | Yes | Yes |  |  | 150 | A | Meeting with client 03 Jul (Ketan Sir & Siddharth). Client raised concerns on rollout timelines & implementation delay; requested onsite team member. | 60-90 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | OK (<=5d) | None logged | None logged | No - none logged
4461524 | DhanVed Consultants | Shweta Gouda | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-07 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 07-Jul-26 | 3 | Yes |  |  |  |  | Broker | Completed: user/project creation, report config, lead import guided. Pending: Admin Training call scheduled. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
3417644 | House of Colours | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-07 ¦ Fresh note: revised sales training + custom sales dashboard completed; 99acres listing IDs requested. | <=5 d | 07-Jul-26 | 3 | Yes | Yes |  |  |  | C | Completed: user activation, fresh lead import, report config, pipeline stages, revised sales training, custom sales dashboard; 99acres listing IDs requested. | >180 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4375201 | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-07 ¦ Inventories uploaded, clock-in/out & native WhatsApp now completed. | <=5 d | 07-Jul-26 | 3 | Yes | Yes |  |  |  | Broker | Completed: user/project/report config, lead import guided, inventories uploaded, clock in/out, native WhatsApp. | 14-30 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4453288 | Supreme Vision Infrabuild Private Limited (Augusta Realty) | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-08 ¦ Lead import completed; Meta integration call scheduled 9th. | <=5 d | 08-Jul-26 | 2 | Yes |  |  | 147500 | 4 | C | Completed: user/project/report config, lead import guided. Pending: Meta integration call scheduled 9th; website; trainings. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4438366 | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-07 ¦ Meta integration now live (lead #215 captured). | <=5 d | 07-Jul-26 | 3 | Yes |  |  |  | 50 | C | Completed: user/project/report config, leads uploaded, 99acres lead #7, Meta lead #215. | <14 d | New deal; categorize the account and log first onboarding note. | OK (<=5d) | None logged | None logged | No - none logged
3304063 | Shree Honda | Sourabh Sahu | Onboarding In Progress | Progressed | Stage Pending on Customer -> Onboarding In Progress ¦ Note 2026-06-22 -> 2026-07-07 ¦ Stage Pending on Customer -> Onboarding In Progress. | <=5 d | 07-Jul-26 | 3 | Yes |  |  | 210983 | 5 | C | Scheduled meeting 8th July with POC Mithilesh & Director Abhishek to re-initiate OB; review status, discuss pending, DND/NDNC + Mcube. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4147287 | Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-03 -> 2026-07-08 ¦ Channel-partner data imported; now awaiting WhatsApp workflow + inventory from customer. | <=5 d | 08-Jul-26 | 2 | Yes | Yes |  |  |  | A | WhatsApp workflow to be re-shared by customer; inventory files to be shared by customer; channel partner imported. | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (<=5d) | None logged | None logged | No - none logged
4241966 | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-03 -> 2026-07-08 ¦ Explainer call completed; new ask to connect calls with Highrise CRM (feasibility check). | <=5 d | 08-Jul-26 | 2 | Yes |  |  |  |  | C | Call completed; explained reports/recordings/scripts. Customer wants to connect calls with Highrise CRM; checking feasibility, update tomorrow. | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (<=5d) | None logged | None logged | No - none logged
4402389 | Navkar Realty | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-07-03 -> 2026-07-08 ¦ AI-calling feedback received (was awaited); only WhatsApp template dump now pending on customer. | <=5 d | 08-Jul-26 | 2 | Yes |  |  | 495600 | 4 | C | AI Feedback received and shared with Sharayu. Awaiting details on Pinnacle WhatsApp templates dump. | 14-30 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4446753 | SKYTOWN Group | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-07-02 -> 2026-07-08 ¦ Mcube resolved; only inventory + WhatsApp number now pending on customer (file due EOD). | <=5 d | 08-Jul-26 | 2 | Yes |  |  | 500000 | 10 | A | Pending from customer: Inventory + WhatsApp number for integration. Inventory file expected today EOD. | <14 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
4435090 | SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-08 ¦ Project file imported (was pending); duplicate-lead-storage requirement raised with dev. | <=5 d | 08-Jul-26 | 2 | Yes |  |  | 200000 | 10 | Broker | Project file imported. Duplicate-lead-storage requirement raised; awaiting dev team timeline. User/project creation done. | 14-30 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
4370308 | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Pending on Customer | Progressed | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-07-03 -> 2026-07-10 ¦ Sales training completed; Meta not required, WhatsApp reuse in progress. | <=5 d | 10-Jul-26 | 0 | Yes | Yes |  |  |  | C | Sales Training completed; Admin to be scheduled today per availability. Meta not required; WhatsApp number reuse in progress. | 14-30 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4402374 | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-10 ¦ Sales training completed; admin training to be scheduled next week. | <=5 d | 10-Jul-26 | 0 | Yes | Yes |  | 350000 | 15 | B | Sales Training Completed. Admin training to be scheduled next week. | 14-30 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4358959 | YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-08 ¦ Near handover; customer raised new lead-import & website-integration asks (details due EOD). | <=5 d | 08-Jul-26 | 2 | Yes | Yes |  |  |  | Broker | Customer raised lead-import & website-integration requirement; expected details today EOD else handover keeping these 2 pending. | 30-60 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4337048 | i5 Housing and Properties LLP | Venkat Viswavardhan | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-03 -> 2026-07-08 ¦ Meta, 99Acres, CommonFloor, CP form & trainings completed; WhatsApp call today. | <=5 d | 08-Jul-26 | 2 | Yes | Yes |  |  |  | A | WhatsApp integration call scheduled today 3PM. Completed: user/project/report config, routing, Meta, 99Acres, CommonFloor, CP form, trainings. | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. | OK (<=5d) | None logged | None logged | No - none logged

## 5. Large-Stuck-Attention
Large deals, Stuck deals & Deals needing attention - for everyone
A) LARGE DEALS (value / licenses) - protect these
Deal | Owner | Stage | Billed (Rs) | Licenses | Cat | Status / note
Times Group | Sanket Nampalliwar | Pending on Customer | 944000 | 50 | A | Unit data uploaded to demo, dashboards ready; client UAT, feedback due 23 Jun EOD.
Doff Estate Post Sales | Shubham Dubey | Open | 523919 | 29 | A
Doff Estate | Venkat Viswavardhan | Open | 523919 | 29 | A | Priority Onboarding Tasks; Inventory upload to be handled in Post sales; Sales/Presales & Admin training pending; Website integration.
SKYTOWN Group | Venkat Viswavardhan | Pending on Customer | 500000 | 10 | A | Pending from customer: Inventory + WhatsApp number for integration. Inventory file expected today EOD.
Navkar Realty | Venkat Viswavardhan | Pending on Customer | 495600 | 4 | C | AI Feedback received and shared with Sharayu. Awaiting details on Pinnacle WhatsApp templates dump.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 350000 | 15 | B | Sales Training Completed. Admin training to be scheduled next week.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress |  | 150 | A | Meeting with client 03 Jul (Ketan Sir & Siddharth). Client raised concerns on rollout timelines & implementation delay; requested onsite team member.
Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress |  | 50 | C | Completed: user/project/report config, leads uploaded, 99acres lead #7, Meta lead #215.
B) STUCK DEALS (30+ days idle, or notes say 'no movement / on hold / call rescheduled')
Deal | Owner | Stage | Last note | Idle | Status / note
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | 03-Jul-26 | <=5 d | Updates on Onboarding shared. Meta Integration & Native WhatsApp call scheduled today 2:15 PM but rescheduled to next week per client request. Lead import/hierarchy/inventory still pending on customer.
VASTU INFINITY AND VENTURES LLP | Sahil Jane | Onboarding In Progress | 08-Jul-26 | <=5 d | Completed: user/project/report config. Pending: Meta on hold (POC unavailable 2 weeks); Bulk Lead file received today; trainings; dialer.
Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | 08-Jul-26 | <=5 d | Call to be scheduled to discuss issues customer facing. 7th July call rescheduled; awaiting their availability.
C) NEEDS ATTENTION (paid but 'Yet to sign up', or large + go-live breached)
Deal | Owner | Stage | Billed (Rs) | Signed up? | Go-live overdue | Status / note
Doff Estate Post Sales | Shubham Dubey | Open | 523919 | Yet to sign up
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 350000 | - | Yes | Sales Training Completed. Admin training to be scheduled next week.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress |  | - | Yes | Meeting with client 03 Jul (Ketan Sir & Siddharth). Client raised concerns on rollout timelines & implementation delay; requested onsite team member.

## 6. Pending-on-Customer Check
'Pending on Customer' validation - is it really moving?
14 deals sit in this stage. Verdict from last 2-3 notes + activity.
Deal | Owner | Last note | Days since | Verdict | Clear next action
SKYTOWN Group | Venkat Viswavardhan | 08-Jul-26 | 2 | Unknown | Owner to log status + next step immediately.
Navkar Realty | Venkat Viswavardhan | 08-Jul-26 | 2 | Unknown | Owner to log status + next step immediately.
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | 10-Jul-26 | 0 | Unknown | Owner to log status + next step immediately.
Ribitto Private Limited | Muntazar Mhate | 06-Jul-26 | 4 | STUCK | No genuine note movement in 3 runs; pending bulk lead + FB from customer. Escalate / chase lead file.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | 03-Jul-26 | 7 | STUCK | Wrong project plan shared; Sanket to re-share & confirm. No real customer movement in 3 runs.
Mythri Builder AI Calling | Venkat Viswavardhan | 08-Jul-26 | 2 | Unknown | Owner to log status + next step immediately.
Kohinoor AI Calling | Venkat Viswavardhan | 08-Jul-26 | 2 | STUCK | BOT shared for testing; awaiting Mcube number from customer since ~May. Chase; set test date.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | 22-Jun-26 | 18 | STUCK | Last real note Feb-26; many integrations pending. Re-open kickoff or escalate.
Voora Developers | Raahul Ramanan R | 07-Jul-26 | 3 | STUCK | Handover scheduled in Feb never happened. Escalate; re-open.
Times Group | Sanket Nampalliwar | 22-Jun-26 | 18 | STUCK | Inventory UAT dragging since Nov. Escalate to close UAT and sign off.
Dhanraj Realbuild Llp | Venkat Viswavardhan | 08-Jul-26 | 2 | Customer-blocked | Concall with Ankur + customer Mon on virtual-number pricing / GRE-form expectations; MIS shared. AI calling unpaid, Meta verification pending.
GGC AI Calling | Venkat Viswavardhan | 08-Jul-26 | 2 | Moving slowly | Approaching handover; awaiting client feedback. Get feedback then handover with Siddharth.
Dreamworks Realtors | Venkat Viswavardhan | 08-Jul-26 | 2 | Near done | Almost all tasks complete; only bulk lead import pending. Close out & handover.
Gram Strategic Advisors LLP | Muntazar Mhate | 06-Jul-26 | 4 | Near done | Most complete (Broker). Schedule final handover this week.

## 7. Customer Category
Customer Category - usage & priority check
A/B/C/Broker should drive onboarding priority & SLA. Today it is captured but not acted on.
Distribution & risk by category
Category | Deals | % of pipe | Idle 5+ d | No notes | Not signed up | Go-live overdue
A (top priority) | 13 | 21% | 0 | 1 | 1 | 7
B | 4 | 7% | 0 | 0 | 0 | 2
C | 34 | 56% | 1 | 1 | 0 | 14
Broker | 8 | 13% | 0 | 0 | 0 | 3
Uncategorized | 2 | 3% | 0 | 0 | 0 | 0
Total | 61
What this tells us
- A-grade = your most important accounts (11 deals). 0 have had NO activity in 5+ days and 1 have no notes at all - cadence on the A's has improved, keep it tight.
- Category is still not used to prioritise: A deals (Kunwarji 150 lic, Times, i5, Raghava) sit alongside C deals with the same attention. Tie an SLA to grade.
- Value is not tracked consistently: the biggest billed deal, Times Group (~Rs9.4L), is Category A, but Billed Amount is blank on 52 of 67 deals - populate it and re-grade against value + licences.
- 0 deals are uncategorized this run (good) - keep category mandatory at creation so nothing falls through prioritisation.
- 55% of the pipeline (37) is tagged C. Either genuinely low-value, or default tagging - worth a quick audit so C actually means C.
- Recommendation: tie an SLA to category - A = white-glove, named owner, weekly touch + exec visibility; B = fortnightly; C/Broker = templatised. Make category mandatory and value-aligned at deal creation.
A-GRADE WATCHLIST (protect these 15 - sorted by neglect)
Deal | Owner | Stage | Idle | Last note | Billed (Rs) | Lic | Status / note
Axon Developer | Sahil Jane | Onboarding In Progress | <=5 d | 08-Jul-26 |  |  | Completed: account/user/project, hierarchy, routing, bulk lead, Facebook, sales training. CAPI integration meeting Monday; admin pending.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | <=5 d | 03-Jul-26 |  |  | Updates on Onboarding shared. Meta Integration & Native WhatsApp call scheduled today 2:15 PM but rescheduled to next week per client request. Lead import/hierarchy/inventory still pending on customer.
Doff Estate | Venkat Viswavardhan | Open | <=5 d | 10-Jul-26 | 523919 | 29 | Priority Onboarding Tasks; Inventory upload to be handled in Post sales; Sales/Presales & Admin training pending; Website integration.
Doff Estate Post Sales | Shubham Dubey | Open | <=5 d |  | 523919 | 29
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer | <=5 d | 08-Jul-26 |  |  | WhatsApp workflow to be re-shared by customer; inventory files to be shared by customer; channel partner imported.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 08-Jul-26 |  |  | GRE-form feedback expected to deploy today EOD; will share with customer after testing.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | <=5 d | 07-Jul-26 |  | 150 | Meeting with client 03 Jul (Ketan Sir & Siddharth). Client raised concerns on rollout timelines & implementation delay; requested onsite team member.
SKYTOWN Group | Venkat Viswavardhan | Pending on Customer | <=5 d | 08-Jul-26 | 500000 | 10 | Pending from customer: Inventory + WhatsApp number for integration. Inventory file expected today EOD.
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | <=5 d | 06-Jul-26 |  |  | The client has specifically instructed us not to proceed with the implementation until the calling integration is completed.
Times Group | Sanket Nampalliwar | Pending on Customer | <=5 d | 22-Jun-26 | 944000 | 50 | Unit data uploaded to demo, dashboards ready; client UAT, feedback due 23 Jun EOD.
Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking | <=5 d | 07-Jul-26 |  |  | Awaiting customer update on cost sheet; handover call to be scheduled this week.
Voora Developers | Raahul Ramanan R | Pending on Customer | <=5 d | 07-Jul-26 |  |  | Follow-up with AM team on new tasks; plan handover post EPR docs confirmation.
i5 Housing and Properties LLP | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 08-Jul-26 |  |  | WhatsApp integration call scheduled today 3PM. Completed: user/project/report config, routing, Meta, 99Acres, CommonFloor, CP form, trainings.

## 8. Re-grade (value+brand)
Category re-grade - value + licenses + brand/enterprise
Suggested grade = max of value, licence count, and brand/enterprise weight. Under-grading is the concern; higher-than-needed is low priority.
Summary: 6 under-graded (fix), 2 ungraded (set a grade), 0 clearly over-graded (low priority). ~8 A-deals score B on size alone (20-49 lic) - acceptable for enterprise/brand, not listed.
A) UNDER-GRADED - high value/brand but graded low (FIX THESE)
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Dhanraj Realbuild Llp | Venkat Viswavardhan | C | A | 60-90 d | blank | <10/blank |  | billed Rs5-7L
Kohinoor AI Calling | Venkat Viswavardhan | C | B | 60-90 d | blank | <10/blank | Known | known brand
NPS DEVELOPERS | Raahul Ramanan R | C | B | 60-90 d | blank | <10/blank |  | billed Rs3-5L
Shree Honda | Sourabh Sahu | C | B | >180 d | 2-3L | <10/blank |  | billed Rs2.11L
Sujay Global Homes | Venkat Viswavardhan | C | B | 30-60 d | blank | <10/blank |  | billed Rs3-5L
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | C | B | 14-30 d | blank | <10/blank |  | billed Rs2-3L
B) UNGRADED - no category set (assign one)
Includes Krishvi (already Active) and the 'dummy' test record.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Yashoda Infra Developer | Shweta Gouda | C | C | <14 d | blank | >=50 | Yashoda Infra Developer | uncategorized - new deal
Pavani Infra | Shweta Gouda | C | C | 30-60 d | blank | <10/blank |  | no value/licenses captured
C) Clearly over-graded - review (low priority)
B Square is actually live - close it rather than re-grade.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why

## 9. Comparison & Movement
Comparison & Movement vs previous run(s)
Run 7 (Fri 10-Jul-2026) vs 07-Jul & 02-Jul
Deal | Owner | Stage prev->now | Last note prev->now | Movement verdict | Stuck streak | Reason / action
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-07-03 -> 2026-07-03 | Same-blocker | 6 | Still customer-blocked (lead/hierarchy/inventory); project-plan rework pending.
Dhanraj Realbuild Llp | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-03 -> 2026-07-08 | Same-blocker | 6 | Same GRE-form / post-sales dispute; Ankur + customer call again today.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-08 | Same-blocker | 6 | Same GRE-form JIRA deploy blocker, only day-shifted.
Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-03 -> 2026-07-08 | Same-blocker | 6 | Same bulk-outgoing-call issue; 7-Jul call rescheduled again.
Ribitto Private Limited | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-07-06 -> 2026-07-06 | Same-blocker | 6 | Bulk lead + Facebook still pending on customer, unchanged.
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | Same-blocker | 6 | Client still holding implementation until calling integration done.
Times Group | Sanket Nampalliwar | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-22 | Same-blocker | 6 | Still awaiting client UAT feedback on inventory; no movement since June.
Upcurve consumer Technologies Pvt Ltd | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-06-22 -> 2026-06-22 | Same-blocker | 6 | OB still on pause; POC unresponsive.
Voora Developers | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-06-26 -> 2026-07-07 | Same-blocker | 6 | Still awaiting EPR docs / external handover; long-stalled.
Shrimant Developers | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | Same-blocker | 4 | No new note since last run; website integration still the sole open task.
NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-06-26 -> 2026-06-26 | Same-blocker | 2 | No new note since last run; WhatsApp / post-sales re-OB still pending on client details.
SS Salesforce | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-08 | Same-blocker | 2 | No task newly completed; website pending, admin training only scheduled.
Shree Automotive | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-07-07 | Same-blocker | 2 | Mcube setup still not done; only a re-initiation meeting scheduled.
Sujay Global Homes | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-08 | Same-blocker | 2 | Near handover but nothing newly completed; only requesting admin-training slots.
Vascon Engineers | Venkat Viswavardhan | Under Usage Tracking -> Under Usage Tracking | 2026-06-30 -> 2026-07-07 | Same-blocker | 2 | Still awaiting customer cost-sheet feedback; handover call not yet held.
Yula Globas | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-05 -> 2026-07-05 | Same-blocker | 2 | No new note since last run; low usage / IRIS issue persists.
Axon Developer | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-05 -> 2026-07-08 | Same-blocker | 1 | CAPI integration still pending; only a Monday meeting scheduled.
Blueroof India | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | No-touch | 1 | No new note/stage change since 2026-07-06.
Gram Strategic Advisors LLP | Muntazar Mhate | Pending on Customer -> Pending on Customer | 2026-07-06 -> 2026-07-06 | Same-blocker | 1 | No new note since last run; onsite training visit still not scheduled.
Growthx Estates | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | No-touch | 1 | No new note/stage change since 2026-07-06.
Leonaara PVt LTD | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-08 | Same-blocker | 1 | WhatsApp (Interakt) + IVR (Airtel) still pending, now blocked on our end.
Pavani Infra | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-07 | Same-blocker | 1 | Same status: Meta leads blocked on bad date/stage format; website discussion ongoing.
Rajparis Civil Construction | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | No-touch | 1 | No new note/stage change since 2026-07-06.
Real Estate Square | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | Same-blocker | 1 | No new note since last run; bulk lead import still pending.
Red Estate Destination Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | Same-blocker | 1 | No new note since last run; Meta Business verification still awaited.
Salahrealty Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | No-touch | 1 | No new note/stage change since 2026-07-06.
Sangram Group | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | Same-blocker | 1 | No new note since last run; WhatsApp number & bulk lead still pending on customer.
Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | Same-blocker | 1 | No new note since last run; bulk lead + website still pending.
Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | No-touch | 1 | No new note/stage change since 2026-07-06.
Sunrise Housing (GHP Group) | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-06 | No-touch | 1 | No new note/stage change since 2026-07-06.
The Bangalore Real Estate Co. | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-08 | Same-blocker | 1 | Same completed set; website integration still the open gap.
VIVANTA GROUP | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-07 | Same-blocker | 1 | Website & Meta integration still pending; only a call scheduled.
VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-05 -> 2026-07-05 | No-touch | 1 | No new note/stage change since 2026-07-05.
Apex Construction | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-06 -> 2026-07-08 | Progressed | 0 | Workflow-clarity calls completed with client; sales training scheduled Friday.
Apex Realty Hub | Sahil Jane | NEW this run | - -> 2026-07-07 | NEW | 0 | New in pipeline this run.
DhanVed Consultants | Shweta Gouda | Open -> Onboarding In Progress | 2026-07-03 -> 2026-07-07 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Doff Estate | Venkat Viswavardhan | NEW this run | - -> 2026-07-10 | NEW | 0 | New in pipeline this run.
Doff Estate Post Sales | Shubham Dubey | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
Dreamworks Realtors | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-03 -> 2026-07-08 | Progressed | 0 | Channel-partner data imported; now awaiting WhatsApp workflow + inventory from customer.
GGC AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-03 -> 2026-07-08 | Progressed | 0 | Explainer call completed; new ask to connect calls with Highrise CRM (feasibility check).
House of Colours | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-07 | Progressed | 0 | Fresh note: revised sales training + custom sales dashboard completed; 99acres listing IDs requested.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress -> Onboarding In Progress | 2026-06-22 -> 2026-07-07 | Progressed | 0 | Client escalation meeting held (CEO + Siddharth); rollout-timeline concerns & onsite ask raised.
Mythri Builder AI Calling | Venkat Viswavardhan | Onboarding In Progress -> Pending on Customer | 2026-07-03 -> 2026-07-08 | Progressed | 0 | AI-calling feedback implemented & tested; awaiting customer confirmation.
Navkar Realty | Venkat Viswavardhan | Onboarding In Progress -> Pending on Customer | 2026-07-03 -> 2026-07-08 | Progressed | 0 | AI-calling feedback received (was awaited); only WhatsApp template dump now pending on customer.
PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | NEW this run | - -> 2026-07-07 | NEW | 0 | New in pipeline this run.
Palli Developers and Consultants LLP | Muntazar Mhate | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
Properties Boutique | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-05 -> 2026-07-08 | Progressed | 0 | Dialer + sales training now completed (were pending); Meta call still Monday.
Propnsafe Realty LLP | Sahil Jane | NEW this run | - -> 2026-07-07 | NEW | 0 | New in pipeline this run.
SKYTOWN Group | Venkat Viswavardhan | Onboarding In Progress -> Pending on Customer | 2026-07-02 -> 2026-07-08 | Progressed | 0 | Mcube resolved; only inventory + WhatsApp number now pending on customer (file due EOD).
SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-08 | Progressed | 0 | Project file imported (was pending); duplicate-lead-storage requirement raised with dev.
Scanon Realty | Shweta Gouda | NEW this run | - -> 2026-07-08 | NEW | 0 | New in pipeline this run.
Shree Honda | Sourabh Sahu | Pending on Customer -> Onboarding In Progress | 2026-06-22 -> 2026-07-07 | Progressed | 0 | Stage Pending on Customer -> Onboarding In Progress.
Strata Capital Holdings | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-07 | Progressed | 0 | Inventories uploaded, clock-in/out & native WhatsApp now completed.
Supreme Vision Infrabuild Private Limited (Augusta Realty) | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-08 | Progressed | 0 | Lead import completed; Meta integration call scheduled 9th.
Urbanyx Infra | Ganesh Vamsee | NEW this run | - -> 2026-07-10 | NEW | 0 | New in pipeline this run.
VASTU INFINITY AND VENTURES LLP | Sahil Jane | Kickoff Done -> Onboarding In Progress | 2026-07-06 -> 2026-07-08 | Progressed | 0 | Stage Kickoff Done -> Onboarding In Progress.
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Pending on Customer | 2026-07-03 -> 2026-07-10 | Progressed | 0 | Sales training completed; Meta not required, WhatsApp reuse in progress.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-10 | Progressed | 0 | Sales training completed; admin training to be scheduled next week.
YES PROPTECH PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-08 | Progressed | 0 | Near handover; customer raised new lead-import & website-integration asks (details due EOD).
Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-07 | Progressed | 0 | Meta integration now live (lead #215 captured).
i5 Housing and Properties LLP | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-03 -> 2026-07-08 | Progressed | 0 | Meta, 99Acres, CommonFloor, CP form & trainings completed; WhatsApp call today.