## 1. Stats
Sell.do Onboarding Pipeline - Statistics
Pipeline 27474 ¦ 65 open deals ¦ Snapshot 2026-07-20
Ageing = days since deal CREATED (created_at). Movement = days since last activity (separate metric).
By Owner
Category | Count
Sahil Jane | 15
Venkat Viswavardhan | 12
Muntazar Mhate | 12
Shweta Gouda | 9
Raahul Ramanan R | 9
Sanket Nampalliwar | 5
Sourabh Sahu | 3
Total | 65
By Pipeline Stage
Category | Count
Open | 5
Kickoff Done | 2
Onboarding In Progress | 42
Pending on Customer | 16
Under Usage Tracking | 0
Total | 65
Deal Ageing = days since CREATED (created_at)
Category | Count
<14 days | 25
14-30 days | 14
30-60 days | 12
60-90 days | 8
90-180 days | 1
180+ days | 5
Total | 65
Movement = days since LAST ACTIVITY
Category | Count
<=5 days (healthy) | 57
5-7 days | 1
7-15 days | 7
15-30 days | 0
30+ days | 0
Total | 65
Touch cadence = days since LAST NOTE (interim proxy until meetings are logged)
Category | Count
<=5 days (OK) | 54
6-10 days | 1
11-15 days | 7
16-30 days | 0
31+ days | 0
Never (no note) | 3
Total | 65
Meetings ON DEALS (not yet logged - format ready going forward)
Category | Count
Deals with a meeting logged on the deal | 0
Meeting scheduled/conducted within 5 days | 0
NO meeting logged (team to start logging) | 65
Risk & Data-Quality Flags
Category | Count
No activity 5+ days (your risk rule) | 8
No notes logged at all | 3
Target go-live date already breached | 12
Customer 'Yet to sign up' | 6
No future follow-up task | 27
Has an OVERDUE task | 7
Billed Amount field blank | 52
Estimated Value populated | 0
Meetings linked to these onboarding deals | 0

## 2. Exec Summary (CEO-CRO)
Onboarding Pipeline - Executive Summary
For CEO & CRO ¦ 2026-07-20
The headline (movement this run)
61 deals are open in onboarding. Comparing today vs the last run: 20 have GENUINELY PROGRESSED, but 33 have NOT moved (26 restate the same blocker, 7 had no activity at all) and 16 of those have now been stuck for 2+ consecutive runs (SUPER-RED - see Sheet 9); 9 of those have been stuck 6 runs in a row. 8 deals are new this run. 26 deals (43%) are already past their committed go-live date.
Data hygiene is still the structural issue: Billed Amount is blank on 43 of 61 deals (70%), Estimated Value is empty on every deal, 38 of 61 have no next task, and 2 (both new) deals still have zero notes. Note that get_deal_notes returns notes unsorted, so several stale deals' newest note had to be recovered via a larger fetch. Revenue-at-risk remains largely invisible in standard reports.
Where the money is exposed
Cash collected but customer still 'Yet to sign up': Doff Estate Post Sales - Rs5.24L fully received but not activated (new deal this run). Push to sign-up now.
Largest accounts by value: Times Group Rs9.44L (Pending-on-Customer - client UAT feedback overdue since 23-Jun, stuck 6 runs), Doff Estate & Doff Estate Post Sales Rs5.24L each (new, Open), SKYTOWN Rs5.0L (moved to Pending-on-Customer), Navkar Rs4.96L (Pending-on-Customer). Largest by licences: Kunwarji Realtors - 150 licences, Category A, go-live breached; client escalated rollout delays on 3-Jul in a meeting with the CEO and requested onsite support.
What we are asking leadership to back
1. A weekly onboarding hygiene standard: every open deal must have a LOGGED MEETING (scheduled or conducted) at least every 5 days, a dated note, and a next task; stage moved at each milestone. (Meetings are still not logged on deals at all.)
2. Make Billed Amount mandatory at deal creation so revenue-at-risk is visible (blank on 78% today).
3. A weekly SUPER-RED review: 16 deals have not genuinely moved for 2+ runs (9 of them for 6 runs straight) - most are stuck 'pending on customer'. Set drop-dead dates or move to HOLD.
4. A 'collections + activation' sweep on the paid-but-dormant accounts above (CRO + Onboarding).

## 3. Owner Scorecard
Owner Scorecard - gaps for the Onboarding Head
Counts per owner across the key risk flags. Use for owner 1:1s.
Owner | Open deals | A-grade | Idle 5+ d | No notes | Go-live overdue | Not signed up | No next task | Overdue task | Key gap to address
Sahil Jane | 15 | 1 | 0 | 1 | 5 | 2 | 3 | 0 | 15 deal(s). no notes: Makliv Infra Consulting Pvt Ltd..
Venkat Viswavardhan | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 12 deal(s). pending-on-customer: Doff Estate, SKYTOWN Group, Navkar Realty, VAZHRAA NIRMAAN PRIVATE LIMITED, GGC AI Calling, Mythri Builder AI Calling.
Muntazar Mhate | 12 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 12 deal(s). pending-on-customer: Rajparis Civil Construction, Sohum Estate Agency (Sameer Chheda), Sangram Group, Shri Krish Housing and Properties Pvt Ltd, Ribitto Private Limited.
Shweta Gouda | 9 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 9 deal(s). no notes: KL HOMES.
Raahul Ramanan R | 9 | 4 | 1 | 1 | 2 | 1 | 6 | 1 | 9 deal(s). no notes: SPR Construction Pvt Ltd (leasing team). pending-on-customer: Calicut Landmark Builders Pvt. Ltd, Voora Developers.
Sanket Nampalliwar | 5 | 2 | 5 | 0 | 3 | 2 | 3 | 2 | 5 deal(s). pending-on-customer: Times Group.
Sourabh Sahu | 3 | 1 | 2 | 0 | 1 | 0 | 3 | 0 | 3 deal(s).
TOTAL | 65 | 12 | 8 | 3 | 12 | 6 | 27 | 7

## 4. Deal-Level Tracker
Deal-Level Tracker - for the Onboarding Head to action
Cols E-F = movement vs the LAST run: Progressed / NEW / STUCK (same blocker or no activity). Stuck deals are grouped at the top. SUPER-RED = no genuine movement for 2+ consecutive runs.
Deal ID | Deal Name | Owner | Stage | Moved? (vs last run) | Movement detail (prev -> now) | Last activity | Last note date | Days since note | Has notes | Go-live overdue | Not signed up | Billed (Rs) | Licenses | Cat | Last note / status | Age (created) | Key Next Step (recommended) | Touch cadence (interim, vs 5d) | Last meeting | Next meeting | Mtg <=5d?
4299438 | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | SUPER-RED (9 runs stuck) | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-07-14 -> 2026-07-20 ¦ Moved into Pending; transactional email still broken, sales training still deferred behind it. [stuck x9] | <=5 d | 20-Jul-26 | 0 | Yes |  |  | 74240 | 6 | C | Mailgun promotional emails working, transactional broken; Sales Training deferred until email issue fixed. | 30-60 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4255681 | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | SUPER-RED (9 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-13 -> 2026-07-17 ¦ Calling-integration blocker persists; now escalated to Ketan - escalation is not resolution. [stuck x9] | <=5 d | 17-Jul-26 | 3 | Yes | Yes |  | 14660 | 41 | A | Weekly tasks on calling-integration timelines/delays marked done; Sanket to talk to Ketan. | 60-90 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
3575524 | Voora Developers | Raahul Ramanan R | Pending on Customer | SUPER-RED (9 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-13 -> 2026-07-17 ¦ Same blockers: balance payment + Manoj's pointers, still awaited. [stuck x9] | <=5 d | 17-Jul-26 | 3 | Yes | Yes |  | 785880 | 21 | A | Pushing online vs onsite meeting tied to balance payment; Amit following up on partial payment; awaiting client acknowledgement on Manoj's pointers. | >180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4144089 | Dhanraj Realbuild Llp | Venkat Viswavardhan | Pending on Customer | SUPER-RED (9 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-11 -> 2026-07-19 ¦ Refund/churn risk deepening; customer refuses AI-calling, wants unavailable sourcing changes. [stuck x9] | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 538552 | 6 | C | Customer refuses AI-calling discussion, wants unavailable sourcing changes; checking with Siddharth (refund risk). | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. (re-grade to A) | OK (<=5d) | None logged | None logged | No - none logged
4233715 | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | SUPER-RED (9 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-11 -> 2026-07-19 ¦ AI-calling still blocked (ESTATE-21040 / SS-12176); only a call being scheduled. [stuck x9] | <=5 d | 19-Jul-26 | 1 | Yes |  |  |  | 2 | C | Schedule call to discuss customer pointers (dependent on Sharayu/customer availability). | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4177642 | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | SUPER-RED (5 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-08 -> 2026-07-17 ¦ Owner states nothing moved this week; escalated to sales. [stuck x5] | <=5 d | 17-Jul-26 | 3 | Yes |  |  | 428104 | 11 | C | Nothing moved this week; escalate to sales for help; admin-training follow-ups; Kylas to be updated. | 60-90 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4345401 | Sangram Group | Muntazar Mhate | Pending on Customer | SUPER-RED (4 runs stuck) | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-07-14 -> 2026-07-20 ¦ Moved into Pending; on-hold email sent; sales training only assured for Monday. [stuck x4] | <=5 d | 20-Jul-26 | 0 | Yes |  |  |  | 5 | C | Pending pointers followed up; customer still hasn't shared fresh WhatsApp number - account-on-hold email sent; client assured Sales Training Monday. | 30-60 d | Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4370391 | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | SUPER-RED (4 runs stuck) | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-07-14 -> 2026-07-17 ¦ Moved into Pending; inventory-layout demo slipped (client unavailable). [stuck x4] | <=5 d | 17-Jul-26 | 3 | Yes |  |  |  | 6 | C | Custom fields set up; inventory-layout demo not done (client team unavailable); movement expected after inventory demo, client available Monday. | 30-60 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4389699 | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | SUPER-RED (4 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-12 -> 2026-07-19 ¦ WhatsApp Interakt still pending on dev; trainings only scheduled, not done. [stuck x4] | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 129800 | 6 | C | Weekly update: Jiras raised for calling-logs and Interakt WhatsApp issues (done); this week sales and tentative admin training; WhatsApp Interakt integration still pending on dev team. | 30-60 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4375201 | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-13 -> 2026-07-18 ¦ Mcube still blocked (recordings not captured); raised to vendor, client waiting. [stuck x3] | <=5 d | 18-Jul-26 | 2 | Yes | Yes |  |  | 2 | Broker | MCube testing blocked - calls initiate but recordings not captured; issue raised to MCube team; client will proceed with integrations once resolved. | 30-60 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4241966 | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-11 -> 2026-07-17 ¦ Still only arranging a call; AI-calling adoption not started. [stuck x3] | <=5 d | 17-Jul-26 | 3 | Yes |  |  |  | 2 | C | Arranging a call between customer, Vinay and Siddharth; checking availability. | 60-90 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | OK (<=5d) | None logged | None logged | No - none logged
4233760 | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-11 -> 2026-07-19 ¦ Still awaiting BOT feedback/adoption; now via a new POC (SS-12285). [stuck x3] | <=5 d | 19-Jul-26 | 1 | Yes |  |  |  | 2 | C | Connect with new POC for BOT feedback and push adoption. | 60-90 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4402389 | Navkar Realty | Venkat Viswavardhan | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-16 -> 2026-07-19 ¦ No progress - customer POC on sick leave; all items pushed to next week. [stuck x3] | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 495600 | 4 | C | Customer (Sahil) on sick leave last week; next week check availability, schedule AI-bot feedback call, follow up on CP form. | 30-60 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4370308 | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Pending on Customer | SUPER-RED (3 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-11 -> 2026-07-17 ¦ Admin training restated as awaiting customer availability - same ask. [stuck x3] | <=5 d | 17-Jul-26 | 3 | Yes |  |  | 243080 | 6 | C | Awaiting customer availability for Admin Training; to schedule next week then handover. | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. (re-grade to B) | OK (<=5d) | None logged | None logged | No - none logged
4402374 | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-10 -> 2026-07-19 ¦ Admin training still only being scheduled a week later - scheduled != done. [stuck x3] | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 350000 | 15 | B | Admin Training to be scheduled per customer availability, then handover. | 30-60 d | New onboarding deal - log kickoff note + set next task. | OK (<=5d) | None logged | None logged | No - none logged
4449587 | Rajparis Civil Construction | Muntazar Mhate | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-07-14 -> 2026-07-20 ¦ Moved into Pending; AiSensy + inventory + cost sheet all awaited from client. [stuck x2] | <=5 d | 20-Jul-26 | 0 | Yes |  |  | 300000 | 15 | B | AiSensy WhatsApp pending client/AiSensy (setup ready our end); inventory & cost sheet awaited from client; SV/CP forms and sales training tentative. | 14-30 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4336926 | Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Pending on Customer | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Pending on Customer ¦ Note 2026-07-14 -> 2026-07-17 ¦ Account already live last week; only Facebook added; moved into Pending with hold threat. [stuck x2] | <=5 d | 17-Jul-26 | 3 | Yes |  |  | 532180 | 10 | C | Sales Training done, account live; Facebook integration done; Prabhu on-site working with client; hold threatened if no update after 3 follow-ups. | 30-60 d | Chase kickoff slot; escalate to customer exec if no response in 5 days. | OK (<=5d) | None logged | None logged | No - none logged
4479599 | Propnsafe Realty LLP | Sahil Jane | Kickoff Done | SUPER-RED (2 runs stuck) | Stage Kickoff Done -> Kickoff Done ¦ Note 2026-07-12 -> 2026-07-19 ¦ Still in Kickoff Done; core setup gated on website + lead import; fancy number is a side item. [stuck x2] | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 172516 | 3 | C | WhatsApp (awaiting fancy number) and Meta (no active forms) unfinished; fancy number now received; Mcube pending website; project, lead import and trainings pending. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
3968505 | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-11 -> 2026-07-19 ¦ Still awaiting Sourcing rework from dev (ETA 29 Jul); customer un-progressed. [stuck x2] | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 481440 | 40 | A | Update shared with dev team, ETA 29 Jul; re-walk customer through Sourcing. | 90-180 d | Past target go-live - re-baseline date; Get the one pending input from customer (data/slot/feedback), then close remaining setup. | OK (<=5d) | None logged | None logged | No - none logged
4435090 | SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-11 -> 2026-07-19 ¦ Owner notes little concrete movement; trainings pending client availability. [stuck x2] | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 258420 | 35 | Broker | Only a next-week note: sales & admin training pending on client availability; little concrete movement. | 14-30 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
4482197 | Scanon Realty | Shweta Gouda | Onboarding In Progress | STUCK - same blocker | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-18 ¦ Sales training rescheduled again on client unavailability - repeat slip. [stuck x1] | <=5 d | 18-Jul-26 | 2 | Yes |  |  | 11328 | 2 | Broker | Sales training rescheduled again due to client unavailability; core setup and lead import done; integrations not required (manual leads). | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4482302 | Doff Estate | Venkat Viswavardhan | Pending on Customer | STUCK - same blocker | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-12 -> 2026-07-19 ¦ Only a next-week plan (lead import 20th, training, IVR follow-up); nothing completed this week. [stuck x1] | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 523919 | 29 | A | Next week: complete bulk lead import on 20th July, arrange sales training, follow up on IVR integration. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4446753 | SKYTOWN Group | Venkat Viswavardhan | Pending on Customer | STUCK - same blocker | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-16 -> 2026-07-19 ¦ Restated: sales training done last week, onsite Wed, still awaiting WhatsApp number. [stuck x1] | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 733488 | 20 | A | Sales training done; onsite visit scheduled Wed; admin training, Q&A and WhatsApp integration pending (awaiting WhatsApp number from client). | 14-30 d | New deal - log first onboarding note / confirm kickoff. | OK (<=5d) | None logged | None logged | No - none logged
3302998 | Times Group | Sanket Nampalliwar | Pending on Customer | SUPER-RED (9 runs stuck) | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-07 -> 2026-07-07 ¦ No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review. | 7-15 d | 07-Jul-26 | 13 | Yes |  |  | 944000 | 50 | A | Data uploaded but client reports discrepancies; internal validation meeting 7 Jul; only formula fields and roles/access pending. | >180 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | Stale | None logged | None logged | No - none logged
3304062 | Shree Automotive | Sourabh Sahu | Onboarding In Progress | SUPER-RED (5 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-07 -> 2026-07-07 ¦ No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review. | 7-15 d | 07-Jul-26 | 13 | Yes |  |  | 104784 | 4 | C | Meeting set 8 Jul with POC/Director to reinitiate OB and finalize plan. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. | Stale | None logged | None logged | No - none logged
4230613 | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-07 -> 2026-07-07 ¦ No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review. | 7-15 d | 07-Jul-26 | 13 | Yes | Yes |  | 1428980 | 150 | A | Client escalated rollout delays, wants 3-5 day onsite; JIRAs (incl mobile) to deploy by 15 Jul; targeting completion end-Jul/early-Aug. | 60-90 d | No record in weeks - owner to log status + set next task TODAY; likely escalate. | Stale | None logged | None logged | No - none logged
3304063 | Shree Honda | Sourabh Sahu | Onboarding In Progress | SUPER-RED (3 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-07 -> 2026-07-07 ¦ No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review. | 7-15 d | 07-Jul-26 | 13 | Yes |  |  | 210984 | 5 | C | Meeting set 8 Jul with POC/Director to reinitiate OB and finalize plan. | >180 d | Re-confirm the customer blocker; set a drop-dead date or move to 'On Hold'. (re-grade to B) | Stale | None logged | None logged | No - none logged
4494717 | Sell.do test | Sanket Nampalliwar | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note 2026-07-09 -> 2026-07-09 ¦ No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review. | 7-15 d | 09-Jul-26 | 11 | Yes |  |  |  | 6 | Push to OB | Kickoff/discovery note for ABC Realty (Pune developer): fast-track 5-day go-live, wants centralized leads, WhatsApp and website/Meta integration. | <14 d | Log first note + confirm kickoff / next milestone. | Stale | None logged | None logged | No - none logged
4475303 | test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note 2026-07-06 -> 2026-07-06 ¦ No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review. | 7-15 d | 06-Jul-26 | 14 | Yes | Yes | Yes | 1233 | 12 | Push to OB | Test note ('test 3'). | 14-30 d | Log first note + confirm kickoff / next milestone. | Stale | None logged | None logged | No - none logged
4475289 | test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | SUPER-RED (2 runs stuck) | Stage Open -> Open ¦ Note 2026-07-06 -> 2026-07-06 ¦ No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review. | 7-15 d | 06-Jul-26 | 14 | Yes | Yes | Yes | 1233 | 12 | Push to OB | Test/dummy deal (Push to OB); only a 'test 3' note, no real onboarding content. | 14-30 d | Log first note + confirm kickoff / next milestone. | Stale | None logged | None logged | No - none logged
4337048 | i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | SUPER-RED (2 runs stuck) | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-11 -> 2026-07-11 ¦ No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review. | <=5 d | 10-Jul-26 | 9 | Yes | Yes |  | 347156 | 18 | A | Inventory upload in progress; customer to update pending items (bulk lead import, website, WhatsApp number, property portals) by 11th EOD. | 30-60 d | Force sign-up/activation - paid but 'Yet to sign up'; escalate to customer exec. | Watch | None logged | None logged | No - none logged
4510192 | SPR Construction Pvt Ltd (leasing team) | Raahul Ramanan R | Onboarding In Progress | No-activity | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> no note ¦ No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review. | 5-7 d |  |  | No |  |  | 735376 | 17 | A |  | <14 d | Log first note + confirm kickoff / next milestone. | No note | None logged | None logged | No - none logged
3317883 | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 20-Jul-26 | 0 | Yes |  |  | 174862 | 4 | C | Status recap: accounts/project/routing/99acres done; Facebook, Mcube, trainings, website, data migration pending; new tasks discussed. | >180 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4535312 | ACL INFRATECH PRIVATE LIMITED (LOVE HOME LLP) | Sahil Jane | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 121000 | 10 | C | Users/projects/reports done; this week focus Meta + bulk lead import + sales/presales training; 99acres, inventory, dialer, admin training pending. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4437383 | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 20-Jul-26 | 0 | Yes | Yes |  | 120336 | 5 | C | Account was on hold; resuming - sales training scheduled Tuesday 11:00 AM. | 14-30 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4535079 | BRICKSAGE PROPERTIES ADVISORS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 106200 | 15 | B | Users/projects/reports done; this week Meta + bulk lead import + training; MagicBricks email initiated, dialer/inventory/admin training pending. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4545857 | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  | Yes | 11232 | 7 | C |  | <14 d | Log first note + confirm kickoff / next milestone. | No note | None logged | None logged | No - none logged
4368709 | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 20-Jul-26 | 0 | Yes | Yes | Yes |  | 5 | C | Account was on hold; onboarding to start from today. | 30-60 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4538512 | KL HOMES | Shweta Gouda | Open | NEW this run | New in pipeline this run. | <=5 d |  |  | No |  | Yes | 65233 | 2 | Broker |  | <14 d | Log first note + confirm kickoff / next milestone. | No note | None logged | None logged | No - none logged
4535970 | Primeplus Realtech Llp | Venkat Viswavardhan | Onboarding In Progress | NEW this run | New in pipeline this run. | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 95000 | 20 | A | Next-week plan: activate users, add projects, send emails for website & property-portal integration, integrate Meta, chase IVR update. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4412002 | Blueroof India | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-18 ¦ Setup, Meta, inventory, bulk import, admin + mobile sales training completed. | <=5 d | 17-Jul-26 | 2 | Yes |  |  | 14160 | 2 | Broker | Setup, Meta, inventory, bulk import, admin + mobile sales training done; website + YouTube pending client; laptop sales training next week. | 14-30 d | Priority tasks shared — progress integrations. | OK (<=5d) | None logged | None logged | No - none logged
4531331 | Emerald Blue | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-16 -> 2026-07-17 ¦ Core setup (users/projects/reports/routing) completed; trainings pending. | <=5 d | 17-Jul-26 | 3 | Yes |  |  | 11328 | 2 | Broker | Users/projects/reports/routing done; bulk lead import, sales & admin training pending/to be scheduled; most integrations marked not required. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4457232 | Growthx Estates | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-18 ¦ Meta, 99acres, offline dialer and sales training (laptop+mobile) completed. | <=5 d | 17-Jul-26 | 2 | Yes |  |  | 118000 | 10 | Broker | Meta, 99acres, offline dialer, laptop+mobile sales training done; bulk import, Google Ads, website initiated, admin training pending. | 14-30 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4508480 | MSK Realty | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Kickoff Done -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-20 ¦ Stage Kickoff Done -> Onboarding In Progress. | <=5 d | 20-Jul-26 | 0 | Yes |  |  | 68440 | 3 | C | Account setup, GPS and clock-in done; bulk lead import, Meta, website, landing pages, native WhatsApp and trainings all pending. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4480069 | Palli Developers and Consultants LLP | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-17 ¦ 99 Acres property portal integration completed. | <=5 d | 17-Jul-26 | 3 | Yes |  |  | 153400 | 5 | C | Weekly update: 99 Acres property portal integration completed. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4472721 | Salah Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-17 ¦ Inventory follow-up completed; admin training slipped on client hardware issue. | <=5 d | 17-Jul-26 | 3 | Yes |  |  | 28792 | 2 | Broker | Inventory follow-up done; admin training not done - client facing laptop/hardware issue. | 14-30 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4430582 | Sunrise Housing (GHP Group) | Muntazar Mhate | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-17 ¦ Setup, routing, IVR, offline dialer, SV form and laptop sales training completed. | <=5 d | 17-Jul-26 | 3 | Yes |  |  | 236000 | 11 | B | Setup, routing, IVR, offline dialer, SV form, laptop sales training done; bulk import, Meta, website, native WhatsApp, mobile training + admin pending. | 14-30 d | New deal — kickoff + sign-up; no notes yet, log first status. | OK (<=5d) | None logged | None logged | No - none logged
4255693 | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | Progressed | Stage Pending on Customer -> Pending on Customer ¦ Note 2026-07-08 -> 2026-07-17 ¦ Multiple items completed (WhatsApp templates, hierarchy, inventory, booking form, cost sheets, payment schedule); only trainings left. | <=5 d | 17-Jul-26 | 3 | Yes |  |  | 627760 | 36 | A | Last week's tasks done (WhatsApp templates, hierarchy, inventory, booking form, cost sheets, payment schedule, timesheet); Manager and Admin Training followed up. | 60-90 d | Past target go-live - re-baseline date; Complete pending setup items and progress toward handover. | OK (<=5d) | None logged | None logged | No - none logged
4510214 | MiCasa Realty | Raahul Ramanan R | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-13 -> 2026-07-20 ¦ Core setup, routing, lead import, website, inventory completed; Mcube awaiting vendor. | <=5 d | 20-Jul-26 | 0 | Yes |  |  | 82000 | 5 | C | Core setup, routing, lead import, website and inventory done; Mcube telephony awaiting vendor; Meta and trainings pending. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4510245 | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note no note -> 2026-07-20 ¦ Account/team setup completed (1 user pending activation); integrations pending client. | <=5 d | 20-Jul-26 | 0 | Yes |  |  | 81184 | 4 | C | Account/team setup done; one user not activated; routing, lead import and all integrations pending on client POC details and call scheduling. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4510267 | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-07-20 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 20-Jul-26 | 0 | Yes |  | Yes |  | 18 | B | Account created; user creation/activation in progress (reminders resent); team/hierarchy/pipeline awaiting client; lead import & inventory calls rescheduled twice; many integrations emailed POCs awaiting update; trainings after basic setup. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4479594 | Apex Realty Hub | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-13 -> 2026-07-19 ¦ Sales and admin training both completed; Meta/WA on hold on client Meta account. | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 81420 | 5 | C | Meta and WhatsApp on hold pending client Meta account; sales and admin training done; integrations to complete if Meta account created this week. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4389674 | Axon Developer | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-12 -> 2026-07-19 ¦ Facebook CAPI and usage check completed; handover doc in preparation. | <=5 d | 19-Jul-26 | 1 | Yes | Yes |  | 450000 | 30 | A | Weekly: Facebook CAPI done, account-usage check done, IVR follow-up initiated, handover doc being prepared; Gupshup WhatsApp and workflow still pending API changes. | 30-60 d | Log first status note and book kickoff; set a next task. | OK (<=5d) | None logged | None logged | No - none logged
4458749 | Properties Boutique | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-13 -> 2026-07-19 ¦ Handover and Q&A completed, account live - effectively wrapped. | <=5 d | 19-Jul-26 | 1 | Yes | Yes |  | 61360 | 7 | C | Account live in OB, handover + Q&A completed; only Meta integration call pending (Monday) - effectively wrapped. | 14-30 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4515897 | R J Real Tech and Properties Pvt Ltd | Sahil Jane | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-07-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 125080 | 8 | C | Users/projects/reports done; this week Meta + bulk lead import + sales training; Facebook, inventory, website, admin training pending. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4516021 | RUBRICK CONSTRUCTIONS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-07-19 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 693840 | 7 | C | Users/projects/reports done; this week Meta + WhatsApp; Google Ads, bulk lead import, dialer, training pending; post-sales/inventory handled by Shubham Dube. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4510268 | SHREYA CAPITAL ADVISORY SERVICES LLP | Sahil Jane | Kickoff Done | Progressed | Stage Kickoff Done -> Kickoff Done ¦ Note no note -> 2026-07-19 ¦ First note logged; users/projects/reports completed; Meta+website upcoming. | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 389400 | 5 | C | Users/projects/reports done; upcoming Meta + website + tentative lead import/inventory (awaiting files); WATI on hold due to account issues. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4458766 | VASTU INFINITY AND VENTURES LLP | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-13 -> 2026-07-19 ¦ Admin training completed, account live in OB, handover planned this week. | <=5 d | 19-Jul-26 | 1 | Yes |  |  | 33000 | 5 | C | Admin training done, account made live in OB, handover planned this week; Meta integration on hold (POC away 2 weeks). | 14-30 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4458771 | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-19 ¦ Facebook and SV form completed; sales training scheduled Wed. | <=5 d | 19-Jul-26 | 1 | Yes | Yes |  | 241900 | 8 | C | Facebook + SV form completed; native WhatsApp on hold per client; sales training scheduled Wednesday; dialer + trainings pending. | 14-30 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4511483 | GAGAN TONDON | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-18 ¦ Users/projects/reports/99acres/MagicBricks completed; lead import waiting on customer. | <=5 d | 18-Jul-26 | 2 | Yes |  |  | 80830 | 9 | Broker | Last week users/projects/reports/99acres/MagicBricks done, lead import waiting on customer; this week Interakt WhatsApp, sales & admin training, handover targeted. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4478489 | PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-13 -> 2026-07-18 ¦ Lead import completed; native WhatsApp awaiting client number. | <=5 d | 18-Jul-26 | 2 | Yes |  |  | 326860 | 5 | C | Lead import done; native WhatsApp awaiting client number; 99 acres and website API details shared; sales training pending. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4511499 | Sunita real estate | Shweta Gouda | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note no note -> 2026-07-18 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 18-Jul-26 | 2 | Yes |  |  |  | 4 | Broker | Last week users/projects/reports/leads/99acres done; this week inventory upload (pending client file), sales training, dialer setup. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4499510 | Sunny Developers & Realtors | Shweta Gouda | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note 2026-07-10 -> 2026-07-18 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 18-Jul-26 | 2 | Yes |  |  |  | 6 | C | Users, project, lead import, pipeline, reports and Meta done; this week targeting Exotel, Google ads and website (awaiting client), then sales training. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4514062 | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | Progressed | Stage Open -> Onboarding In Progress ¦ Note 2026-07-14 -> 2026-07-16 ¦ Stage Open -> Onboarding In Progress. | <=5 d | 16-Jul-26 | 4 | Yes |  |  | 17700 | 2 | Broker | This week targeting lead import and sales training. | <14 d | Log first note + confirm kickoff / next milestone. | OK (<=5d) | None logged | None logged | No - none logged
4438366 | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | Progressed | Stage Onboarding In Progress -> Onboarding In Progress ¦ Note 2026-07-13 -> 2026-07-18 ¦ Native WhatsApp (the prior blocker) completed; trainings slipped to next week. | <=5 d | 18-Jul-26 | 2 | Yes |  |  |  | 3 | C | Native WhatsApp done; sales & admin training slipped to next week; website + Housing integration pending on client. | 14-30 d | New deal; categorize the account and log first onboarding note. | OK (<=5d) | None logged | None logged | No - none logged

## 5. Large-Stuck-Attention
Large deals, Stuck deals & Deals needing attention - for everyone
A) LARGE DEALS (value / licenses) - protect these
Deal | Owner | Stage | Billed (Rs) | Licenses | Cat | Status / note
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | 1428980 | 150 | A | Client escalated rollout delays, wants 3-5 day onsite; JIRAs (incl mobile) to deploy by 15 Jul; targeting completion end-Jul/early-Aug.
Times Group | Sanket Nampalliwar | Pending on Customer | 944000 | 50 | A | Data uploaded but client reports discrepancies; internal validation meeting 7 Jul; only formula fields and roles/access pending.
Voora Developers | Raahul Ramanan R | Pending on Customer | 785880 | 21 | A | Pushing online vs onsite meeting tied to balance payment; Amit following up on partial payment; awaiting client acknowledgement on Manoj's pointers.
SKYTOWN Group | Venkat Viswavardhan | Pending on Customer | 733488 | 20 | A | Sales training done; onsite visit scheduled Wed; admin training, Q&A and WhatsApp integration pending (awaiting WhatsApp number from client).
SPR Construction Pvt Ltd (leasing team) | Raahul Ramanan R | Onboarding In Progress | 735376 | 17 | A
RUBRICK CONSTRUCTIONS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | 693840 | 7 | C | Users/projects/reports done; this week Meta + WhatsApp; Google Ads, bulk lead import, dialer, training pending; post-sales/inventory handled by Shubham Dube.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | 627760 | 36 | A | Last week's tasks done (WhatsApp templates, hierarchy, inventory, booking form, cost sheets, payment schedule, timesheet); Manager and Admin Training followed up.
Doff Estate | Venkat Viswavardhan | Pending on Customer | 523919 | 29 | A | Next week: complete bulk lead import on 20th July, arrange sales training, follow up on IVR integration.
Dhanraj Realbuild Llp | Venkat Viswavardhan | Pending on Customer | 538552 | 6 | C | Customer refuses AI-calling discussion, wants unavailable sourcing changes; checking with Siddharth (refund risk).
Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Pending on Customer | 532180 | 10 | C | Sales Training done, account live; Facebook integration done; Prabhu on-site working with client; hold threatened if no update after 3 follow-ups.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | 481440 | 40 | A | Update shared with dev team, ETA 29 Jul; re-walk customer through Sourcing.
Navkar Realty | Venkat Viswavardhan | Pending on Customer | 495600 | 4 | C | Customer (Sahil) on sick leave last week; next week check availability, schedule AI-bot feedback call, follow up on CP form.
Axon Developer | Sahil Jane | Onboarding In Progress | 450000 | 30 | A | Weekly: Facebook CAPI done, account-usage check done, IVR follow-up initiated, handover doc being prepared; Gupshup WhatsApp and workflow still pending API changes.
NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | 428104 | 11 | C | Nothing moved this week; escalate to sales for help; admin-training follow-ups; Kylas to be updated.
SHREYA CAPITAL ADVISORY SERVICES LLP | Sahil Jane | Kickoff Done | 389400 | 5 | C | Users/projects/reports done; upcoming Meta + website + tentative lead import/inventory (awaiting files); WATI on hold due to account issues.
i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | 347156 | 18 | A | Inventory upload in progress; customer to update pending items (bulk lead import, website, WhatsApp number, property portals) by 11th EOD.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 350000 | 15 | B | Admin Training to be scheduled per customer availability, then handover.
PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Onboarding In Progress | 326860 | 5 | C | Lead import done; native WhatsApp awaiting client number; 99 acres and website API details shared; sales training pending.
Rajparis Civil Construction | Muntazar Mhate | Pending on Customer | 300000 | 15 | B | AiSensy WhatsApp pending client/AiSensy (setup ready our end); inventory & cost sheet awaited from client; SV/CP forms and sales training tentative.
SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 258420 | 35 | Broker | Only a next-week note: sales & admin training pending on client availability; little concrete movement.
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | 14660 | 41 | A | Weekly tasks on calling-integration timelines/delays marked done; Sanket to talk to Ketan.
B) STUCK DEALS (30+ days idle, or notes say 'no movement / on hold / call rescheduled')
Deal | Owner | Stage | Last note | Idle | Status / note
STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | 20-Jul-26 | <=5 d | Account created; user creation/activation in progress (reminders resent); team/hierarchy/pipeline awaiting client; lead import & inventory calls rescheduled twice; many integrations emailed POCs awaiting update; trainings after basic setup.
Veedhan Buildtech | Sahil Jane | Onboarding In Progress | 20-Jul-26 | <=5 d | Account was on hold; onboarding to start from today.
Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | 20-Jul-26 | <=5 d | Account was on hold; resuming - sales training scheduled Tuesday 11:00 AM.
Apex Realty Hub | Sahil Jane | Onboarding In Progress | 19-Jul-26 | <=5 d | Meta and WhatsApp on hold pending client Meta account; sales and admin training done; integrations to complete if Meta account created this week.
VASTU INFINITY AND VENTURES LLP | Sahil Jane | Onboarding In Progress | 19-Jul-26 | <=5 d | Admin training done, account made live in OB, handover planned this week; Meta integration on hold (POC away 2 weeks).
VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | 19-Jul-26 | <=5 d | Facebook + SV form completed; native WhatsApp on hold per client; sales training scheduled Wednesday; dialer + trainings pending.
SHREYA CAPITAL ADVISORY SERVICES LLP | Sahil Jane | Kickoff Done | 19-Jul-26 | <=5 d | Users/projects/reports done; upcoming Meta + website + tentative lead import/inventory (awaiting files); WATI on hold due to account issues.
Scanon Realty | Shweta Gouda | Onboarding In Progress | 18-Jul-26 | <=5 d | Sales training rescheduled again due to client unavailability; core setup and lead import done; integrations not required (manual leads).
C) NEEDS ATTENTION (paid but 'Yet to sign up', or large + go-live breached)
Deal | Owner | Stage | Billed (Rs) | Signed up? | Go-live overdue | Status / note
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | 1428980 | - | Yes | Client escalated rollout delays, wants 3-5 day onsite; JIRAs (incl mobile) to deploy by 15 Jul; targeting completion end-Jul/early-Aug.
Voora Developers | Raahul Ramanan R | Pending on Customer | 785880 | - | Yes | Pushing online vs onsite meeting tied to balance payment; Amit following up on partial payment; awaiting client acknowledgement on Manoj's pointers.
Axon Developer | Sahil Jane | Onboarding In Progress | 450000 | - | Yes | Weekly: Facebook CAPI done, account-usage check done, IVR follow-up initiated, handover doc being prepared; Gupshup WhatsApp and workflow still pending API changes.
i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | 347156 | - | Yes | Inventory upload in progress; customer to update pending items (bulk lead import, website, WhatsApp number, property portals) by 11th EOD.
KL HOMES | Shweta Gouda | Open | 65233 | Yet to sign up
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | 14660 | - | Yes | Weekly tasks on calling-integration timelines/delays marked done; Sanket to talk to Ketan.
Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | 11232 | Yet to sign up
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | 1233 | Yet to sign up | Yes | Test note ('test 3').
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open | 1233 | Yet to sign up | Yes | Test/dummy deal (Push to OB); only a 'test 3' note, no real onboarding content.
Veedhan Buildtech | Sahil Jane | Onboarding In Progress |  | Yet to sign up | Yes | Account was on hold; onboarding to start from today.

## 6. Pending-on-Customer Check
'Pending on Customer' validation - is it really moving?
16 deals sit in this stage. Verdict from last 2-3 notes + activity.
Deal | Owner | Last note | Days since | Verdict | Clear next action
Doff Estate | Venkat Viswavardhan | 19-Jul-26 | 1 | Unknown | Owner to log status + next step immediately.
Rajparis Civil Construction | Muntazar Mhate | 20-Jul-26 | 0 | Unknown | Owner to log status + next step immediately.
Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | 17-Jul-26 | 3 | Unknown | Owner to log status + next step immediately.
Sangram Group | Muntazar Mhate | 20-Jul-26 | 0 | Unknown | Owner to log status + next step immediately.
Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | 17-Jul-26 | 3 | Unknown | Owner to log status + next step immediately.
Ribitto Private Limited | Muntazar Mhate | 20-Jul-26 | 0 | STUCK | No genuine note movement in 3 runs; pending bulk lead + FB from customer. Escalate / chase lead file.
Dhanraj Realbuild Llp | Venkat Viswavardhan | 19-Jul-26 | 1 | STUCK | Customer unhappy vs sales promises, possible refund case. Needs Ankur/sales call now.
Voora Developers | Raahul Ramanan R | 17-Jul-26 | 3 | STUCK | Voora: pending EPR docs + external handover since Feb. Escalate.
Mythri Builder AI Calling | Venkat Viswavardhan | 19-Jul-26 | 1 | Stalled | Awaiting flow + feedback from customer on AI calling. Set a deadline.
Navkar Realty | Venkat Viswavardhan | 19-Jul-26 | 1 | Customer-blocked | Customer asked to hold till 13-Jul; pending details due today. Chase today or escalate to sales.
Times Group | Sanket Nampalliwar | 07-Jul-26 | 13 | Customer-blocked | Times: client reported data discrepancies; review meeting rescheduled. Fix a date.
GGC AI Calling | Venkat Viswavardhan | 17-Jul-26 | 3 | Moving slowly | AI calling: pushing Netram for outgoing calls; no customer confirmation yet.
Kohinoor AI Calling | Venkat Viswavardhan | 19-Jul-26 | 1 | Moving slowly | Outgoing-calling issues raised; JIRA open (ESTATE-21040). Track ETA.
SKYTOWN Group | Venkat Viswavardhan | 19-Jul-26 | 1 | Moving | Inventory uploaded; only WhatsApp number pending from client. Chase number, then close.
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | 17-Jul-26 | 3 | Moving | Sales training done; admin training to be scheduled. Book the date.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | 17-Jul-26 | 3 | Moving | Calicut: Q&A + mobile + admin training 2.0 planned this week.

## 7. Customer Category
Customer Category - usage & priority check
A/B/C/Broker should drive onboarding priority & SLA. Today it is captured but not acted on.
Distribution & risk by category
Category | Deals | % of pipe | Idle 5+ d | No notes | Not signed up | Go-live overdue
A (top priority) | 12 | 18% | 3 | 1 | 0 | 5
B | 5 | 8% | 0 | 0 | 1 | 0
C | 34 | 52% | 2 | 1 | 2 | 4
Broker | 11 | 17% | 0 | 1 | 1 | 1
Uncategorized | 0 | 0% | 0 | 0 | 0 | 0
Total | 62
What this tells us
- A-grade = your most important accounts (11 deals). 3 have had NO activity in 5+ days and 1 have no notes at all - cadence on the A's has improved, keep it tight.
- Category is still not used to prioritise: A deals (Kunwarji 150 lic, Times, i5, Raghava) sit alongside C deals with the same attention. Tie an SLA to grade.
- Value is not tracked consistently: the biggest billed deal, Times Group (~Rs9.4L), is Category A, but Billed Amount is blank on 52 of 67 deals - populate it and re-grade against value + licences.
- 0 deals are uncategorized this run (good) - keep category mandatory at creation so nothing falls through prioritisation.
- 55% of the pipeline (37) is tagged C. Either genuinely low-value, or default tagging - worth a quick audit so C actually means C.
- Recommendation: tie an SLA to category - A = white-glove, named owner, weekly touch + exec visibility; B = fortnightly; C/Broker = templatised. Make category mandatory and value-aligned at deal creation.
A-GRADE WATCHLIST (protect these 15 - sorted by neglect)
Deal | Owner | Stage | Idle | Last note | Billed (Rs) | Lic | Status / note
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | 7-15 d | 07-Jul-26 | 1428980 | 150 | Client escalated rollout delays, wants 3-5 day onsite; JIRAs (incl mobile) to deploy by 15 Jul; targeting completion end-Jul/early-Aug.
Times Group | Sanket Nampalliwar | Pending on Customer | 7-15 d | 07-Jul-26 | 944000 | 50 | Data uploaded but client reports discrepancies; internal validation meeting 7 Jul; only formula fields and roles/access pending.
SPR Construction Pvt Ltd (leasing team) | Raahul Ramanan R | Onboarding In Progress | 5-7 d |  | 735376 | 17
Axon Developer | Sahil Jane | Onboarding In Progress | <=5 d | 19-Jul-26 | 450000 | 30 | Weekly: Facebook CAPI done, account-usage check done, IVR follow-up initiated, handover doc being prepared; Gupshup WhatsApp and workflow still pending API changes.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | <=5 d | 17-Jul-26 | 627760 | 36 | Last week's tasks done (WhatsApp templates, hierarchy, inventory, booking form, cost sheets, payment schedule, timesheet); Manager and Admin Training followed up.
Doff Estate | Venkat Viswavardhan | Pending on Customer | <=5 d | 19-Jul-26 | 523919 | 29 | Next week: complete bulk lead import on 20th July, arrange sales training, follow up on IVR integration.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 19-Jul-26 | 481440 | 40 | Update shared with dev team, ETA 29 Jul; re-walk customer through Sourcing.
Primeplus Realtech Llp | Venkat Viswavardhan | Onboarding In Progress | <=5 d | 19-Jul-26 | 95000 | 20 | Next-week plan: activate users, add projects, send emails for website & property-portal integration, integrate Meta, chase IVR update.
SKYTOWN Group | Venkat Viswavardhan | Pending on Customer | <=5 d | 19-Jul-26 | 733488 | 20 | Sales training done; onsite visit scheduled Wed; admin training, Q&A and WhatsApp integration pending (awaiting WhatsApp number from client).
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | <=5 d | 17-Jul-26 | 14660 | 41 | Weekly tasks on calling-integration timelines/delays marked done; Sanket to talk to Ketan.
Voora Developers | Raahul Ramanan R | Pending on Customer | <=5 d | 17-Jul-26 | 785880 | 21 | Pushing online vs onsite meeting tied to balance payment; Amit following up on partial payment; awaiting client acknowledgement on Manoj's pointers.
i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | <=5 d | 10-Jul-26 | 347156 | 18 | Inventory upload in progress; customer to update pending items (bulk lead import, website, WhatsApp number, property portals) by 11th EOD.

## 8. Re-grade (value+brand)
Category re-grade - value + licenses + brand/enterprise
Suggested grade = max of value, licence count, and brand/enterprise weight. Under-grading is the concern; higher-than-needed is low priority.
Summary: 5 under-graded (fix), 1 ungraded (set a grade), 0 clearly over-graded (low priority). ~8 A-deals score B on size alone (20-49 lic) - acceptable for enterprise/brand, not listed.
A) UNDER-GRADED - high value/brand but graded low (FIX THESE)
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Dhanraj Realbuild Llp | Venkat Viswavardhan | C | A | 60-90 d | 5-7L | <10/blank |  | billed Rs5-7L
Kohinoor AI Calling | Venkat Viswavardhan | C | B | 60-90 d | blank | <10/blank | Known | known brand
NPS DEVELOPERS | Raahul Ramanan R | C | B | 60-90 d | 3-5L | 10-19 |  | billed Rs3-5L
Shree Honda | Sourabh Sahu | C | B | >180 d | 2-3L | <10/blank |  | billed Rs2.11L
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | C | B | 30-60 d | 2-3L | <10/blank |  | billed Rs2-3L
B) UNGRADED - no category set (assign one)
Includes Krishvi (already Active) and the 'dummy' test record.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why
Yashoda Infra Developer | Shweta Gouda | C | C | 14-30 d | blank | <10/blank | Yashoda Infra Developer | uncategorized - new deal
C) Clearly over-graded - review (low priority)
B Square is actually live - close it rather than re-grade.
Deal | Owner | Current | Suggested | Age (created) | Billed | Licenses | Brand | Why

## 9. Comparison & Movement
Comparison & Movement vs previous run(s)
Run 10 (Mon 20-Jul-2026) vs 16-Jul & 13-Jul
Deal | Owner | Stage prev->now | Last note prev->now | Movement verdict | Stuck streak | Reason / action
Dhanraj Realbuild Llp | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-11 -> 2026-07-19 | Same-blocker | 9 | Refund/churn risk deepening; customer refuses AI-calling, wants unavailable sourcing changes.
Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-11 -> 2026-07-19 | Same-blocker | 9 | AI-calling still blocked (ESTATE-21040 / SS-12176); only a call being scheduled.
Ribitto Private Limited | Muntazar Mhate | Onboarding In Progress -> Pending on Customer | 2026-07-14 -> 2026-07-20 | Same-blocker | 9 | Moved into Pending; transactional email still broken, sales training still deferred behind it.
SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-07-13 -> 2026-07-17 | Same-blocker | 9 | Calling-integration blocker persists; now escalated to Ketan - escalation is not resolution.
Times Group | Sanket Nampalliwar | Pending on Customer -> Pending on Customer | 2026-07-07 -> 2026-07-07 | No-activity | 9 | No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review.
Voora Developers | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-07-13 -> 2026-07-17 | Same-blocker | 9 | Same blockers: balance payment + Manoj's pointers, still awaited.
NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-07-08 -> 2026-07-17 | Same-blocker | 5 | Owner states nothing moved this week; escalated to sales.
Shree Automotive | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2026-07-07 -> 2026-07-07 | No-activity | 5 | No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review.
Leonaara PVt LTD | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-12 -> 2026-07-19 | Same-blocker | 4 | WhatsApp Interakt still pending on dev; trainings only scheduled, not done.
Sangram Group | Muntazar Mhate | Onboarding In Progress -> Pending on Customer | 2026-07-14 -> 2026-07-20 | Same-blocker | 4 | Moved into Pending; on-hold email sent; sales training only assured for Monday.
Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Onboarding In Progress -> Pending on Customer | 2026-07-14 -> 2026-07-17 | Same-blocker | 4 | Moved into Pending; inventory-layout demo slipped (client unavailable).
GGC AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-11 -> 2026-07-17 | Same-blocker | 3 | Still only arranging a call; AI-calling adoption not started.
Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress -> Onboarding In Progress | 2026-07-07 -> 2026-07-07 | No-activity | 3 | No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review.
Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-11 -> 2026-07-19 | Same-blocker | 3 | Still awaiting BOT feedback/adoption; now via a new POC (SS-12285).
Navkar Realty | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-16 -> 2026-07-19 | Same-blocker | 3 | No progress - customer POC on sick leave; all items pushed to next week.
Shree Honda | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2026-07-07 -> 2026-07-07 | No-activity | 3 | No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review.
Strata Capital Holdings | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-13 -> 2026-07-18 | Same-blocker | 3 | Mcube still blocked (recordings not captured); raised to vendor, client waiting.
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-11 -> 2026-07-17 | Same-blocker | 3 | Admin training restated as awaiting customer availability - same ask.
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-10 -> 2026-07-19 | Same-blocker | 3 | Admin training still only being scheduled a week later - scheduled != done.
GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-11 -> 2026-07-19 | Same-blocker | 2 | Still awaiting Sourcing rework from dev (ETA 29 Jul); customer un-progressed.
Propnsafe Realty LLP | Sahil Jane | Kickoff Done -> Kickoff Done | 2026-07-12 -> 2026-07-19 | Same-blocker | 2 | Still in Kickoff Done; core setup gated on website + lead import; fancy number is a side item.
Rajparis Civil Construction | Muntazar Mhate | Onboarding In Progress -> Pending on Customer | 2026-07-14 -> 2026-07-20 | Same-blocker | 2 | Moved into Pending; AiSensy + inventory + cost sheet all awaited from client.
SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress -> Onboarding In Progress | 2026-07-11 -> 2026-07-19 | Same-blocker | 2 | Owner notes little concrete movement; trainings pending client availability.
Sell.do test | Sanket Nampalliwar | Open -> Open | 2026-07-09 -> 2026-07-09 | No-activity | 2 | No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review.
Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Pending on Customer | 2026-07-14 -> 2026-07-17 | Same-blocker | 2 | Account already live last week; only Facebook added; moved into Pending with hold threat.
i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress -> Onboarding In Progress | 2026-07-11 -> 2026-07-11 | No-activity | 2 | No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review.
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open -> Open | 2026-07-06 -> 2026-07-06 | No-activity | 2 | No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review.
test deal Push to OB 63 Copy | Sanket Nampalliwar | Open -> Open | 2026-07-06 -> 2026-07-06 | No-activity | 2 | No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review.
Doff Estate | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-12 -> 2026-07-19 | Same-blocker | 1 | Only a next-week plan (lead import 20th, training, IVR follow-up); nothing completed this week.
SKYTOWN Group | Venkat Viswavardhan | Pending on Customer -> Pending on Customer | 2026-07-16 -> 2026-07-19 | Same-blocker | 1 | Restated: sales training done last week, onsite Wed, still awaiting WhatsApp number.
SPR Construction Pvt Ltd (leasing team) | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | - -> - | No-activity | 1 | No note after 2026-07-16 (last run) and no stage change - nothing happened since the last review.
Scanon Realty | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-14 -> 2026-07-18 | Same-blocker | 1 | Sales training rescheduled again on client unavailability - repeat slip.
ACL INFRATECH PRIVATE LIMITED (LOVE HOME LLP) | Sahil Jane | NEW this run | - -> 2026-07-19 | NEW | 0 | New in pipeline this run.
Apex Realty Hub | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-13 -> 2026-07-19 | Progressed | 0 | Sales and admin training both completed; Meta/WA on hold on client Meta account.
Aryma Infra (OPC)Pvt Ltd | Sahil Jane | NEW this run | - -> 2026-07-20 | NEW | 0 | New in pipeline this run.
Axon Developer | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-12 -> 2026-07-19 | Progressed | 0 | Facebook CAPI and usage check completed; handover doc in preparation.
BRICKSAGE PROPERTIES ADVISORS PRIVATE LIMITED | Sahil Jane | NEW this run | - -> 2026-07-19 | NEW | 0 | New in pipeline this run.
Blueroof India | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-14 -> 2026-07-18 | Progressed | 0 | Setup, Meta, inventory, bulk import, admin + mobile sales training completed.
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer -> Pending on Customer | 2026-07-08 -> 2026-07-17 | Progressed | 0 | Multiple items completed (WhatsApp templates, hierarchy, inventory, booking form, cost sheets, payment schedule); only trainings left.
Emerald Blue | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-16 -> 2026-07-17 | Progressed | 0 | Core setup (users/projects/reports/routing) completed; trainings pending.
GAGAN TONDON | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-14 -> 2026-07-18 | Progressed | 0 | Users/projects/reports/99acres/MagicBricks completed; lead import waiting on customer.
Growthx Estates | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-14 -> 2026-07-18 | Progressed | 0 | Meta, 99acres, offline dialer and sales training (laptop+mobile) completed.
Jinraj Real Estate | Raahul Ramanan R | NEW this run | - -> 2026-07-20 | NEW | 0 | New in pipeline this run.
KL HOMES | Shweta Gouda | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
MSK Realty | Muntazar Mhate | Kickoff Done -> Onboarding In Progress | 2026-07-14 -> 2026-07-20 | Progressed | 0 | Stage Kickoff Done -> Onboarding In Progress.
Makliv Infra Consulting Pvt Ltd. | Sahil Jane | NEW this run | - -> - | NEW | 0 | New in pipeline this run.
MiCasa Realty | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | 2026-07-13 -> 2026-07-20 | Progressed | 0 | Core setup, routing, lead import, website, inventory completed; Mcube awaiting vendor.
PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-13 -> 2026-07-18 | Progressed | 0 | Lead import completed; native WhatsApp awaiting client number.
Palli Developers and Consultants LLP | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-14 -> 2026-07-17 | Progressed | 0 | 99 Acres property portal integration completed.
Primeplus Realtech Llp | Venkat Viswavardhan | NEW this run | - -> 2026-07-19 | NEW | 0 | New in pipeline this run.
Properties Boutique | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-13 -> 2026-07-19 | Progressed | 0 | Handover and Q&A completed, account live - effectively wrapped.
R J Real Tech and Properties Pvt Ltd | Sahil Jane | Open -> Onboarding In Progress | - -> 2026-07-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
RUBRICK CONSTRUCTIONS PRIVATE LIMITED | Sahil Jane | Open -> Onboarding In Progress | - -> 2026-07-19 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress -> Onboarding In Progress | - -> 2026-07-20 | Progressed | 0 | Account/team setup completed (1 user pending activation); integrations pending client.
SHREYA CAPITAL ADVISORY SERVICES LLP | Sahil Jane | Kickoff Done -> Kickoff Done | - -> 2026-07-19 | Progressed | 0 | First note logged; users/projects/reports completed; Meta+website upcoming.
STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Open -> Onboarding In Progress | - -> 2026-07-20 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Salah Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-14 -> 2026-07-17 | Progressed | 0 | Inventory follow-up completed; admin training slipped on client hardware issue.
Sunita real estate | Shweta Gouda | Open -> Onboarding In Progress | - -> 2026-07-18 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Sunny Developers & Realtors | Shweta Gouda | Open -> Onboarding In Progress | 2026-07-10 -> 2026-07-18 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Sunrise Housing (GHP Group) | Muntazar Mhate | Onboarding In Progress -> Onboarding In Progress | 2026-07-14 -> 2026-07-17 | Progressed | 0 | Setup, routing, IVR, offline dialer, SV form and laptop sales training completed.
VASTU INFINITY AND VENTURES LLP | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-13 -> 2026-07-19 | Progressed | 0 | Admin training completed, account live in OB, handover planned this week.
VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress -> Onboarding In Progress | 2026-07-14 -> 2026-07-19 | Progressed | 0 | Facebook and SV form completed; sales training scheduled Wed.
Veedhan Buildtech | Sahil Jane | NEW this run | - -> 2026-07-20 | NEW | 0 | New in pipeline this run.
WINTER HOME PROPERTIES | Shweta Gouda | Open -> Onboarding In Progress | 2026-07-14 -> 2026-07-16 | Progressed | 0 | Stage Open -> Onboarding In Progress.
Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress -> Onboarding In Progress | 2026-07-13 -> 2026-07-18 | Progressed | 0 | Native WhatsApp (the prior blocker) completed; trainings slipped to next week.

## 10. Reality Check (JIRA)
Reality Check - JIRA cited in the note vs the live ticket
GHOST DEPENDENCY = the ticket is closed/Won't Fix but the deal is still parked against it. Fix these first.
Severity | Deal | Owner | Ticket | Live status | Fix ver | Last updated | Stuck runs | What the note tells the customer | Why it matters
GHOST DEPENDENCY | Kohinoor AI Calling | Venkat Viswavardhan | ESTATE-21040 | Won't Fix | 11.3 | 2026-07-13 | 9 | Schedule call to discuss customer pointers (dependent on Sharayu/customer availability). | Ticket is Won't Fix - the deal is still being held against a dependency that is closed. Customer is waiting for nothing.
GHOST DEPENDENCY | Kohinoor AI Calling | Venkat Viswavardhan | SS-12176 | Done | 11.0 | 2026-07-16 | 9 | Schedule call to discuss customer pointers (dependent on Sharayu/customer availability). | Ticket is Done - the deal is still being held against a dependency that is closed. Customer is waiting for nothing.
GHOST DEPENDENCY | Times Group | Sanket Nampalliwar | ESTATE-18697 | Done | 6.0 | 2026-02-13 | 9 | Data uploaded but client reports discrepancies; internal validation meeting 7 Jul; only formula fields and roles/access | Ticket is Done - the deal is still being held against a dependency that is closed. Customer is waiting for nothing.
STUCK IN OUR QUEUE | Mythri Builder AI Calling | Venkat Viswavardhan | SS-12285 | Tech Discussion |  | 2026-06-26 | 3 | Connect with new POC for BOT feedback and push adoption. | Ticket sits in 'Tech Discussion' - this is our bottleneck, not the customer's.

## 11. Who's Really Blocking
Who is really blocking each deal
'Pending on Customer' with a non-CUSTOMER blocker = the stage is being used as a parking lot. 3 such deals this run.
Blocker | Deal | Owner | Stage | Stuck runs | Value | Age | Latest note
US-COMMERCIAL | Times Group | Sanket Nampalliwar | Pending on Customer | 9 | 7-10L | >180 d | Data uploaded but client reports discrepancies; internal validation meeting 7 Jul; only formula fields and roles/access pending.
US-COMMERCIAL | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | 4 | 1-2L | 30-60 d | Weekly update: Jiras raised for calling-logs and Interakt WhatsApp issues (done); this week sales and tentative admin training; WhatsApp Interakt inte
OWNER-INACTION | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | 9 | blank | 60-90 d | Weekly tasks on calling-integration timelines/delays marked done; Sanket to talk to Ketan.
OWNER-INACTION | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | 5 | 3-5L | 60-90 d | Nothing moved this week; escalate to sales for help; admin-training follow-ups; Kylas to be updated.
OWNER-INACTION | Shree Automotive | Sourabh Sahu | Onboarding In Progress | 5 | 1-2L | >180 d | Meeting set 8 Jul with POC/Director to reinitiate OB and finalize plan.
OWNER-INACTION | Navkar Realty | Venkat Viswavardhan | Pending on Customer | 3 | 3-5L | 30-60 d | Customer (Sahil) on sick leave last week; next week check availability, schedule AI-bot feedback call, follow up on CP form.
OWNER-INACTION | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | 3 | >=10L | 60-90 d | Client escalated rollout delays, wants 3-5 day onsite; JIRAs (incl mobile) to deploy by 15 Jul; targeting completion end-Jul/early-Aug.
OWNER-INACTION | Shree Honda | Sourabh Sahu | Onboarding In Progress | 3 | 2-3L | >180 d | Meeting set 8 Jul with POC/Director to reinitiate OB and finalize plan.
OWNER-INACTION | SPR Construction Pvt Ltd (leasing team) | Raahul Ramanan R | Onboarding In Progress | 1 | 7-10L | <14 d
OWNER-INACTION | Blueroof India | Muntazar Mhate | Onboarding In Progress | 0 | blank | 14-30 d | Setup, Meta, inventory, bulk import, admin + mobile sales training done; website + YouTube pending client; laptop sales training next week.
US-TECH | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | 9 | blank | 30-60 d | Mailgun promotional emails working, transactional broken; Sales Training deferred until email issue fixed.
US-TECH | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | 3 | blank | 30-60 d | MCube testing blocked - calls initiate but recordings not captured; issue raised to MCube team; client will proceed with integrations once resolved.
US-TECH | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | 2 | 3-5L | 90-180 d | Update shared with dev team, ETA 29 Jul; re-walk customer through Sourcing.
VENDOR | Propnsafe Realty LLP | Sahil Jane | Kickoff Done | 2 | 1-2L | <14 d | WhatsApp (awaiting fancy number) and Meta (no active forms) unfinished; fancy number now received; Mcube pending website; project, lead import and tra
VENDOR | i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | 2 | 3-5L | 30-60 d | Inventory upload in progress; customer to update pending items (bulk lead import, website, WhatsApp number, property portals) by 11th EOD.
VENDOR | GAGAN TONDON | Shweta Gouda | Onboarding In Progress | 0 | blank | <14 d | Last week users/projects/reports/99acres/MagicBricks done, lead import waiting on customer; this week Interakt WhatsApp, sales & admin training, hando
VENDOR | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | 0 | 1-2L | >180 d | Status recap: accounts/project/routing/99acres done; Facebook, Mcube, trainings, website, data migration pending; new tasks discussed.
UNCLEAR | Dhanraj Realbuild Llp | Venkat Viswavardhan | Pending on Customer | 9 | 5-7L | 60-90 d | Customer refuses AI-calling discussion, wants unavailable sourcing changes; checking with Siddharth (refund risk).
UNCLEAR | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 3 | 3-5L | 30-60 d | Admin Training to be scheduled per customer availability, then handover.
UNCLEAR | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | 3 | blank | 60-90 d | Arranging a call between customer, Vinay and Siddharth; checking availability.
UNCLEAR | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | 3 | blank | 60-90 d | Connect with new POC for BOT feedback and push adoption.
UNCLEAR | SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | 2 | 2-3L | 14-30 d | Only a next-week note: sales & admin training pending on client availability; little concrete movement.
UNCLEAR | Doff Estate | Venkat Viswavardhan | Pending on Customer | 1 | 5-7L | <14 d | Next week: complete bulk lead import on 20th July, arrange sales training, follow up on IVR integration.
UNCLEAR | Scanon Realty | Shweta Gouda | Onboarding In Progress | 1 | blank | <14 d | Sales training rescheduled again due to client unavailability; core setup and lead import done; integrations not required (manual leads).
UNCLEAR | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | 0 | blank | <14 d
UNCLEAR | KL HOMES | Shweta Gouda | Open | 0 | blank | <14 d
UNCLEAR | Primeplus Realtech Llp | Venkat Viswavardhan | Onboarding In Progress | 0 | blank | <14 d | Next-week plan: activate users, add projects, send emails for website & property-portal integration, integrate Meta, chase IVR update.
UNCLEAR | ACL INFRATECH PRIVATE LIMITED (LOVE HOME LLP) | Sahil Jane | Onboarding In Progress | 0 | 1-2L | <14 d | Users/projects/reports done; this week focus Meta + bulk lead import + sales/presales training; 99acres, inventory, dialer, admin training pending.
UNCLEAR | BRICKSAGE PROPERTIES ADVISORS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | 0 | 1-2L | <14 d | Users/projects/reports done; this week Meta + bulk lead import + training; MagicBricks email initiated, dialer/inventory/admin training pending.
UNCLEAR | Emerald Blue | Muntazar Mhate | Onboarding In Progress | 0 | blank | <14 d | Users/projects/reports/routing done; bulk lead import, sales & admin training pending/to be scheduled; most integrations marked not required.
UNCLEAR | RUBRICK CONSTRUCTIONS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | 0 | 5-7L | <14 d | Users/projects/reports done; this week Meta + WhatsApp; Google Ads, bulk lead import, dialer, training pending; post-sales/inventory handled by Shubha
UNCLEAR | R J Real Tech and Properties Pvt Ltd | Sahil Jane | Onboarding In Progress | 0 | 1-2L | <14 d | Users/projects/reports done; this week Meta + bulk lead import + sales training; Facebook, inventory, website, admin training pending.
UNCLEAR | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | 0 | blank | <14 d | This week targeting lead import and sales training.
UNCLEAR | SHREYA CAPITAL ADVISORY SERVICES LLP | Sahil Jane | Kickoff Done | 0 | 3-5L | <14 d | Users/projects/reports done; upcoming Meta + website + tentative lead import/inventory (awaiting files); WATI on hold due to account issues.
UNCLEAR | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | 0 | blank | <14 d | Account/team setup done; one user not activated; routing, lead import and all integrations pending on client POC details and call scheduling.
UNCLEAR | MiCasa Realty | Raahul Ramanan R | Onboarding In Progress | 0 | blank | <14 d | Core setup, routing, lead import, website and inventory done; Mcube telephony awaiting vendor; Meta and trainings pending.
UNCLEAR | MSK Realty | Muntazar Mhate | Onboarding In Progress | 0 | blank | <14 d | Account setup, GPS and clock-in done; bulk lead import, Meta, website, landing pages, native WhatsApp and trainings all pending.
UNCLEAR | Palli Developers and Consultants LLP | Muntazar Mhate | Onboarding In Progress | 0 | 1-2L | <14 d | Weekly update: 99 Acres property portal integration completed.
UNCLEAR | Apex Realty Hub | Sahil Jane | Onboarding In Progress | 0 | blank | <14 d | Meta and WhatsApp on hold pending client Meta account; sales and admin training done; integrations to complete if Meta account created this week.
UNCLEAR | VASTU INFINITY AND VENTURES LLP | Sahil Jane | Onboarding In Progress | 0 | blank | 14-30 d | Admin training done, account made live in OB, handover planned this week; Meta integration on hold (POC away 2 weeks).
UNCLEAR | Properties Boutique | Sahil Jane | Onboarding In Progress | 0 | blank | 14-30 d | Account live in OB, handover + Q&A completed; only Meta integration call pending (Monday) - effectively wrapped.
UNCLEAR | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | 0 | blank | 14-30 d | Native WhatsApp done; sales & admin training slipped to next week; website + Housing integration pending on client.
UNCLEAR | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | 0 | 1-2L | 14-30 d | Account was on hold; resuming - sales training scheduled Tuesday 11:00 AM.
UNCLEAR | Axon Developer | Sahil Jane | Onboarding In Progress | 0 | 3-5L | 30-60 d | Weekly: Facebook CAPI done, account-usage check done, IVR follow-up initiated, handover doc being prepared; Gupshup WhatsApp and workflow still pendin
UNCLEAR | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | 0 | blank | 30-60 d | Account was on hold; onboarding to start from today.
UNCLEAR | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | 0 | 5-7L | 60-90 d | Last week's tasks done (WhatsApp templates, hierarchy, inventory, booking form, cost sheets, payment schedule, timesheet); Manager and Admin Training
CUSTOMER | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | 9 | blank | 60-90 d | Schedule call to discuss customer pointers (dependent on Sharayu/customer availability).
CUSTOMER | Voora Developers | Raahul Ramanan R | Pending on Customer | 9 | 7-10L | >180 d | Pushing online vs onsite meeting tied to balance payment; Amit following up on partial payment; awaiting client acknowledgement on Manoj's pointers.
CUSTOMER | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | 4 | blank | 30-60 d | Custom fields set up; inventory-layout demo not done (client team unavailable); movement expected after inventory demo, client available Monday.
CUSTOMER | Sangram Group | Muntazar Mhate | Pending on Customer | 4 | blank | 30-60 d | Pending pointers followed up; customer still hasn't shared fresh WhatsApp number - account-on-hold email sent; client assured Sales Training Monday.
CUSTOMER | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Pending on Customer | 3 | 2-3L | 30-60 d | Awaiting customer availability for Admin Training; to schedule next week then handover.
CUSTOMER | Rajparis Civil Construction | Muntazar Mhate | Pending on Customer | 2 | 3-5L | 14-30 d | AiSensy WhatsApp pending client/AiSensy (setup ready our end); inventory & cost sheet awaited from client; SV/CP forms and sales training tentative.
CUSTOMER | Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Pending on Customer | 2 | 5-7L | 30-60 d | Sales Training done, account live; Facebook integration done; Prabhu on-site working with client; hold threatened if no update after 3 follow-ups.
CUSTOMER | SKYTOWN Group | Venkat Viswavardhan | Pending on Customer | 1 | 7-10L | 14-30 d | Sales training done; onsite visit scheduled Wed; admin training, Q&A and WhatsApp integration pending (awaiting WhatsApp number from client).
CUSTOMER | Sunita real estate | Shweta Gouda | Onboarding In Progress | 0 | blank | <14 d | Last week users/projects/reports/leads/99acres done; this week inventory upload (pending client file), sales training, dialer setup.
CUSTOMER | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | 0 | blank | <14 d | Account created; user creation/activation in progress (reminders resent); team/hierarchy/pipeline awaiting client; lead import & inventory calls resch
CUSTOMER | Sunny Developers & Realtors | Shweta Gouda | Onboarding In Progress | 0 | blank | <14 d | Users, project, lead import, pipeline, reports and Meta done; this week targeting Exotel, Google ads and website (awaiting client), then sales trainin
CUSTOMER | PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Onboarding In Progress | 0 | 3-5L | <14 d | Lead import done; native WhatsApp awaiting client number; 99 acres and website API details shared; sales training pending.
CUSTOMER | Salah Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | 0 | blank | 14-30 d | Inventory follow-up done; admin training not done - client facing laptop/hardware issue.
CUSTOMER | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | 0 | 2-3L | 14-30 d | Facebook + SV form completed; native WhatsApp on hold per client; sales training scheduled Wednesday; dialer + trainings pending.
CUSTOMER | Growthx Estates | Muntazar Mhate | Onboarding In Progress | 0 | 1-2L | 14-30 d | Meta, 99acres, offline dialer, laptop+mobile sales training done; bulk import, Google Ads, website initiated, admin training pending.
CUSTOMER | Sunrise Housing (GHP Group) | Muntazar Mhate | Onboarding In Progress | 0 | 2-3L | 14-30 d | Setup, routing, IVR, offline dialer, SV form, laptop sales training done; bulk import, Meta, website, native WhatsApp, mobile training + admin pending

## 12. Escalation & Risk Register
Escalation & Risk Register
Anything mentioning refund / legal / escalation / hold / unhappy. 'Moved since? = NO' means we logged the escalation and then did nothing.
Blocker | Deal | Owner | Stage | Value | Licences | Age | Stuck runs | First flagged | Days open | Moved since? | Latest note
UNCLEAR | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | blank | 5 | 30-60 d | 0 | 2026-06-18 | 32 | yes | Account was on hold; onboarding to start from today.
UNCLEAR | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | 1-2L | 5 | 14-30 d | 0 | 2026-07-02 | 18 | yes | Account was on hold; resuming - sales training scheduled Tuesday 11:00 AM.
UNCLEAR | Dhanraj Realbuild Llp | Venkat Viswavardhan | Pending on Customer | 5-7L | 6 | 60-90 d | 9 | 2026-07-07 | 13 | NO | Customer refuses AI-calling discussion, wants unavailable sourcing changes; checking with Siddharth (refund risk).
UNCLEAR | VASTU INFINITY AND VENTURES LLP | Sahil Jane | Onboarding In Progress | blank | 5 | 14-30 d | 0 | 2026-07-10 | 10 | yes | Admin training done, account made live in OB, handover planned this week; Meta integration on hold (POC away 2 weeks).
US-COMMERCIAL | Times Group | Sanket Nampalliwar | Pending on Customer | 7-10L | 50 | >180 d | 9 | 2026-07-13 | 7 | NO | Data uploaded but client reports discrepancies; internal validation meeting 7 Jul; only formula fields and roles/access pending.
OWNER-INACTION | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | >=10L | 150 | 60-90 d | 3 | 2026-07-13 | 7 | NO | Client escalated rollout delays, wants 3-5 day onsite; JIRAs (incl mobile) to deploy by 15 Jul; targeting completion end-Jul/early-Aug.
CUSTOMER | Sangram Group | Muntazar Mhate | Pending on Customer | blank | 5 | 30-60 d | 4 | 2026-07-16 | 4 | NO | Pending pointers followed up; customer still hasn't shared fresh WhatsApp number - account-on-hold email sent; client assured Sales Training Monday.
CUSTOMER | Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Pending on Customer | 5-7L | 10 | 30-60 d | 2 | 2026-07-16 | 4 | NO | Sales Training done, account live; Facebook integration done; Prabhu on-site working with client; hold threatened if no update after 3 follow-ups.
OWNER-INACTION | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | 3-5L | 11 | 60-90 d | 5 | 2026-07-20 | 0 | NO | Nothing moved this week; escalate to sales for help; admin-training follow-ups; Kylas to be updated.
US-COMMERCIAL | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | 1-2L | 6 | 30-60 d | 4 | 2026-07-20 | 0 | NO | Weekly update: Jiras raised for calling-logs and Interakt WhatsApp issues (done); this week sales and tentative admin training; WhatsApp Interakt integration st
UNCLEAR | SHREYA CAPITAL ADVISORY SERVICES LLP | Sahil Jane | Kickoff Done | 3-5L | 5 | <14 d | 0 | 2026-07-20 | 0 | yes | Users/projects/reports done; upcoming Meta + website + tentative lead import/inventory (awaiting files); WATI on hold due to account issues.
UNCLEAR | Apex Realty Hub | Sahil Jane | Onboarding In Progress | blank | 5 | <14 d | 0 | 2026-07-20 | 0 | yes | Meta and WhatsApp on hold pending client Meta account; sales and admin training done; integrations to complete if Meta account created this week.
CUSTOMER | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | 2-3L | 8 | 14-30 d | 0 | 2026-07-20 | 0 | yes | Facebook + SV form completed; native WhatsApp on hold per client; sales training scheduled Wednesday; dialer + trainings pending.

## 13. Scope Coverage
Scope Coverage - what was skipped, disclaimed, or never tracked
CHALLENGE = 'Not required' on a MUST item. NOT TRACKED = blank field: the work is invisible, not done. Both are ways scope quietly disappears.
Flag | Deal | Owner | Stage | Checklist item | Tier | Value | Licences | Billed | Stuck runs | Why it matters
CHALLENGE | Times Group | Sanket Nampalliwar | Pending on Customer | Lead routing configured | MUST | N | 50 | 944000 | 9 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Times Group | Sanket Nampalliwar | Pending on Customer | Pipeline / stages configured | MUST | N | 50 | 944000 | 9 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Times Group | Sanket Nampalliwar | Pending on Customer | Existing leads imported | MUST | N | 50 | 944000 | 9 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | SKYTOWN Group | Venkat Viswavardhan | Pending on Customer | Existing leads imported | MUST | N | 20 | 733488 | 1 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Navkar Realty | Venkat Viswavardhan | Pending on Customer | Existing leads imported | MUST | N | 4 | 495600 | 3 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | Existing leads imported | MUST | N | 40 | 481440 | 2 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Existing leads imported | MUST | N | 15 | 350000 | 3 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | Existing leads imported | MUST | N | 8 | 241900 | 0 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Palli Developers and Consultants LLP | Muntazar Mhate | Onboarding In Progress | Channel-partner module | MUST | N | 5 | 153400 | 0 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | ACL INFRATECH PRIVATE LIMITED (LOVE HOME LLP) | Sahil Jane | Onboarding In Progress | Channel-partner module | MUST | N | 10 | 121000 | 0 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | Channel-partner module | MUST | N | 6 | 74240 | 9 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | MSK Realty | Muntazar Mhate | Onboarding In Progress | Channel-partner module | MUST | N | 3 | 68440 | 0 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Properties Boutique | Sahil Jane | Onboarding In Progress | Existing leads imported | MUST | N | 7 | 61360 | 0 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Salah Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | Existing leads imported | MUST | N | 2 | 28792 | 0 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Scanon Realty | Shweta Gouda | Onboarding In Progress | Lead routing configured | MUST | N | 2 | 11328 | 1 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | Existing leads imported | MUST | N | 2 |  | 3 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | Sales / pre-sales training | MUST | N | 2 |  | 3 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | Admin training | MUST | N | 2 |  | 3 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | Existing leads imported | MUST | N | 2 |  | 3 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | Sales / pre-sales training | MUST | N | 2 |  | 3 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | Admin training | MUST | N | 2 |  | 3 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | Existing leads imported | MUST | N | 2 |  | 9 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | Sales / pre-sales training | MUST | N | 2 |  | 9 | Marked 'Not required' on a MUST item. No account goes live without this.
CHALLENGE | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | Admin training | MUST | N | 2 |  | 9 | Marked 'Not required' on a MUST item. No account goes live without this.
NOT TRACKED | Doff Estate | Venkat Viswavardhan | Pending on Customer | Marketing training | BASIC | - | 29 | 523919 | 1 | Standard item for this segment, left blank.
NOT TRACKED | Axon Developer | Sahil Jane | Onboarding In Progress | Marketing training | BASIC | - | 30 | 450000 | 0 | Standard item for this segment, left blank.
NOT TRACKED | PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Onboarding In Progress | DLT (SMS) registration | BASIC | - | 5 | 326860 | 0 | Standard item for this segment, left blank.
NOT TRACKED | PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 5 | 326860 | 0 | Standard item for this segment, left blank.
NOT TRACKED | PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Onboarding In Progress | Workflow automation | BASIC | - | 5 | 326860 | 0 | Standard item for this segment, left blank.
NOT TRACKED | PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Onboarding In Progress | Marketing training | BASIC | - | 5 | 326860 | 0 | Standard item for this segment, left blank.
NOT TRACKED | SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Property portals (99acres etc) | BASIC | - | 35 | 258420 | 2 | Standard item for this segment, left blank.
NOT TRACKED | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | Sales / pre-sales training | MUST | - | 8 | 241900 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | Admin training | MUST | - | 8 | 241900 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | Workflow automation | BASIC | - | 8 | 241900 | 0 | Standard item for this segment, left blank.
NOT TRACKED | VRUSHABADRI DEVELOPERS | Sahil Jane | Onboarding In Progress | Marketing training | BASIC | - | 8 | 241900 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | Website integration | BASIC | - | 4 | 174862 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | Meta / Facebook lead-gen | BASIC | - | 4 | 174862 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | Property portals (99acres etc) | BASIC | - | 4 | 174862 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | WhatsApp integration | BASIC | - | 4 | 174862 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | WhatsApp templates | BASIC | - | 4 | 174862 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | Cloud telephony / IVR | BASIC | - | 4 | 174862 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 4 | 174862 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | Workflow automation | BASIC | - | 4 | 174862 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Propnsafe Realty LLP | Sahil Jane | Kickoff Done | Marketing training | BASIC | - | 3 | 172516 | 2 | Standard item for this segment, left blank.
NOT TRACKED | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | Marketing training | BASIC | - | 6 | 129800 | 4 | Standard item for this segment, left blank.
NOT TRACKED | R J Real Tech and Properties Pvt Ltd | Sahil Jane | Onboarding In Progress | Sales / pre-sales training | MUST | - | 8 | 125080 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | R J Real Tech and Properties Pvt Ltd | Sahil Jane | Onboarding In Progress | Admin training | MUST | - | 8 | 125080 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | R J Real Tech and Properties Pvt Ltd | Sahil Jane | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 8 | 125080 | 0 | Standard item for this segment, left blank.
NOT TRACKED | R J Real Tech and Properties Pvt Ltd | Sahil Jane | Onboarding In Progress | Workflow automation | BASIC | - | 8 | 125080 | 0 | Standard item for this segment, left blank.
NOT TRACKED | R J Real Tech and Properties Pvt Ltd | Sahil Jane | Onboarding In Progress | Marketing training | BASIC | - | 8 | 125080 | 0 | Standard item for this segment, left blank.
NOT TRACKED | ACL INFRATECH PRIVATE LIMITED (LOVE HOME LLP) | Sahil Jane | Onboarding In Progress | Website integration | BASIC | - | 10 | 121000 | 0 | Standard item for this segment, left blank.
NOT TRACKED | ACL INFRATECH PRIVATE LIMITED (LOVE HOME LLP) | Sahil Jane | Onboarding In Progress | WhatsApp integration | BASIC | - | 10 | 121000 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | Sales / pre-sales training | MUST | - | 5 | 120336 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | Admin training | MUST | - | 5 | 120336 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 5 | 120336 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | Workflow automation | BASIC | - | 5 | 120336 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Onboarding In Progress | Marketing training | BASIC | - | 5 | 120336 | 0 | Standard item for this segment, left blank.
NOT TRACKED | BRICKSAGE PROPERTIES ADVISORS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | WhatsApp templates | BASIC | - | 15 | 106200 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Lead routing configured | MUST | - | 4 | 81184 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Pipeline / stages configured | MUST | - | 4 | 81184 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Channel-partner module | MUST | - | 4 | 81184 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Sales / pre-sales training | MUST | - | 4 | 81184 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Admin training | MUST | - | 4 | 81184 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Website integration | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Meta / Facebook lead-gen | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Property portals (99acres etc) | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | WhatsApp integration | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | WhatsApp templates | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Cloud telephony / IVR | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | DLT (SMS) registration | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Workflow automation | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Marketing training | BASIC | - | 4 | 81184 | 0 | Standard item for this segment, left blank.
NOT TRACKED | GAGAN TONDON | Shweta Gouda | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 9 | 80830 | 0 | Standard item for this segment, left blank.
NOT TRACKED | GAGAN TONDON | Shweta Gouda | Onboarding In Progress | Channel-partner module | BASIC | - | 9 | 80830 | 0 | Standard item for this segment, left blank.
NOT TRACKED | GAGAN TONDON | Shweta Gouda | Onboarding In Progress | Workflow automation | BASIC | - | 9 | 80830 | 0 | Standard item for this segment, left blank.
NOT TRACKED | GAGAN TONDON | Shweta Gouda | Onboarding In Progress | Marketing training | BASIC | - | 9 | 80830 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | User logins created | MUST | - | 2 | 65233 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Lead routing configured | MUST | - | 2 | 65233 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Pipeline / stages configured | MUST | - | 2 | 65233 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Existing leads imported | MUST | - | 2 | 65233 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Sales / pre-sales training | MUST | - | 2 | 65233 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Admin training | MUST | - | 2 | 65233 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Projects created | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Website integration | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Meta / Facebook lead-gen | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Property portals (99acres etc) | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | WhatsApp integration | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | WhatsApp templates | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Cloud telephony / IVR | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | DLT (SMS) registration | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Offline dialer / tracker app | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Channel-partner module | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Workflow automation | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | KL HOMES | Shweta Gouda | Open | Marketing training | BASIC | - | 2 | 65233 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Properties Boutique | Sahil Jane | Onboarding In Progress | Marketing training | BASIC | - | 7 | 61360 | 0 | Standard item for this segment, left blank.
NOT TRACKED | VASTU INFINITY AND VENTURES LLP | Sahil Jane | Onboarding In Progress | Marketing training | BASIC | - | 5 | 33000 | 0 | Standard item for this segment, left blank.
NOT TRACKED | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | Channel-partner module | MUST | - | 2 | 17700 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | Website integration | BASIC | - | 2 | 17700 | 0 | Standard item for this segment, left blank.
NOT TRACKED | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | WhatsApp integration | BASIC | - | 2 | 17700 | 0 | Standard item for this segment, left blank.
NOT TRACKED | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | WhatsApp templates | BASIC | - | 2 | 17700 | 0 | Standard item for this segment, left blank.
NOT TRACKED | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 2 | 17700 | 0 | Standard item for this segment, left blank.
NOT TRACKED | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | Workflow automation | BASIC | - | 2 | 17700 | 0 | Standard item for this segment, left blank.
NOT TRACKED | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | Marketing training | BASIC | - | 2 | 17700 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Scanon Realty | Shweta Gouda | Onboarding In Progress | Meta / Facebook lead-gen | BASIC | - | 2 | 11328 | 1 | Standard item for this segment, left blank.
NOT TRACKED | Scanon Realty | Shweta Gouda | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 2 | 11328 | 1 | Standard item for this segment, left blank.
NOT TRACKED | Scanon Realty | Shweta Gouda | Onboarding In Progress | Channel-partner module | BASIC | - | 2 | 11328 | 1 | Standard item for this segment, left blank.
NOT TRACKED | Scanon Realty | Shweta Gouda | Onboarding In Progress | Workflow automation | BASIC | - | 2 | 11328 | 1 | Standard item for this segment, left blank.
NOT TRACKED | Scanon Realty | Shweta Gouda | Onboarding In Progress | Marketing training | BASIC | - | 2 | 11328 | 1 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Lead routing configured | MUST | - | 7 | 11232 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Channel-partner module | MUST | - | 7 | 11232 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Sales / pre-sales training | MUST | - | 7 | 11232 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Admin training | MUST | - | 7 | 11232 | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Website integration | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Meta / Facebook lead-gen | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Property portals (99acres etc) | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | WhatsApp integration | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | WhatsApp templates | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Cloud telephony / IVR | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | DLT (SMS) registration | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Offline dialer / tracker app | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Workflow automation | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Marketing training | BASIC | - | 7 | 11232 | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | Sales / pre-sales training | MUST | - | 4 |  | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | Admin training | MUST | - | 4 |  | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | Website integration | BASIC | - | 4 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | Meta / Facebook lead-gen | BASIC | - | 4 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | WhatsApp integration | BASIC | - | 4 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | WhatsApp templates | BASIC | - | 4 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 4 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | Channel-partner module | BASIC | - | 4 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | Workflow automation | BASIC | - | 4 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunita real estate | Shweta Gouda | Onboarding In Progress | Marketing training | BASIC | - | 4 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Lead routing configured | MUST | - | 18 |  | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Sales / pre-sales training | MUST | - | 18 |  | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Admin training | MUST | - | 18 |  | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Website integration | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Meta / Facebook lead-gen | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Property portals (99acres etc) | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | WhatsApp integration | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | WhatsApp templates | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Cloud telephony / IVR | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | DLT (SMS) registration | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Inventory / units loaded | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Workflow automation | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Marketing training | BASIC | - | 18 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunny Developers & Realtors | Shweta Gouda | Onboarding In Progress | WhatsApp integration | BASIC | - | 6 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunny Developers & Realtors | Shweta Gouda | Onboarding In Progress | WhatsApp templates | BASIC | - | 6 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunny Developers & Realtors | Shweta Gouda | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 6 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunny Developers & Realtors | Shweta Gouda | Onboarding In Progress | Workflow automation | BASIC | - | 6 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Sunny Developers & Realtors | Shweta Gouda | Onboarding In Progress | Marketing training | BASIC | - | 6 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | DLT (SMS) registration | BASIC | - | 3 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 3 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | Workflow automation | BASIC | - | 3 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | Marketing training | BASIC | - | 3 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Website integration | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Meta / Facebook lead-gen | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | WhatsApp integration | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | WhatsApp templates | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | DLT (SMS) registration | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Channel-partner module | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Workflow automation | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Marketing training | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | Channel-partner module | BASIC | - | 6 |  | 4 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Lead routing configured | MUST | - | 5 |  | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Sales / pre-sales training | MUST | - | 5 |  | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Admin training | MUST | - | 5 |  | 0 | Must-have item with no value at all - this work is invisible.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Website integration | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Meta / Facebook lead-gen | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Property portals (99acres etc) | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | WhatsApp integration | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | WhatsApp templates | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Cloud telephony / IVR | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | DLT (SMS) registration | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Offline dialer / tracker app | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Inventory / units loaded | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Workflow automation | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Marketing training | BASIC | - | 5 |  | 0 | Standard item for this segment, left blank.
NOT TRACKED | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | Cloud telephony / IVR | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | DLT (SMS) registration | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | Website integration | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | Property portals (99acres etc) | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | WhatsApp integration | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | WhatsApp templates | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | DLT (SMS) registration | BASIC | - | 2 |  | 3 | Standard item for this segment, left blank.
NOT TRACKED | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | DLT (SMS) registration | BASIC | - | 2 |  | 9 | Standard item for this segment, left blank.
NO LEAD SOURCE | Times Group | Sanket Nampalliwar | Pending on Customer | Website integration | BASIC | N | 50 | 944000 | 9 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | SPR Construction Pvt Ltd (leasing team) | Raahul Ramanan R | Onboarding In Progress | Website integration | BASIC | I | 17 | 735376 | 1 | Not one lead source is live (in progress: website, facebook, google). The CRM has nothing flowing into it.
NO LEAD SOURCE | RUBRICK CONSTRUCTIONS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | Website integration | BASIC | N | 7 | 693840 | 0 | Not one lead source is live (in progress: facebook, google). The CRM has nothing flowing into it.
NO LEAD SOURCE | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | Website integration | BASIC | N | 40 | 481440 | 2 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | SHREYA CAPITAL ADVISORY SERVICES LLP | Sahil Jane | Kickoff Done | Website integration | BASIC | W | 5 | 389400 | 0 | Not one lead source is live (in progress: website, facebook). The CRM has nothing flowing into it.
NO LEAD SOURCE | Sunrise Housing (GHP Group) | Muntazar Mhate | Onboarding In Progress | Website integration | BASIC | I | 11 | 236000 | 0 | Not one lead source is live (in progress: website, facebook). The CRM has nothing flowing into it.
NO LEAD SOURCE | Shree Honda | Sourabh Sahu | Onboarding In Progress | Website integration | BASIC | N | 5 | 210984 | 3 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Jinraj Real Estate | Raahul Ramanan R | Onboarding In Progress | Website integration | BASIC | - | 4 | 174862 | 0 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Propnsafe Realty LLP | Sahil Jane | Kickoff Done | Website integration | BASIC | N | 3 | 172516 | 2 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | R J Real Tech and Properties Pvt Ltd | Sahil Jane | Onboarding In Progress | Website integration | BASIC | W | 8 | 125080 | 0 | Not one lead source is live (in progress: website, facebook). The CRM has nothing flowing into it.
NO LEAD SOURCE | ACL INFRATECH PRIVATE LIMITED (LOVE HOME LLP) | Sahil Jane | Onboarding In Progress | Website integration | BASIC | - | 10 | 121000 | 0 | Not one lead source is live (in progress: facebook, propertyPortal). The CRM has nothing flowing into it.
NO LEAD SOURCE | BRICKSAGE PROPERTIES ADVISORS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | Website integration | BASIC | I | 15 | 106200 | 0 | Not one lead source is live (in progress: website, facebook, propertyPortal). The CRM has nothing flowing into it.
NO LEAD SOURCE | Shree Automotive | Sourabh Sahu | Onboarding In Progress | Website integration | BASIC | N | 4 | 104784 | 5 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Primeplus Realtech Llp | Venkat Viswavardhan | Onboarding In Progress | Website integration | BASIC | W | 20 | 95000 | 0 | Not one lead source is live (in progress: website, facebook, propertyPortal, google). The CRM has nothing flowing into it.
NO LEAD SOURCE | Rare Property Advisory LLP | Raahul Ramanan R | Onboarding In Progress | Website integration | BASIC | - | 4 | 81184 | 0 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | Website integration | BASIC | I | 6 | 74240 | 9 | Not one lead source is live (in progress: website, facebook, google). The CRM has nothing flowing into it.
NO LEAD SOURCE | MSK Realty | Muntazar Mhate | Onboarding In Progress | Website integration | BASIC | I | 3 | 68440 | 0 | Not one lead source is live (in progress: website, facebook). The CRM has nothing flowing into it.
NO LEAD SOURCE | KL HOMES | Shweta Gouda | Open | Website integration | BASIC | - | 2 | 65233 | 0 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | VASTU INFINITY AND VENTURES LLP | Sahil Jane | Onboarding In Progress | Website integration | BASIC | N | 5 | 33000 | 0 | Not one lead source is live (in progress: facebook). The CRM has nothing flowing into it.
NO LEAD SOURCE | Salah Realty Pvt Ltd | Muntazar Mhate | Onboarding In Progress | Website integration | BASIC | N | 2 | 28792 | 0 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | WINTER HOME PROPERTIES | Shweta Gouda | Onboarding In Progress | Website integration | BASIC | - | 2 | 17700 | 0 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Emerald Blue | Muntazar Mhate | Onboarding In Progress | Website integration | BASIC | N | 2 | 11328 | 0 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Scanon Realty | Shweta Gouda | Onboarding In Progress | Website integration | BASIC | N | 2 | 11328 | 1 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Open | Website integration | BASIC | - | 7 | 11232 | 0 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Sunita real estate | Shweta Gouda | Onboarding In Progress | Website integration | BASIC | - | 4 |  | 0 | Not one lead source is live (in progress: propertyPortal). The CRM has nothing flowing into it.
NO LEAD SOURCE | STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Onboarding In Progress | Website integration | BASIC | - | 18 |  | 0 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Yashoda Infra Developer | Shweta Gouda | Onboarding In Progress | Website integration | BASIC | W | 3 |  | 0 | Not one lead source is live (in progress: website, facebook, propertyPortal). The CRM has nothing flowing into it.
NO LEAD SOURCE | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Website integration | BASIC | - | 2 |  | 3 | Not one lead source is live (in progress: propertyPortal). The CRM has nothing flowing into it.
NO LEAD SOURCE | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | Website integration | BASIC | N | 6 |  | 4 | Not one lead source is live (in progress: facebook, propertyPortal). The CRM has nothing flowing into it.
NO LEAD SOURCE | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Website integration | BASIC | - | 5 |  | 0 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | GGC AI Calling | Venkat Viswavardhan | Pending on Customer | Website integration | BASIC | N | 2 |  | 3 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | Website integration | BASIC | - | 2 |  | 3 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
NO LEAD SOURCE | Kohinoor AI Calling | Venkat Viswavardhan | Pending on Customer | Website integration | BASIC | N | 2 |  | 9 | Not one lead source is live (all marked N/blank). The CRM has nothing flowing into it.
PREMATURE HANDOVER | BRICKSAGE PROPERTIES ADVISORS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | (whole deal) | - | - | 15 | 106200 | 0 | Handed over with 5 MUST item(s) not completed: Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training.
GO-LIVE FICTION | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | (whole deal) | - | - | 150 | 1428980 | 3 | Actual Go-Live date is set (2026-05-22) but 1 MUST item(s) are still open: Admin training.
GO-LIVE FICTION | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | (whole deal) | - | - | 36 | 627760 | 0 | Actual Go-Live date is set (2026-07-21) but 1 MUST item(s) are still open: Admin training.
GO-LIVE FICTION | Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Pending on Customer | (whole deal) | - | - | 10 | 532180 | 2 | Actual Go-Live date is set (2026-07-08) but 2 MUST item(s) are still open: Existing leads imported, Admin training.
GO-LIVE FICTION | GRUHAM SPACES LLP | Venkat Viswavardhan | Onboarding In Progress | (whole deal) | - | - | 40 | 481440 | 2 | Actual Go-Live date is set (2026-05-06) but 1 MUST item(s) are still open: Existing leads imported.
GO-LIVE FICTION | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | (whole deal) | - | - | 11 | 428104 | 5 | Actual Go-Live date is set (2026-07-21) but 2 MUST item(s) are still open: Sales / pre-sales training, Admin training.
GO-LIVE FICTION | i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | (whole deal) | - | - | 18 | 347156 | 2 | Actual Go-Live date is set (2026-07-03) but 1 MUST item(s) are still open: Existing leads imported.
GO-LIVE FICTION | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Pending on Customer | (whole deal) | - | - | 6 | 243080 | 3 | Actual Go-Live date is set (2026-07-09) but 1 MUST item(s) are still open: Admin training.
GO-LIVE FICTION | Growthx Estates | Muntazar Mhate | Onboarding In Progress | (whole deal) | - | - | 10 | 118000 | 0 | Actual Go-Live date is set (2026-07-17) but 2 MUST item(s) are still open: Existing leads imported, Admin training.
GO-LIVE FICTION | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | (whole deal) | - | - | 41 | 14660 | 9 | Actual Go-Live date is set (2026-07-07) but 2 MUST item(s) are still open: Pipeline / stages configured, Admin training.
NO FEEDBACK | BRICKSAGE PROPERTIES ADVISORS PRIVATE LIMITED | Sahil Jane | Onboarding In Progress | (whole deal) | - | - | 15 | 106200 | 0 | Handed over without the onboarding feedback form.
STALLED ITEM | Kunwarji Realtors | Sanket Nampalliwar | Onboarding In Progress | Admin training | MUST | W | 150 | 1428980 | 3 | Still 'Waiting on customer' after 77 days since start.
STALLED ITEM | Times Group | Sanket Nampalliwar | Pending on Customer | Sales / pre-sales training | MUST | I | 50 | 944000 | 9 | Still 'Initiated' after 391 days since start.
STALLED ITEM | Times Group | Sanket Nampalliwar | Pending on Customer | Admin training | MUST | I | 50 | 944000 | 9 | Still 'Initiated' after 391 days since start.
STALLED ITEM | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | Admin training | MUST | W | 36 | 627760 | 0 | Still 'Waiting on customer' after 68 days since start.
STALLED ITEM | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | WhatsApp integration | BASIC | W | 36 | 627760 | 0 | Still 'Waiting on customer' after 68 days since start.
STALLED ITEM | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | WhatsApp templates | BASIC | W | 36 | 627760 | 0 | Still 'Waiting on customer' after 68 days since start.
STALLED ITEM | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | Cloud telephony / IVR | BASIC | I | 36 | 627760 | 0 | Still 'Initiated' after 68 days since start.
STALLED ITEM | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | Inventory / units loaded | BASIC | I | 36 | 627760 | 0 | Still 'Initiated' after 68 days since start.
STALLED ITEM | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | Site-visit form | BASIC | I | 36 | 627760 | 0 | Still 'Initiated' after 68 days since start.
STALLED ITEM | Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Pending on Customer | Marketing training | BASIC | W | 36 | 627760 | 0 | Still 'Waiting on customer' after 68 days since start.
STALLED ITEM | Navkar Realty | Venkat Viswavardhan | Pending on Customer | Sales / pre-sales training | MUST | W | 4 | 495600 | 3 | Still 'Waiting on customer' after 34 days since start.
STALLED ITEM | Navkar Realty | Venkat Viswavardhan | Pending on Customer | Admin training | MUST | W | 4 | 495600 | 3 | Still 'Waiting on customer' after 34 days since start.
STALLED ITEM | Navkar Realty | Venkat Viswavardhan | Pending on Customer | WhatsApp templates | BASIC | W | 4 | 495600 | 3 | Still 'Waiting on customer' after 34 days since start.
STALLED ITEM | Axon Developer | Sahil Jane | Onboarding In Progress | Admin training | MUST | W | 30 | 450000 | 0 | Still 'Waiting on customer' after 35 days since start.
STALLED ITEM | Axon Developer | Sahil Jane | Onboarding In Progress | WhatsApp integration | BASIC | I | 30 | 450000 | 0 | Still 'Initiated' after 35 days since start.
STALLED ITEM | Axon Developer | Sahil Jane | Onboarding In Progress | WhatsApp templates | BASIC | I | 30 | 450000 | 0 | Still 'Initiated' after 35 days since start.
STALLED ITEM | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | Sales / pre-sales training | MUST | I | 11 | 428104 | 5 | Still 'Initiated' after 84 days since start.
STALLED ITEM | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | Admin training | MUST | I | 11 | 428104 | 5 | Still 'Initiated' after 84 days since start.
STALLED ITEM | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | Website integration | BASIC | W | 11 | 428104 | 5 | Still 'Waiting on customer' after 84 days since start.
STALLED ITEM | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | WhatsApp integration | BASIC | I | 11 | 428104 | 5 | Still 'Initiated' after 84 days since start.
STALLED ITEM | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | WhatsApp templates | BASIC | I | 11 | 428104 | 5 | Still 'Initiated' after 84 days since start.
STALLED ITEM | NPS DEVELOPERS | Raahul Ramanan R | Onboarding In Progress | Cloud telephony / IVR | BASIC | I | 11 | 428104 | 5 | Still 'Initiated' after 84 days since start.
STALLED ITEM | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Admin training | MUST | W | 15 | 350000 | 3 | Still 'Waiting on customer' after 34 days since start.
STALLED ITEM | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | WhatsApp integration | BASIC | W | 15 | 350000 | 3 | Still 'Waiting on customer' after 34 days since start.
STALLED ITEM | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | WhatsApp templates | BASIC | W | 15 | 350000 | 3 | Still 'Waiting on customer' after 34 days since start.
STALLED ITEM | VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Onboarding In Progress | Offline dialer / tracker app | BASIC | W | 15 | 350000 | 3 | Still 'Waiting on customer' after 34 days since start.
STALLED ITEM | i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | Existing leads imported | MUST | W | 18 | 347156 | 2 | Still 'Waiting on customer' after 48 days since start.
STALLED ITEM | i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | Website integration | BASIC | W | 18 | 347156 | 2 | Still 'Waiting on customer' after 48 days since start.
STALLED ITEM | i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | WhatsApp integration | BASIC | W | 18 | 347156 | 2 | Still 'Waiting on customer' after 48 days since start.
STALLED ITEM | i5 Housing and Properties LLP | Sourabh Sahu | Onboarding In Progress | WhatsApp templates | BASIC | W | 18 | 347156 | 2 | Still 'Waiting on customer' after 48 days since start.
STALLED ITEM | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Pending on Customer | Admin training | MUST | W | 6 | 243080 | 3 | Still 'Waiting on customer' after 39 days since start.
STALLED ITEM | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Pending on Customer | WhatsApp integration | BASIC | W | 6 | 243080 | 3 | Still 'Waiting on customer' after 39 days since start.
STALLED ITEM | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Pending on Customer | WhatsApp templates | BASIC | W | 6 | 243080 | 3 | Still 'Waiting on customer' after 39 days since start.
STALLED ITEM | VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Pending on Customer | Offline dialer / tracker app | BASIC | W | 6 | 243080 | 3 | Still 'Waiting on customer' after 39 days since start.
STALLED ITEM | Shree Honda | Sourabh Sahu | Onboarding In Progress | Existing leads imported | MUST | I | 5 | 210984 | 3 | Still 'Initiated' after 367 days since start.
STALLED ITEM | Shree Honda | Sourabh Sahu | Onboarding In Progress | Sales / pre-sales training | MUST | I | 5 | 210984 | 3 | Still 'Initiated' after 367 days since start.
STALLED ITEM | Shree Honda | Sourabh Sahu | Onboarding In Progress | Admin training | MUST | I | 5 | 210984 | 3 | Still 'Initiated' after 367 days since start.
STALLED ITEM | Shree Honda | Sourabh Sahu | Onboarding In Progress | WhatsApp integration | BASIC | W | 5 | 210984 | 3 | Still 'Waiting on customer' after 367 days since start.
STALLED ITEM | Shree Honda | Sourabh Sahu | Onboarding In Progress | WhatsApp templates | BASIC | W | 5 | 210984 | 3 | Still 'Waiting on customer' after 367 days since start.
STALLED ITEM | Shree Honda | Sourabh Sahu | Onboarding In Progress | Cloud telephony / IVR | BASIC | I | 5 | 210984 | 3 | Still 'Initiated' after 367 days since start.
STALLED ITEM | Shree Honda | Sourabh Sahu | Onboarding In Progress | Workflow automation | BASIC | W | 5 | 210984 | 3 | Still 'Waiting on customer' after 367 days since start.
STALLED ITEM | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | Sales / pre-sales training | MUST | I | 6 | 129800 | 4 | Still 'Initiated' after 34 days since start.
STALLED ITEM | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | Admin training | MUST | I | 6 | 129800 | 4 | Still 'Initiated' after 34 days since start.
STALLED ITEM | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | WhatsApp integration | BASIC | I | 6 | 129800 | 4 | Still 'Initiated' after 34 days since start.
STALLED ITEM | Leonaara PVt LTD | Sahil Jane | Onboarding In Progress | WhatsApp templates | BASIC | I | 6 | 129800 | 4 | Still 'Initiated' after 34 days since start.
STALLED ITEM | Shree Automotive | Sourabh Sahu | Onboarding In Progress | Existing leads imported | MUST | I | 4 | 104784 | 5 | Still 'Initiated' after 367 days since start.
STALLED ITEM | Shree Automotive | Sourabh Sahu | Onboarding In Progress | Sales / pre-sales training | MUST | I | 4 | 104784 | 5 | Still 'Initiated' after 367 days since start.
STALLED ITEM | Shree Automotive | Sourabh Sahu | Onboarding In Progress | Admin training | MUST | I | 4 | 104784 | 5 | Still 'Initiated' after 367 days since start.
STALLED ITEM | Shree Automotive | Sourabh Sahu | Onboarding In Progress | WhatsApp integration | BASIC | W | 4 | 104784 | 5 | Still 'Waiting on customer' after 367 days since start.
STALLED ITEM | Shree Automotive | Sourabh Sahu | Onboarding In Progress | WhatsApp templates | BASIC | W | 4 | 104784 | 5 | Still 'Waiting on customer' after 367 days since start.
STALLED ITEM | Shree Automotive | Sourabh Sahu | Onboarding In Progress | Cloud telephony / IVR | BASIC | I | 4 | 104784 | 5 | Still 'Initiated' after 367 days since start.
STALLED ITEM | Shree Automotive | Sourabh Sahu | Onboarding In Progress | Workflow automation | BASIC | W | 4 | 104784 | 5 | Still 'Waiting on customer' after 367 days since start.
STALLED ITEM | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | Existing leads imported | MUST | W | 6 | 74240 | 9 | Still 'Waiting on customer' after 56 days since start.
STALLED ITEM | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | Sales / pre-sales training | MUST | W | 6 | 74240 | 9 | Still 'Waiting on customer' after 56 days since start.
STALLED ITEM | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | Website integration | BASIC | I | 6 | 74240 | 9 | Still 'Initiated' after 56 days since start.
STALLED ITEM | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | Meta / Facebook lead-gen | BASIC | W | 6 | 74240 | 9 | Still 'Waiting on customer' after 56 days since start.
STALLED ITEM | Ribitto Private Limited | Muntazar Mhate | Pending on Customer | DLT (SMS) registration | BASIC | I | 6 | 74240 | 9 | Still 'Initiated' after 56 days since start.
STALLED ITEM | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | Pipeline / stages configured | MUST | W | 41 | 14660 | 9 | Still 'Waiting on customer' after 70 days since start.
STALLED ITEM | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | Admin training | MUST | W | 41 | 14660 | 9 | Still 'Waiting on customer' after 70 days since start.
STALLED ITEM | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | Website integration | BASIC | I | 41 | 14660 | 9 | Still 'Initiated' after 70 days since start.
STALLED ITEM | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | WhatsApp integration | BASIC | W | 41 | 14660 | 9 | Still 'Waiting on customer' after 70 days since start.
STALLED ITEM | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | WhatsApp templates | BASIC | W | 41 | 14660 | 9 | Still 'Waiting on customer' after 70 days since start.
STALLED ITEM | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | Cloud telephony / IVR | BASIC | I | 41 | 14660 | 9 | Still 'Initiated' after 70 days since start.
STALLED ITEM | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | Inventory / units loaded | BASIC | I | 41 | 14660 | 9 | Still 'Initiated' after 70 days since start.
STALLED ITEM | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | Site-visit form | BASIC | I | 41 | 14660 | 9 | Still 'Initiated' after 70 days since start.
STALLED ITEM | SPR Construction Pvt Ltd | Raahul Ramanan R | Onboarding In Progress | Marketing training | BASIC | W | 41 | 14660 | 9 | Still 'Waiting on customer' after 70 days since start.
STALLED ITEM | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Lead routing configured | MUST | W | 2 |  | 3 | Still 'Waiting on customer' after 35 days since start.
STALLED ITEM | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Pipeline / stages configured | MUST | W | 2 |  | 3 | Still 'Waiting on customer' after 35 days since start.
STALLED ITEM | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Existing leads imported | MUST | W | 2 |  | 3 | Still 'Waiting on customer' after 35 days since start.
STALLED ITEM | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Sales / pre-sales training | MUST | W | 2 |  | 3 | Still 'Waiting on customer' after 35 days since start.
STALLED ITEM | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Admin training | MUST | W | 2 |  | 3 | Still 'Waiting on customer' after 35 days since start.
STALLED ITEM | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Property portals (99acres etc) | BASIC | W | 2 |  | 3 | Still 'Waiting on customer' after 35 days since start.
STALLED ITEM | Strata Capital Holdings | Shweta Gouda | Onboarding In Progress | Cloud telephony / IVR | BASIC | I | 2 |  | 3 | Still 'Initiated' after 35 days since start.
STALLED ITEM | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | Existing leads imported | MUST | I | 6 |  | 4 | Still 'Initiated' after 32 days since start.
STALLED ITEM | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | Sales / pre-sales training | MUST | W | 6 |  | 4 | Still 'Waiting on customer' after 32 days since start.
STALLED ITEM | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | Admin training | MUST | W | 6 |  | 4 | Still 'Waiting on customer' after 32 days since start.
STALLED ITEM | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | Meta / Facebook lead-gen | BASIC | W | 6 |  | 4 | Still 'Waiting on customer' after 32 days since start.
STALLED ITEM | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | Property portals (99acres etc) | BASIC | W | 6 |  | 4 | Still 'Waiting on customer' after 32 days since start.
STALLED ITEM | Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Pending on Customer | Offline dialer / tracker app | BASIC | W | 6 |  | 4 | Still 'Waiting on customer' after 32 days since start.
STALLED ITEM | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Projects created | MUST | I | 5 |  | 0 | Still 'Initiated' after 40 days since start.
STALLED ITEM | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Pipeline / stages configured | MUST | I | 5 |  | 0 | Still 'Initiated' after 40 days since start.
STALLED ITEM | Veedhan Buildtech | Sahil Jane | Onboarding In Progress | Existing leads imported | MUST | I | 5 |  | 0 | Still 'Initiated' after 40 days since start.
STALLED ITEM | Sangram Group | Muntazar Mhate | Pending on Customer | Sales / pre-sales training | MUST | W | 5 |  | 4 | Still 'Waiting on customer' after 48 days since start.
STALLED ITEM | Sangram Group | Muntazar Mhate | Pending on Customer | Admin training | MUST | W | 5 |  | 4 | Still 'Waiting on customer' after 48 days since start.
STALLED ITEM | Sangram Group | Muntazar Mhate | Pending on Customer | WhatsApp integration | BASIC | W | 5 |  | 4 | Still 'Waiting on customer' after 48 days since start.
STALLED ITEM | Sangram Group | Muntazar Mhate | Pending on Customer | WhatsApp templates | BASIC | W | 5 |  | 4 | Still 'Waiting on customer' after 48 days since start.
STALLED ITEM | Mythri Builder AI Calling | Venkat Viswavardhan | Pending on Customer | Cloud telephony / IVR | BASIC | W | 2 |  | 3 | Still 'Waiting on customer' after 88 days since start.

## 14. Coverage by Deal
Coverage by Deal - how much of the checklist is actually done
Sorted worst-first by MUST %. 'Not required' % is the share of the whole checklist this owner disclaimed on this deal.
Deal | Owner | Segment | Stage | Licences | Billed | Days since start | MUST done | MUST % | BASIC % | Not tracked | 'Not required' % | Open MUST items
SPR Construction Pvt Ltd (leasing team) | Raahul Ramanan R | Developer | Onboarding In Progress | 17 | 735376 | 13 | 0/7 | 0 | 58 | 0 | 34 | User logins created, Projects created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
RUBRICK CONSTRUCTIONS PRIVATE LIMITED | Sahil Jane | Developer | Onboarding In Progress | 7 | 693840 | 6 | 0/7 | 0 | 67 | 0 | 45 | User logins created, Projects created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
Jinraj Real Estate | Raahul Ramanan R | Developer | Onboarding In Progress | 4 | 174862 | 5 | 0/7 | 0 | 8 | 8 | 3 | User logins created, Projects created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
R J Real Tech and Properties Pvt Ltd | Sahil Jane | Developer | Onboarding In Progress | 8 | 125080 | 6 | 0/7 | 0 | 42 | 5 | 18 | User logins created, Projects created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
Primeplus Realtech Llp | Venkat Viswavardhan | Developer | Onboarding In Progress | 20 | 95000 | 4 | 0/7 | 0 | 17 | 0 | 21 | User logins created, Projects created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
Rare Property Advisory LLP | Raahul Ramanan R | Channel partner | Onboarding In Progress | 4 | 81184 |  | 0/7 | 0 | 0 | 15 | 0 | User logins created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Channel-partner module, Sales / pre-sales training, Admin training
KL HOMES | Shweta Gouda | Broker | Open | 2 | 65233 |  | 0/6 | 0 | 0 | 18 | 0 | User logins created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
Makliv Infra Consulting Pvt Ltd. | Sahil Jane | Channel partner | Open | 7 | 11232 | 1 | 0/7 | 0 | 0 | 14 | 3 | User logins created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Channel-partner module, Sales / pre-sales training, Admin training
STONE AND ACRES REALITY CONSULTATNTS LLP | Raahul Ramanan R | Developer | Onboarding In Progress | 18 |  | 7 | 0/7 | 0 | 0 | 14 | 0 | User logins created, Projects created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
SHREYA CAPITAL ADVISORY SERVICES LLP | Sahil Jane | Developer | Kickoff Done | 5 | 389400 | 8 | 1/7 | 14 | 50 | 0 | 39 | Projects created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
VRUSHABADRI DEVELOPERS | Sahil Jane | Developer | Onboarding In Progress | 8 | 241900 | 18 | 1/7 | 14 | 75 | 4 | 47 | Projects created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
ACL INFRATECH PRIVATE LIMITED (LOVE HOME LLP) | Sahil Jane | Channel partner | Onboarding In Progress | 10 | 121000 | 6 | 1/7 | 14 | 45 | 2 | 45 | Lead routing configured, Pipeline / stages configured, Existing leads imported, Channel-partner module, Sales / pre-sales training, Admin training
Veedhan Buildtech | Sahil Jane | Developer | Onboarding In Progress | 5 |  | 40 | 1/7 | 14 | 8 | 14 | 3 | Projects created, Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
Propnsafe Realty LLP | Sahil Jane | Broker | Kickoff Done | 3 | 172516 | 14 | 1/6 | 17 | 58 | 1 | 45 | Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
BRICKSAGE PROPERTIES ADVISORS PRIVATE LIMITED | Sahil Jane | Broker | Onboarding In Progress | 15 | 106200 | 5 | 1/6 | 17 | 42 | 1 | 37 | Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
GAGAN TONDON | Shweta Gouda | Broker | Onboarding In Progress | 9 | 80830 | 7 | 1/6 | 17 | 50 | 4 | 16 | Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
Strata Capital Holdings | Shweta Gouda | Broker | Onboarding In Progress | 2 |  | 35 | 1/6 | 17 | 8 | 9 | 3 | Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
Times Group | Sanket Nampalliwar | Developer | Pending on Customer | 50 | 944000 | 391 | 2/7 | 29 | 100 | 0 | 66 | Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
WINTER HOME PROPERTIES | Shweta Gouda | Channel partner | Onboarding In Progress | 2 | 17700 | 5 | 2/7 | 29 | 45 | 7 | 16 | Pipeline / stages configured, Existing leads imported, Channel-partner module, Sales / pre-sales training, Admin training
Yashoda Infra Developer | Shweta Gouda | Developer | Onboarding In Progress | 3 |  | 21 | 2/7 | 29 | 42 | 4 | 13 | Lead routing configured, Pipeline / stages configured, Existing leads imported, Sales / pre-sales training, Admin training
Scanon Realty | Shweta Gouda | Broker | Onboarding In Progress | 2 | 11328 | 11 | 2/6 | 33 | 58 | 5 | 24 | Lead routing configured, Pipeline / stages configured, Sales / pre-sales training, Admin training
PANCHRATNA SKYLINE PRIVATE LIMITED | Shweta Gouda | Developer | Onboarding In Progress | 5 | 326860 | 11 | 3/7 | 43 | 33 | 4 | 11 | Lead routing configured, Pipeline / stages configured, Sales / pre-sales training, Admin training
Palli Developers and Consultants LLP | Muntazar Mhate | Channel partner | Onboarding In Progress | 5 | 153400 | 13 | 3/7 | 43 | 55 | 0 | 42 | Existing leads imported, Channel-partner module, Sales / pre-sales training, Admin training
MSK Realty | Muntazar Mhate | Channel partner | Onboarding In Progress | 3 | 68440 | 8 | 3/7 | 43 | 55 | 0 | 47 | Existing leads imported, Channel-partner module, Sales / pre-sales training, Admin training
Sunny Developers & Realtors | Shweta Gouda | Developer | Onboarding In Progress | 6 |  | 5 | 3/7 | 43 | 42 | 5 | 8 | Lead routing configured, Existing leads imported, Sales / pre-sales training, Admin training
Salah Realty Pvt Ltd | Muntazar Mhate | Broker | Onboarding In Progress | 2 | 28792 | 14 | 3/6 | 50 | 92 | 0 | 58 | Existing leads imported, Sales / pre-sales training, Admin training
Emerald Blue | Muntazar Mhate | Broker | Onboarding In Progress | 2 | 11328 | 6 | 3/6 | 50 | 92 | 0 | 61 | Existing leads imported, Sales / pre-sales training, Admin training
Sunita real estate | Shweta Gouda | Broker | Onboarding In Progress | 4 |  | 6 | 3/6 | 50 | 25 | 10 | 8 | Pipeline / stages configured, Sales / pre-sales training, Admin training
Sohum Estate Agency (Sameer Chheda) | Muntazar Mhate | Broker | Pending on Customer | 6 |  | 32 | 3/6 | 50 | 67 | 1 | 47 | Existing leads imported, Sales / pre-sales training, Admin training
Doff Estate | Venkat Viswavardhan | Developer | Pending on Customer | 29 | 523919 | 12 | 4/7 | 57 | 92 | 1 | 50 | Existing leads imported, Sales / pre-sales training, Admin training
Navkar Realty | Venkat Viswavardhan | Developer | Pending on Customer | 4 | 495600 | 34 | 4/7 | 57 | 92 | 0 | 45 | Existing leads imported, Sales / pre-sales training, Admin training
Sunrise Housing (GHP Group) | Muntazar Mhate | Developer | Onboarding In Progress | 11 | 236000 | 25 | 4/7 | 57 | 67 | 0 | 42 | Existing leads imported, Sales / pre-sales training, Admin training
Shree Honda | Sourabh Sahu | Developer | Onboarding In Progress | 5 | 210984 | 367 | 4/7 | 57 | 67 | 0 | 50 | Existing leads imported, Sales / pre-sales training, Admin training
Aryma Infra (OPC)Pvt Ltd | Sahil Jane | Developer | Onboarding In Progress | 5 | 120336 | 27 | 4/7 | 57 | 58 | 5 | 21 | Lead routing configured, Sales / pre-sales training, Admin training
Shree Automotive | Sourabh Sahu | Developer | Onboarding In Progress | 4 | 104784 | 367 | 4/7 | 57 | 67 | 0 | 50 | Existing leads imported, Sales / pre-sales training, Admin training
Ribitto Private Limited | Muntazar Mhate | Channel partner | Pending on Customer | 6 | 74240 | 56 | 4/7 | 57 | 73 | 0 | 39 | Existing leads imported, Channel-partner module, Sales / pre-sales training
GGC AI Calling | Venkat Viswavardhan | Developer | Pending on Customer | 2 |  | 98 | 4/7 | 57 | 83 | 2 | 63 | Existing leads imported, Sales / pre-sales training, Admin training
Mythri Builder AI Calling | Venkat Viswavardhan | Developer | Pending on Customer | 2 |  | 88 | 4/7 | 57 | 50 | 5 | 42 | Existing leads imported, Sales / pre-sales training, Admin training
Kohinoor AI Calling | Venkat Viswavardhan | Developer | Pending on Customer | 2 |  | 89 | 4/7 | 57 | 92 | 1 | 63 | Existing leads imported, Sales / pre-sales training, Admin training
SWARAJYA REALTORS PRIVATE LIMITED | Venkat Viswavardhan | Broker | Onboarding In Progress | 35 | 258420 | 25 | 4/6 | 67 | 83 | 1 | 50 | Sales / pre-sales training, Admin training
Growthx Estates | Muntazar Mhate | Broker | Onboarding In Progress | 10 | 118000 | 19 | 4/6 | 67 | 100 | 0 | 47 | Existing leads imported, Admin training
SKYTOWN Group | Venkat Viswavardhan | Developer | Pending on Customer | 20 | 733488 | 21 | 5/7 | 71 | 75 | 0 | 34 | Existing leads imported, Admin training
Shri Krish Housing and Properties Pvt Ltd | Muntazar Mhate | Developer | Pending on Customer | 10 | 532180 | 21 | 5/7 | 71 | 67 | 0 | 47 | Existing leads imported, Admin training
NPS DEVELOPERS | Raahul Ramanan R | Developer | Onboarding In Progress | 11 | 428104 | 84 | 5/7 | 71 | 67 | 0 | 47 | Sales / pre-sales training, Admin training
VENDSPACEZ PRIVATE LIMITED | Venkat Viswavardhan | Developer | Onboarding In Progress | 15 | 350000 | 34 | 5/7 | 71 | 75 | 0 | 39 | Existing leads imported, Admin training
Leonaara PVt LTD | Sahil Jane | Developer | Onboarding In Progress | 6 | 129800 | 34 | 5/7 | 71 | 75 | 1 | 50 | Sales / pre-sales training, Admin training
MiCasa Realty | Raahul Ramanan R | Developer | Onboarding In Progress | 5 | 82000 | 13 | 5/7 | 71 | 83 | 0 | 50 | Sales / pre-sales training, Admin training
SPR Construction Pvt Ltd | Raahul Ramanan R | Developer | Onboarding In Progress | 41 | 14660 | 70 | 5/7 | 71 | 42 | 0 | 37 | Pipeline / stages configured, Admin training
Sangram Group | Muntazar Mhate | Developer | Pending on Customer | 5 |  | 48 | 5/7 | 71 | 83 | 0 | 45 | Sales / pre-sales training, Admin training
Properties Boutique | Sahil Jane | Broker | Onboarding In Progress | 7 | 61360 | 20 | 5/6 | 83 | 92 | 1 | 53 | Existing leads imported
VASTU INFINITY AND VENTURES LLP | Sahil Jane | Broker | Onboarding In Progress | 5 | 33000 | 18 | 5/6 | 83 | 75 | 1 | 50 | Existing leads imported
Blueroof India | Muntazar Mhate | Broker | Onboarding In Progress | 2 | 14160 | 28 | 5/6 | 83 | 92 | 0 | 50 | Sales / pre-sales training
Kunwarji Realtors | Sanket Nampalliwar | Developer | Onboarding In Progress | 150 | 1428980 | 77 | 6/7 | 86 | 100 | 0 | 29 | Admin training
Calicut Landmark Builders Pvt. Ltd | Raahul Ramanan R | Developer | Pending on Customer | 36 | 627760 | 68 | 6/7 | 86 | 50 | 0 | 29 | Admin training
GRUHAM SPACES LLP | Venkat Viswavardhan | Developer | Onboarding In Progress | 40 | 481440 | 126 | 6/7 | 86 | 100 | 0 | 53 | Existing leads imported
Axon Developer | Sahil Jane | Developer | Onboarding In Progress | 30 | 450000 | 35 | 6/7 | 86 | 75 | 1 | 39 | Admin training
i5 Housing and Properties LLP | Sourabh Sahu | Developer | Onboarding In Progress | 18 | 347156 | 48 | 6/7 | 86 | 75 | 0 | 39 | Existing leads imported
Rajparis Civil Construction | Muntazar Mhate | Developer | Pending on Customer | 15 | 300000 | 20 | 6/7 | 86 | 67 | 0 | 26 | Sales / pre-sales training
VAZHRAA NIRMAAN PRIVATE LIMITED | Venkat Viswavardhan | Developer | Pending on Customer | 6 | 243080 | 39 | 6/7 | 86 | 75 | 0 | 50 | Admin training
Voora Developers | Raahul Ramanan R | Developer | Pending on Customer | 21 | 785880 | 189 | 7/7 | 100 | 100 | 0 | 18
Dhanraj Realbuild Llp | Venkat Viswavardhan | Developer | Pending on Customer | 6 | 538552 | 89 | 7/7 | 100 | 100 | 0 | 42
Apex Realty Hub | Sahil Jane | Broker | Onboarding In Progress | 5 | 81420 | 14 | 6/6 | 100 | 83 | 0 | 42